Annual Review/Programme Completion Review
Programme Title	Somaliland CSSF Programme
Programme ID	C-AFR-0030
Country and Region	Somaliland (Somalia), Africa
IATI Unique ID
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO)
Total Budget	ODA: £2.0m	Non-ODA: £0.8m
Budget this FY	ODA: £1.2m	Non-ODA: £0.4m
Spend this FY	ODA: £780,287	Non-ODA: £238,363
Time Frame	Start Date: 1 April 2021	End Date: 31 March 2023

Outputs	Scale of Delivery
Advisory support, mentoring, training and limited material investment increases the capacity of the Somaliland Police and Somaliland National Army to effectively plan, lead and deliver their operations	3
Advisory support, mentoring and training increases the capacity of the Somaliland security sector to better coordinate their operations, share intelligence and deliver the security response to the November 2022 Presidential elections	1
Advisory support, mentoring, training and limited material investment increases the capacity of the Somaliland Ministry of Interior and Ministry of Defence to provide effective civil oversight of the police and army and to engage with parliamentary scrutiny	1
International Election Observation for the 2021 parliamentary and local council elections increases public trust in the legitimacy of the electoral process and the new Parliament	4
Advisory support, mentoring, training and limited material investment enables the Internal Affairs, Security and Defence Committee and other relevant committees in Parliament to scrutinise the work of security institutions and support passage of effective security legislation.	2
Advisory support to senior officials in the police, defence sector and parliament delivers sustained influence with current leadership, while engagement with training reform builds links with the next generation of Somaliland leaders.	2
Support for women to be represented in bodies responsible for oversight and training of the armed forces and other meaningful roles leads to more women in prominent security sector roles.	2
Analysis of security risks linked to the Berbera Corridor and drivers of religious extremism and support for terrorist groups helps shape Somaliland’s national security planning and informs future UK funded security sector interventions.	4
Overall Scale of Output Delivery	2

Outcome Assessment	The programme was approved in November (Q3 FY21/22) and hence during the assessment period the programme was under early inception stages. Key outputs were not delivered as expected and the implementing partner had delivery challenges. The outcomes are ambitious and may not be achievable within the programme implementation period and may need to be reviewed.
Overall Outcome Progress Rating:		Amber red
Overall Risk Rating:		Medium/High

Summary of Programme Performance
Year	2021/22		2022/23	2023/24
Programme Rating	2	Amber/Red	n/a	n/a
Risk Rating	Medium/High

What Support Did the UK Provide in FY 21/22?
Advisory support, short term training and mentoring and limited material support with Somaliland Ministry of Defence, Ministry of Interior, Army, Police and the Parliament’s Internal Affairs, Security and Defence Committee and Constitutional, Human Rights and Justice Committee.

Support to the sole apolitical international election observation mission covering the 2021 parliamentary and local council elections. It provided an expert assessment of the pre-election preparations and of the election day itself. The mission trained and deployed short-term observers to four regions, collecting data for a confidential interim report delivered to the National Electoral Commission and the international community, and providing recommendations for the 2022 Presidential elections.

Key Lessons
- Given the challenges of building relationships any future programme design needs to consider political buy in as a necessary pre-condition for change and progress, rather than being assumed to exist.
- For security institutions, such as the Army, to be responsive, internal reform is essential. Future programmes should prioritise institutional reforms to avoid overly focussing on individuals.
- An exit and sustainability strategy should be built into programme design.
- An actively engaged and inclusive board is essential for effective oversight and governance. The programme currently lacks senior championing within the Somalia country plan.
- Evidence of what works, and lessons learned from previous interventions should be integrated into the design and delivery of new activities, tempering optimism with realism and contextual awareness. Untested assumptions should be monitored, and emerging evidence applied to improve the programme.

Key Recommendations for FY 21/22
- Develop a sustainability and exit plan and roll out immediately relevant transition measures especially for the programme components ending by 31 March 2023.
- Revise and update the results framework to rationalise the outcome and output indicators and milestones ensuring they are realistic and achievable yet stretching enough and in line with delivery and contextual realities.
- Use evidence and lessons learned, including from long-standing support on defense and policing institutional support, to consolidate outcomes and develop better indicators.
- Embed the current programme within broader Somaliland Strategy.
- Develop clearer governance structures.