Annual Review/Programme Completion Review (21/22)
Programme Title	CSSF West Africa Regional Response Programme (RRP)
Programme ID	C-AFR-0038
Country and Region	Burkina Faso, Cameroon, Cote d’Ivoire, The Gambia, Ghana
IATI Unique ID
HMG Partners / (Lead in bold)	Foreign, Commonwealth & Development Office (FCDO), Ministry of Defence (MOD)
Total Budget	ODA: £1.04m	Non-ODA: £0.4m
Budget this FY	ODA: £1.04m	Non-ODA: £0.4m
Spend this FY	ODA: £1.04m	Non-ODA: £0.37m
Time Frame	Start Date: September 2021	End Date: March 2022

Outputs	Individual Output Rating
Effective support to targeted national government groupings and regional bodies (such as ECOWAS, G7++ Friends of Gulf of Guinea, Yaounde Architecture, Accra Initiative).	1
Enhanced capacity of targeted institutions and beneficiaries of RRP projects.	3
Improved knowledge among programme beneficiaries about the drivers of regional instability (including the gendered drivers and impacts) and about potential solutions to the challenges.	4
Overall Rating of Output Delivery:	3

Summary of Programme Performance
Year	2019/20		2020/21		2021/22
Programme Rating	N/A	N/A	N/A	N/A	3*	Amber**
Risk Rating	N/A		N/A		Medium
Note: Output* / Outcome score**. FY21/22 is the first year of the programme.

What Support Did the UK Provide in FY 21/22?
The Programme funded a diverse set of projects to prevent instability in the West Africa region:
Activity to counter violent extremism/terrorism in coastal states including
- support to develop a road map for peace in Northern Ghana integrating elements of this into local government district budgets and plans.
- facilitating the setting-up of a Northern Ghana Security Platform to counter the threats of violent extremism and terrorism and establishing Peace and Security Response Teams in four pilot communities.
- Supporting dialogues in border areas of Ghana and Burkina Faso between farming and herder - communities to reduce the threats of extremism; providing community level social support to strengthen resilience and developing a road map for coordination of state actors in Ghana and Burkina Faso to respond to violent extremist threats.
- The funding of research and analysis on terrorism and extremism in Cote d’Ivoire to inform future programming.
Support to peaceful elections in The Gambia by developing codes of conduct for peaceful Presidential and parliamentary elections which were agreed by all six presidential candidates and 85% of parliamentary candidates. This was accompanied by support for responsible media reporting and use of social media related to the elections.
Support to strengthen human rights monitoring related to the anglophone crisis in Cameroon; developing a stronger network of civic actors to continue human rights monitoring; capacity building of human rights defenders, local influencers and community policing. There was agreement with the EU to sustain support on human rights monitoring and training human rights defenders.
Key Lessons
Small projects have worked best when part of a broader, integrated approach to address the threats of violent extremism, linking into national and local activities.
Consensus building and stakeholder analysis is crucial for project success. Combatting extremism effectively requires the active engagement of senior government actors, security forces, civil society organisation, community members and other actors. UK access to senior decision makers has contributed to project success and wider impact. Strong links to UK strategic interests maximise post engagement.
Small projects offer the chance for significant scale-up or replication across the region. Posts and implementers should work together to secure follow-on funding for projects where appropriate to offer a higher chance of catalytic effect.
The flexible fund mechanism can work well but activities in smaller Posts with less capacity need central CSSF support.
Key Recommendations for FY 22/23
- Make the MEL arrangements for the new Upstream Threats Programme (UTP) more proportionate to ease the reporting burden on implementing partners and Posts.
- Support projects that can more directly achieve catalytic effect, by demonstrating clear pathways for effect as part of project design, and with clear exit/transition plans.
- Increase the focus on gender equality and social inclusion (GESI) by setting out the specific GESI results each project is intending to achieve, how this will happen and how results will be measured.
- Make the new programme more integrated by demonstrating connections in the theory of change and developing systems for better aggregation of individual project results.