Annual Review/Programme Completion Review (21/22)

A. Summary Sheet
NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Colombia Peace and Stabilisation Programme (CPSP)
Programme ID
Country and Region	Colombia, Americas
IATI Unique ID
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO)
Total Budget	ODA: £69,400,000 from 2015-16 until FY 2021-22	Non-ODA: 0
Budget this FY	ODA: £6,295,000	Non-ODA: 0
Spend this FY	ODA: £6,246,707	Non-ODA: 0
Time Frame	Start Date: 1 April 2021	End Date: 31 March 2022

Outputs	Individual Output Rating
Support the Colombian State to effectively implement the peace agreement	4
Enhancing the participation of civil society in the implementation of the peace accords	4
Building the capacity and capability of the Government of Colombia (GoC) and civil society to tackle threats to peace, particularly human rights abuses and environmental crime	4
Overall Rating of Output Delivery	4

Outcome Assessment	The programme and its implementers successfully managed to adapt to numerous challenges throughout the review period (including ongoing Covid-19 restrictions, fluid security dynamics, the outbreak of nationwide protests and Presidential elections) to continue to deliver high performing programming. The team’s flexibility, resilience and innovation enabled the programme to continue to support the delivery of critical outcomes in support of peace and stability in Colombia, as evidenced by this Review.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Medium-low

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c		2021/22
Programme Rating	A	A	A	A	A+	A	A	4	Green	4	Green
Risk Rating	Medium	Medium		Medium		Medium		Medium-Low		Medium-Low
Programme changes during this period		The programme and its implementers successfully managed to adapt to the ongoing Covid-19 pandemic and associated restrictions, security dynamics, outbreak of nationwide protests and Presidential political elections.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 21/22?

The UK provided £6.25m of support to Colombia in FY21/22 via the Colombia Peace and Stabilization Programme. CSSF funding continued to be aimed at supporting Colombia’s efforts to achieve long-term peace by implementing the peace agreement with the Revolutionary Armed Forces of Colombia (FARC-EP) and tackling the underlying causes of conflict. The programme continued to ensure coordination and synergies with other HMG policy and programmatic interventions in Colombia and the region, including regional Countering Illicit Economies Programme (CIEP), Department for Business, Energy and Industrial Strategy (BEIS) and International Climate Finance (ICF) work. During the period under review, the UK funded 14 bilateral and multilateral projects that were delivered by different implementing partners via the programme.

This included providing support to the following areas:

1. Colombian institutions tasked with implementing and overseeing the elements of the peace agreement;
2. The UN Multi-Partner Trust Fund (MPTF) supporting reintegration, rural development and assistance to victims;
3. The designated peace monitoring mission of the Organisation of American States;
4. The International Organisation for Migration, which included work to support the Police and the transitional justice mechanism as well as improving community security and respect for human rights;
5. The UN Office on Drugs and Crime’s work supporting investigations and prosecutions linked tackling deforestation;
6. The UN High Commissioner for Human Rights on monitoring the human rights situation in Colombia
7. Access for victims to the transitional justice system with a focus especially on preventing sexual violence in conflict (PSVI) and;
8. Support to three Colombian and international NGOs and foundations working on peace and stability.

Key Results for FY 21/22:

- The five year anniversary of the peace agreement was reached in November 2021 and represented an important milestone in Colombia's history of peace, reconciliation and stabilisation. Following concerted lobbying efforts, high-level events to celebrate the anniversary showcased UK support, particularly in the areas of reintegration, transitional justice and PDET delivery.
- In tackling environmental crime, the collaboration between CSSF-ICF continued as part of the TEFOS programme, with a key highpoint being the legal classification of deforestation as an environmental crime coupled with increased prominence of the issue in national security considerations and strategies.
- The CPSP team has continued to support and work in coordination with international actors to improve cooperation and effective support for the implementation of the peace agreements, including during a period as chair of the MPTF. UK influence was particularly evident in contributing towards the MPTF work plan with increased focus and funding secured for themes of security, community participation and the environment.
- Following the outbreak of nationwide protests, the CSSF team engaged with different implementers to adapt existing projects to respond. This included using the existing Congressional support project to fund additional activities to enable engagement between Congressional representatives and young people in the cities most affected by the national strikes. This created channels of communication between Congress and young people and resulted in the latter engaging in the development of Bills to be submitted to Congress.
- The CSSF police programme has started generating positive results in conflict prevention and community relations in conflict-affected areas. The presence, participation, and activities carried out by the conflict transformation teams resulted in peaceful protests taking place in 98% of the municipalities prioritised by the project.
- Support on transitional justice – in particular, supporting access for women, indigenous and LGBT+ communities to seek justice with the transitional system and with a particular focus being on gender-based violence and rights relating to the environment.
- Together with the Prosperity Programme, the CPSP strengthened UK-Colombia market development opportunities for ex-combatants, victims and crop substitution participants who have benefited from UK investments in productive coffee and cocoa projects. This initiative is part of the embassy's commitment to generate improved income and livelihoods for conflict-affected communities.

Key Lessons
- The UK’s expertise and influence plays an important part of international efforts to support the peace process – especially regarding MPTF donor coordination. The UK is a key and trusted partner of the Government of Colombia (GoC) and international partners. Therefore, programming activity plays a key part in wider diplomatic efforts.
- A blend of multilateral and bilateral funding continued to provide the UK with impactful and wide ranging interventions and the team has adapted to a changing fiscal landscape whilst still having impact and influence.
- Despite the complex security situation and various challenges around the peace implementation itself, the Colombian peace process is one of very few examples of a peace process that is progressing. Its hopeful continued success will provide lessons to future upcoming peace talks anticipated by an incoming administration in Colombia and with other armed and criminal groups.
- An innovation led within this programme and by the programme team laid the foundation for new environmental crime programming to be taken up by another CSSF programme in the Portfolio working regionally.
- The programme responded to, and evolved activities, in an agile way to respond to 2021 social unrest.

Key Recommendations for FY 21/22
- Develop links with the incoming administration on peace agenda, positioning UK as a key influencer.
- Police reform and support to the GoC on Security Sector Reform could be a growing area of work for the programme, taking into account the opportunities with the new government and the impact of the security situation.
- Prepare for, and respond to, upcoming political events – e.g. the publication of the Truth commission’s final report as well as elections – allowing space for the programme to evolve and respond accordingly.
- Explore new approaches on security and justice - working closely with regional CSSF programming and anticipating the complexities of potential upcoming negotiations with other criminal groups.
- Explore support to proposed peace talks with ELN in coordination with the Government and other members of the international community, maximising civil society participation and taking into account lessons learned from the FARC process.
- Reduce CSSF contributions to TEFOS, given the scaling up by BEIS, whilst ensuring CSSF capacity and expertise is still available to ICF colleagues - ensuring that the links on environment and peace remain adequately covered by UK programming. Share learning/model for conflict sensitivity training of ICF teams, with appropriate time and resources to be supported to do so.
- Conduct a full assessment of the Programmes application of the FCDO Programme Operating Framework requirements on Paris Alignment and Environmental Protection, which can be used as a case study for the CSSF network.