CSSF Annual Review (21/22) - Summary Sheet

This Summary Sheet captures the headlines on programme performance, lessons and recommendations over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Combatting Illicit Economies Programme (CIEP)
Programme ID	C-AMS-0003
Country and Region	Latin America: Colombia, Peru, Panama, Ecuador, Brazil and Venezuela
IATI Unique ID	CSSF-04-000004
HMG Partners / (Lead in bold)	Foreign and Commonwealth Office / (became Foreign, Commonwealth and Development Office (FCDO) midway through financial year)
Total Budget	ODA: £ 3,380,000	Non-ODA: £0
Budget this FY	ODA: £ 2,935,000	Non-ODA: £0
Spend this FY	ODA: £2,914,260	Non-ODA: 0
Time Frame	Start Date: April 2020	End Date: March 2025

Outputs	Scale of Delivery
# of outputs harvested showing increased capacity (including civil society) to demand or influence State action on illicit economies	4
# of outputs harvested showing increased domestic collaboration and adoption of more effective practices based upon evidence across institutions engaged in tackling illicit economies	5
# of outputs harvested showing increased regional / international collaboration and adoption of more effective practices based upon evidence across institutions engaged in tackling illicit economies	3
Overall Scale of Output Delivery	4

Outcome Assessment	The CIEP has delivered 17 outcome level changes against its target of 15 demonstrating significant results against its outcome of increasing country and regional level awareness and effectiveness in combatting illicit economies. / Over the 21/22 FY the programme has demonstrated substantial achievements exceeding all of its planned outcome targets, even as the programme grew from its original three country focus (Preu, Colombia and Panama) to six (Peru, Colombia, Panama, Venezula, Ecuador, Brazil). For each outcome there are strong qualititative and quantitative results, alongside a number of secondary and tertiary results that are outside of the results framework. The programme demonstrates strong CSSF principles in action and presents a number of useful lessons for wider CSSF and FCDO programmes.
Overall Outcome Progress Rating:		4
Overall Risk Rating:		Amber/Green

Summary of Programme Performance
Year	2020/21a		2021/22		2022/23		2023/24		2024/25
Programme Rating	2	Amber	4	Amber/ / Green
Risk Rating	Medium		Medium
Programme changes during this period			During the 21/22 FY the programme adapted both its focus to Illicit Financial flows (IFFs) and Money Laundering (ML), expanded activity into three new countries (Ecuador, Venezula, Brazil) and developed new thematic activity on Enviromental Crime, and research on State Threat activity.
Note: a scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?

The Combatting Illicit Economies Programme (CIEP) seeks to tackle global illicit financial flow (IFFs) and money laundering dynamics, as they impact Latin America and generate instability, organized crime and corruption risks that threatens UK interests. The programme works regionally but with a particular focus on Colombia, Peru, Panama, and Venezuela (expanded to Brazil and Ecuador for FY21/22). The programme engages in a mixed delivery model, which encompasses work with Non-Governmental Organisations (NGOs), multilateral organisations, commercial implementers and through deployed HMG advisors working with regional counterparts to build institutional capacity.

In financial year 21/22, the programme engaged in the following activity:

- Support to regional investigative journalism
- Tackling the role of illicit corporate structures in sustaining organized crime dynamics
- Enhancing capacity to interrogate and share digital evidence in complex cases
- Promoting design of improved criminal justice policies against organised crime
- Tackling anti-corruption dynamics sustaining drug trafficking
- Strengthening international supply chains against risks from illegal gold
- Removing barriers to using anti-corruption mechanisms for women and LGBTQ+ communities
- Strengthening civil society capacity to tackle corruption, illicit economies and serious organized crime
- Promoting regional action to reduce environmental crime in the Amazon
- Analysis of regional tax and financial systems vulnerabilities
- Developing capacity to tackle trade-based money laundering
- Technical support to develop illicit financial flows analytical capacity and allied processes

Key Results for FY 20/21:

The 2021/22 CIEP programme outcome measures the effect the programme has had on improving organisational effectiveness to identify, tackle and suppress illicit economies generated by Latin America. At an aggregate level the programme has demonstrated results against all 17 of the outcome measurements across six countries. The overall outcome is broken down into three key indicators which assess results based on the HMG Outcome Harvesting Methodology as follows:

Outcome indicator 1: Outcomes harvested showing improved, evidence-based processes being adopted by organizations engaged in tackling illicit economies regionally. Against an envisioned target of 7 results, the CIEP is assessed as achieving 10 outcomes in 21/22.

Outcome indicator 2: Outcomes harvested showing improved, evidence-based domestic coordination between organizations engaged in tackling illicit economies regionally. Against an envisioned target of 5 results, the CIEP is assessed as achieving 2 outcomes in 21/22.

Outcome indicator 3: Outcomes harvested showing improved, evidence based cross-border coordination between organizations engaged in tackling illicit economies regionally, and improved compliance with international standards. Against an envisioned target of 3 results, the CIEP is assessed as achieving 5 outcomes in 21/22.

Key Lessons

- Well positioned, regionally established expertise that speaks Spanish is unusual in region amongst donors seeking country or regional reform. The unique position of the CSSF advisory team has allowed it to make rapid progress with host governments and allow rapid adaptation to circumstances and opportunities. The CSSF Americas model should be strongly considered as an operating model across the CSSF.
- The adaptability of the CIEP has allowed it to seize first mover advantage on opportunities, and adapt quickly to emerging threats, through flexing resource and rapidly developing projects to scope entry points. Linking such adaptability to core UK and host government priorities is difficult, showcasing the CIEP’s strength in engagement.
- A more strategic focus of the CIEP around IFFs/ML has strengthened the purpose and justification of the programme as it has expanded across more countries. This strategic focus has been critical in securing buy in from HMG partners as the CIEP “Brand” has developed securing buy in from new posts.
- Establishing HMG/CSSF presence is easier in smaller countries such as Panama and Ecuador as a thought leader and where smaller resources can have greater impact. It is harder to distinguish the CIEP USP in larger countries such as Colombia which have larger donor presence, requiring greater resources to achieve similar effect.
- The CSSF has shown a competitive advantage compared to wider donors by having an adaptive advisory core, and the capacity to roam to new opportunities in region. This is unique compared to larger donor programmes which whilst grander in scale, lack the flexibility or adaptability of the CSSF expertise. Critically CIEP advisors have demonstrated the ability to diagnose, develop and apply solutions, engage political actors and sustain technical relations until longer delivery mechanisms can be developed.
- The agility of the CIEP needs to be balanced with stable programming “core” backed by long serving expertise to allow for impact to be achieved. There is a risk of incoherence and minimal impact if a programme is constantly evolving and just reacting to opportunity without allowing time for projects to demonstrate impact (normally 3 years). For the current model to be sustained it is essential that the programme actively plans and considers succession planning of its advisors.
- Linked to the issue of a “core” of longer term programming is a need to ensure the CIEP allows consideration a wide range of actors beyond governmental organisations or existing lines of Multilateral effort. Whilst the CIEP has admirable NGO delivered projects, engagement with the wider private sector should be considered to help generate sustained change beyond political cycles.
- Novel amongst many donors and wider developmental approaches is the CIEP’s join up across the “whole of system” when considering IFF/ML flows from law enforcement through to conviction/deterrence. This is demonstrated particularly amongst coherence of HMG security efforts and with host nation governments demonstrating a key lesson for new CSSF regional programmes or Portfolios.

Key Recommendations for FY 21/22

- Given the reliance of the CIEP programme on Spanish speaking regional advisors, prompt succession planning needs to be a critical consideration.
- Programme management staffing needs to be reviewed as the programme shifts into new countries and new thematic areas with consideration needed over the balance of C4 capacity. The CIEP should consider the location of its advisors with the shift of the programme from three to six countries. In particular, Ecuador should be considered for potentially permanently basing an Advisor in Quito.
- Given some of the CIEP programme overlaps with wider CSSF transnational threats work, the programme should explore potential overlaps and funding options.
- CIEP team should explore further engagement with the FCDO Open Societies team to explore potential wider funding support on Open/Beneficial Ownership work across the region.
- CIEP could explore strengthening host government law enforcement understanding of Open Registries to support IF investigations.
- JFU MEL advisory support should engage with CIEP team to design collective Impact Indicators across the CIEP/SOC programming in region, alongside support from the JFU economist to improve VFM indicators.
- It would be worth the CIEP team exploring strengthening its results framework to capture second and third order benefits of the CIEP. For example wider enabling results for HMG through the CIEP are not currently routinely captured.
- The CIEP programme should directly engage with the CSSF SOC Enablers Programme leads to share research and capability on combatting environmental crime particularly on the IGARAPE project.