Programme Completion Review (21/22)
A. Summary Sheet
Programme Title	Algeria Programme
Programme ID	C-MNA-0001
Country and Region	Algeria, Middle East and North Africa
IATI Unique ID	CSSF-06-000001
HMG Partners	Foreign, Commonwealth & Development Office (FCDO)
Total Budget	ODA: £31.7m	Non-ODA: £0
Budget this FY	ODA: £2m	Non-ODA: £0
Spend this FY	ODA: £1.66m	Non-ODA: £0
Time Frame	Start Date: April 2016	End Date: March 2022

Outputs	Individual Output Rating
1: Media professionals, parliamentarians and CSOs are supported to be more effective in engaging with Algerian public.	3
2: Improved knowledge and understanding of Algerian state institutions and CSOs of policy issues relating to the protection of rights of women, vulnerable groups, victims of trafficking and domestic violence	4
3: Algerian institutions at national level are supported to take forward economic reform plans; and at a local level targeted employment opportunities are provided, particularly for marginalised groups.	3
4: The programme extends its network of local stakeholders and delivers UK expertise for the wider embassy benefit	1
Overall Rating of Output Delivery	3

Outcome Assessment	This year, the Conflict Security and Stability Fund (CSSF) programme has continued to work to support Algeria in urgently needed reform. A challenging operating environment was further compounded by the ongoing COVID-19 pandemic. However, the programme continued towards its core objectives while taking opportunities to maximise evidence-based adaptive programming on priority areas. / Over the course of the full lifespan of the programme, outcomes have been best met through established partners with existing good working relationships in country. Refreshing the evidence regularly, particularly pre and post Hirak, coupled with the strong focus on exiting sustainably has meant that outcomes are likely to have good longevity.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		Medium

Summary of Programme Performance
Year	2019/20		2020/21		2021/22
Programme Rating	B	B	3	Amber	3	Amber
Risk Rating	Medium		Medium		Medium

Note: Output / Outcome score

What Support Did the UK Provide in FY 21/22?

The CSSF programme supported Integrated Review priorities of open societies and conflict resolution. The aim was to tackle the risk of conflict and instability through political and governance focussed interventions that reflect citizens' needs and economic realities whilst retaining a focus on marginalised groups, including women and girls. The programme had three main outcomes to try and achieve this:
Increased trust and citizen engagement: Through support to state broadcasters and civil society organisations, particularly focussing on youth. And by working with the Algerian Parliament to increase engagement.

Protected human rights, especially of women and vulnerable groups: Through support to strengthen parliament’s ability to implement constitutional provisions on gender. And by focussing on countering human trafficking and supporting victims.

Increased economic opportunities and fairer, more accountable, distribution of social assistance: Through supporting youth in Tamanrasset, a remote area in the south of Algeria to promote systemic change and by supporting the Government of Algeria (GoA) to identify households most vulnerable to reforms to subsidies on key products.

Key Results for FY 21/22
- Algerian civil society organisations are benefiting from media training & expertise. Support has included launching new TV channels with a specific aim of reaching youth to provide practical advice on COVID-19 and to fight mis/disinformation about the vaccine rollout in Algeria.
- 120 criminal justice practitioners were trained on the identification, investigation, and prosecution of transnational trafficking in person cases.
- In Tamanraset, 230 young Algerians, almost half of which were female, were supported in their job search or business launch. 41 graduates (60% women) were placed in jobs and 11 graduates started their own business.
- Adaptive programming has contributed to the reduction of risks related to wildfires and built vulnerable forests resilience. This included Rehabilitating 178,78Ha of forest.
- Continued progress towards supporting the country subsidies reform, which has been included in a new finance law (2022) and the design and implementation of the Cash Compensation Program (CCP) to protect those most vulnerable to reforms.
- The Algerian Parliament in partnership with the Coalition of Women Parliamentarians to strengthened skills of MPs and staff on public procurement and evidence-based policy making.

Key Lessons
- The focus on exiting well has increased potential for sustainability. A proactive approach to secure other donor funding for Embassy designed projects has helped to ensure sustainably.
- Exit planning at outset, agreed with partners has been instrumental in delivering value for money. Exit strategies must be considered as part of programme design both in country and by central teams in London. Being able to plan a responsible programme exit will deliver greater value for money and reduce conflict sensitivity risks.
- Small amounts of funding can deliver real impact, but it can take time to see progress. Even established partners often need significantly longer than anticipated to deliver in a context such as Algeria.
- Relationships really matter - in an operating context such as Algeria progress is likely to be slow and opportunities to engage with the GoE are limited. It is therefore important to capitalise on opportunities when they arise and the CSSF has provided a flexible tool to help enable this.

Key Recommendations for FY 21/22
- Continue to seek additional programme funds from alternative funding streams, particularly in education and security sectors.
- Ensure that a point of contact in the Embassy is in place to invest in developing relationships with the World Bank and to ensure the project is delivered.
- Continue relationships with former implementing partners. Create a partner alumni network and tracker.
Create and promote an evidence pack to share across FCDO MENA Posts. This should include key achievements, lessons, and links to evidence. To support this approach and to pass on institutional knowledge Research Analysts should be heavily involved. Research Analysts of a high level of expertise and a method to retain some of the institutional knowledge.