Annual Review (21/22)

A. Summary Sheet

Programme Title	Egypt Programme
Programme ID	C-MNA-0004
Country and Region	Egypt, Middle East and North Africa
IATI Unique ID	CSSF-06-000002
HMG Partners / (Lead in bold)	Foreign, Commonwealth & Development Office (FCDO)
Total Budget	ODA: £57.55m	Non-ODA: £0.75m
Budget this FY	ODA: £4m	Non-ODA: £0
Spend this FY	ODA: £3.82m	Non-ODA: £0
Time Frame	Start Date: April 2018	End Date: March 2022

Outputs	Individual Output Rating
1.1 (Economic, Arab Women’s Empowerment Fund (AWEF) Women are aware of and access jobs in the Ready-Made Garment (RMG) sector and firms employ empowering working conditions that results in increased productivity and product quality	4
1.2 (Economic, AWEF) Women are aware of and access jobs in the citrus sub-sector and firms employ empowering working conditions that results in increased productivity and product quality	4
1.3 (Economic, AWEF) Disadvantaged women have improved access to digital financial services and are financially included	4
1.4 (Economic, AWEF) AWEF targets social norms that hamper women’s economic empowerment working through public media such as radio and film	4
2.1 Health Education, United Nations International Children's Emergency Fund (UNICEF) through World Health Organisation (WHO) Education directorates are equipped to offer continuous teacher professional development programmes to school workforce	2
2.2 (Health Education, WHO) Prevention and response COVID 19 mechanisms to address acute socio-economic impacts of COVID 19	3
2.3 (Health Education, WHO) Enhancing Governance of National Health Stakeholders to enable efficient functions	3
2.4 (Health Education, United Nations Office on Drugs and Crime (UNODC) Improvements in health provision for drug users in communities reintegrating prisoners	1
3.1 (Migration, STARS) Psychosocial support, education, work opportunities, and legal counsel are provided for unaccompanied children using a centre so that they are better prepared to survive and manage day-to-day life in Cairo;	3
3.2 (Migration,STARS) Psychosocial support, education and professional development, and legal assistance are provided to vulnerable youth, adults, and families to allow for local integration in Cairo and help them recover from and prevent modern slavery.	3
4.1 (National Council for Women [NCW] and UN Women) The government of Egypt develops a high-impact inclusive National Action Plan (NAP) on Women, Peace, & Security to advance women's rights, stability & sustainable development efforts through meaningful &effective participation of Egyptian women & men at all levels.	3
4.2 (Social Development, United Nations Development Programme (UNDP)/ Ministry of Social Solidarity (MoSS) Development of curriculum for social protection awareness	3
4.3 (Social Development, UNDP/MoSS) Structures of MoSS services enhanced via improved accountability and governance systems, quality checks of services, improved reporting at MoSS departments levels and responsive mechanisms for social care and other services provided by MoSS.	3
4.4 (Social Development, UNDP/MoSS) Monitoring and Evaluation (M&E) systems established	3
5.1 Research: Deployable Civilian Expert (DCE) bringing together open-source information, expertise and producing comprehensive overview of current understanding.	3
Overall Rating of Output Delivery	3

Outcome Assessment	The Egypt CSSF programme was in a transition year in financial year 21/22 as it responded to the new strategic direction emanating from the CSSF Strategic Review, which resulted in new Fund Level Outcomes, and the new Middle East and North Africa (MENA) Strategy. This meant many projects closing and some new projects starting. Funding restraints also meant a much-reduced size of the programme – reducing from £12m to £4m. The programme aimed to respond to three core areas of work: civil society and civic space; justice and human rights; conflict and Counter Terrorism. Given the transitional period, there was a lack of an overarching cohesive strategy at programme level and though projects achieved outcomes individually, overall strategic direction was missing. Despite these factors, there is evidence to suggest that progress has been made toward meeting most intended outcomes and outputs. It should be noted that an already challenging operating environment was further compounded by the on-going impact of Covid-19. Some programming responded to this.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		Medium

Summary of Programme Performance
Year	2019/20		2020/21		2021/22
Programme Rating	A	A	4	Green	3	Amber
Risk Rating	Medium		Medium-High		Medium

Note: Output / Outcome score

What Support Did the UK Provide in FY 21/22?

CSSF funding was provided to eight projects with the objective of delivering five outcomes:

- Improve accessibility and quality of employment
- Reinforcement and improvement of education and health services (Covid-19 response)
- Improved management and support systems for refugees and asylum seekers arriving in Egypt
- Improved governance in key sectors of women's social empowerment
- Improved evidence-base on the drivers of conflict and the nature of the criminal justice system, to design future UK engagement

Key Results for FY 21/22

- Women, Peace and Security National Action Plan (NAP) produced and ready to be published (with UN Women)
- Psychosocial support, education, work opportunities, and legal counsel provided for unaccompanied children including 1,198 persons in the psycho-educational programme and 9,997 children receiving additional psycho-social support.
- 185,000 economically impoverished women given improved digital options in managing their business finances
- Seven companies in the Ready-Made Garment (RMG) sector adopted or expanded the Supervisory Skills Training (SST) model
- 1095 women trained in safety, hygiene (including on Covid-19) in the citrus fruit processing sector
- An in-depth review was produced on the drivers of conflict in Sinai
- An in-depth review of criminal justice sector covering “known pathways and blind spots”

Key Lessons

- Importance of regular engagement with centre/London on strategic direction in order to be able to adapt to new steers and as sounding board on key decisions.
- Good use has been made of enabling CSSF programmes to be complementary to political objectives within the Embassy which is enhancing political access and influence (PAI).
- There is recognition that our ability to enable wide-spread change in Egypt is very limited, thus a focus on catalytic/influencing work is being rightly prioritised.

Key Recommendations for FY 21/22

- An overarching cohesive strategy at programme level should be put into place to ensure projects complement one another and work towards a unified, clear purpose.
- Consider and explore options relating to programming in the state threats sector
- Take a more proactive approach to programme design by, for example, putting out invitations to tender on key programming areas.
- Consider adapting programming approach, including looking at implementing partners without such high overhead costs to achieve better value for money for the UK taxpayer.
- Explore options to fund civil society, or civil society-like, organisations which can contribute collectively to building a “positive” stability whilst realising that not all endeavours will succeed.
- Ensure a sufficient focus on good exit-planning and sustainability for the projects which are closing.
- Explore opportunities for using non-ODA funds including carefully assessing potential options in the security sector.
- Conduct a new conflict analysis to better understand the current dynamics and consider areas for strategic UK engagement.
- Demonstrate utilisation of CSSF funded research projects in Embassy work and/or future CSSF programming.