Annual Review (21/22)

A. Summary Sheet

Programme Title	Iraq Programme
Programme ID	C-MNA-0007
Country and Region	Iraq, Middle East and North Africa
IATI Unique ID	CSSF-06-000029
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO)
Total Budget	ODA: £32.82m	Non-ODA: £2.04m
Budget this FY	ODA: £7.85m	Non-ODA: £1m
Spend this FY	ODA: £8.17m	Non-ODA: £1.2m
Time Frame	Start Date: April 2021	End Date: March 2024

Outputs	Individual Output Rating
1.1 Working Groups in Military Education Development Project (MEDP) target institutions work with MEDP experts to identify gaps and co-develop updated materials	1
1.2 Modernised, standardised curriculum progressively introduced and embedded across MEDP target institutions	1
1.3 Disinformation by hostile actors is reported and reduced	4
1.4 United Nations Development Programme (UNDP) strengthens resilience to Violent Extremist Organisations (VEO) through reconstruction of essential service infrastructure in target governorates, supporting Internally Displaced Persons (IDP) returns and generating livelihoods	4
1.5 Irregular migration from Iraq is reduced.	2
2.1 The technical capacity of Independent High Electoral Commission (IHEC) staff at Headquarters and in governorates offices is improved through a comprehensive capacity building strategy	3
2.2 Technical Assistance (TA) delivered that aims to build capabilities; develop/change motives; support creation of an enabling environment for reforms.	4
2.3 UNDP Funding Facility for Stabilisation (FFS) develops an effective exit strategy having developed government of Iraq capabilities to manage ongoing/future reconstruction and rehabilitation needs to enable sufficient basic service delivery.	3
2.4 Leads are generated, British Embassy Baghdad receives demand-led requests from the government of Iraq (GOI), and interventions are designed appropriately by the Technical Assistance Facility for Iraq (TAFFI) to respond to requests.	4
3.1 Civil society is provided with opportunities to participate in electoral processes and able to access necessary and accurate information.	3
3.2 Moderate / reformist voices can share their views and content whilst being protected online	4
3.3 Women led organisations in Iraq have improved capability and access to resources to develop and implement programming on Women, Peace and Security (WPS) priorities in Iraq	4
Overall Rating of Output Delivery	3

Outcome Assessment	Currently the programme has a reasonable expectation that it will deliver progress towards outcomes over its lifetime, but this is highly dependent on external factors. The programme has delivered good work which increases the chances of a more transparent government, strengthened relations between the Iraqi state and its citizens, and grassroots activity in support of the United Nations Security Council resolution (UNSCR) 1325 WPS agenda. However, at the time of writing, Iraq is gripped by a protracted political crisis which has prevented the Parliamentarians elected taking their seats and may escalate into wider conflict. Underperformance by the implementing partner on the Military Education project risks missing delivery targets on this work, though closure was value for money for the taxpayer and well managed by the programme team. If this is re-procured quickly, relationships within the institutional system are there to support better delivery in future.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		High

Summary of Programme Performance
Year	2019/20		2020/21		2021/22
Programme Rating	B	B	3	Amber	3	Amber
Risk Rating	High		High		High
Overall Rating of Output Delivery: 3 / Overall Outcome Progress Rating: Amber / Overall Risk Rating: Amber

What Support Did the UK Provide in FY 21/22?

- A range of activities were funded aimed at reducing potential threat to the UK originating from within Iraq; supporting the development of an accountable Iraqi state; and increasing the ability of citizens to have their voices heard and interact with authorities.
- The UK provided the following support during this period:
  - Technical Assistance to government bodies in the Federal Government of Iraq and Kurdistan Regional Government (KRG).
  - Capacity building support to Women’s Rights Organisations (WRO) across all regions of Iraq
  - Support to the electoral process, including capability building within the electoral commission through the United Nations Assistance Mission for Iraq (UNAMI), countering elections focused disinformation online, and election monitoring through the United Nations Office for Project Services (UNOPS.)
  - Funding for International Organization for Migration (IOM) to facilitate reintegration of returnees in line with UK Counter Terror (CT) and Counter-Daesh Coalition objectives.
  - Funding for infrastructure projects in three priority governorates liberated from Daesh through the Funding Facility for Stabilisation.

Key Results for FY 21/22

- 11 technical assistance ventures were provided over the FY 21/22 across a wide range of Government of Iraq and Kurdish Regional Government ministries and bodies, which has been positively received. For example, support provided to the Financial Intelligence Unit at the Central Bank of Iraq has operationalised anti-money laundering and CT financing reporting from banks across the country.
- 13 Women’s Rights Organisations received grant funding and initial training which has begun to create a nationwide network across all governorates of Iraq and attracted other donor funding to grow over future years. This has included support to WROs in liberated governorates working with minorities who endured serious hardships under Daesh, such as Yazidi and Christian women. There are strongly positive prospects for this support to be extended to a further 13 organisations in FY 22/23, with many proposals already received.
- With UK support, UNAMI was able to provide capacity building support to election officials and communications staff at the Independent High Electoral Commission and provide election monitoring staff at over 1000 polling stations – the largest ever United Nations elections monitoring mission.
- Counter-disinformation support was provided to help defend the legitimacy of the electoral process, resulting in hundreds of instances of disinformation being removed, and increased capacity for moderate voices to operate online.
- Short term support for the International Organisation for Migration provided mental health and reintegration support for 70 Iraqi citizens repatriated from Belarus, and enabled the return and reintegration of others from IDP camps in northeast Syria.
- Critical infrastructure projects were enabled through the Funding Facility for Stabilisation across liberated governorates which had not previously benefitted in an equitable way. UK leadership in donor coordination strengthened the FFS’s planning for the 2023 transition to the Government of Iraq.
Key Lessons
- WPS programming based on well researched, targeted grants to existing grass roots organisations is an effective way to deliver quickly and effectively in this space. The development of an application process, as well as resource and capability limitations in grassroots organisations increasing duration of due diligence processes, should be factored into timeline planning.
- UK donor coordination in addition to programme management engagement with large funding facilities offers a time intensive but effective way for programme teams to secure assurances that delivery is more likely to be in line with UK priorities.
- Programming in support of delivery of elections stands the best chances of success when provided in a holistic fashion; in close partnership with political staff and the international community as an enabler to political level discussions and commitments. For example, this includes building the capacity of domestic electoral authorities, supporting the development of regulations, as well as provision of international election monitoring.
- Programming seeking to develop training for security institutions requires regular engagement with senior staff from commercial partners and UK officials to regularly re-affirm buy-in to concept and content.

Key Recommendations for FY 21/22

- Maintain the UK’s strong involvement in coordination donor during the final phase of the Funding Facility for Stabilisation (FFS) Iraq.
- Review the programme’s results framework, including ensuring output and outcome indicators are fit for purpose. Central team in London to provide Monitoring, Evaluation and Learning (MEL) support to help take this forward, as team in country does not have the capacity.
- Secure third-party monitoring for at least part of the programme, to develop the means to verify partner reporting.
- Recruit at least one additional member of Country Based Staff (CBS) possibly located in Erbil to strengthen coordination and leverage of UK funding in the Kurdish Region of Iraq (KRI). Over time, consider relocating a current United Kingdom Based (UKB) BE Baghdad project role to Erbil, depending on platform capacity.
- Focus on expectation management with partners when Technical Assistance Ventures (TAVs) close or conclude. TAVs have been successful to the extent of reducing beneficiary willingness to work with other partners. There are opportunities to further TAVs – e.g. with the Financial Intelligence Unit (FIU) but objectives must be actively managed and time-bound.
- Ensure capacity building support provided to the WPS project activity Implementing Partner is responsive to needs articulated by WROs under WVF to ensure best Value for Money and chance of sustainability.