Programme Completion Review (21/22)

A. Summary Sheet

Programme Title	Lebanon: Political Reform Programme
Programme ID	C-MNA-0020
Country and Region	Lebanon, Middle East and North Africa
IATI Unique ID	CSSF-06-000034
HMG Partners / (Lead in bold)	Foreign, Commonwealth & Development Office (FCDO)
Total Budget	ODA: £7.69m	Non-ODA: £0
Budget this FY	ODA: £3m	Non-ODA: £0
Spend this FY	ODA: £2.75m	Non-ODA: £0
Time Frame	Start Date: April 2019	End Date: March 2022

Outputs	Individual Output Rating
1 – Women supported to take an active part in decision making and gender equality promoted.	4
2 – Institutional capacity and systems built, incentives for constructive engagement and reform created in support of greater accountability and transparency, more responsive policy, and more equitable opportunities.	4
3 – Capacity and capabilities of civil society strengthened to enable effective domestic pressure for change and more constructive state-society engagement.	2
Overall Rating of Output Delivery	3

Outcome Assessment	Outcome 1: Modest progress through the holding of the first public hearing in the Lebanese parliament by the Women and Children’s Parliamentary Committee and upskilling of Parliamentary staff to support future public hearings; creation and support of a feminist platform to amplify gender issues; and rollout of a e-governance platform which allows for oversight and scrutiny within parts of Lebanese public administration. / Outcome 2: while a small number of reformers (including a handful of new Members of Parliament, in the women’s movement and within the Central Inspection) have been supported, their ability to build substantial coalitions which effect change has been limited by a number of contextual challenges/intransigence within the prevalent confessional system.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		High

Summary of Programme Performance
Year	2019/20		2020/21		2021/22
Programme Rating	A	A	3	Green	3	Amber
Risk Rating	Medium		Medium-High		High

Note: Output / Outcome score

What Support Did the UK Provide in FY 21/22?

- Continued support to Government of Lebanon’s Central Inspection (CI) in roll-out of e-governance platform to improve governance, increase transparency and reduce corruption;
- Support via the Westminster Foundation for Democracy (WFD) to increased public accountability of Parliament, enhancing dialogue with other state institutions and civil society;
- Support for the continued development of the IMPACT e-governance platform;
- Support via UN Women for the consolidation of a stronger and more cohesive women’s rights movement, supporting women to become more politically active.

Key Results for FY 21/22

- Roll-out of e-governance inspection module to 138 government entities;
- World Bank make disbursal of Economic Security Network (ESN) contingent on the use of IMPACT;
- Roadmap produced outlining consolidation and action for Feminist Platform beyond lifetime of this project;
- Support to Parliament included the drafting of the first Committee strategic plan and holding of a public enquiry (the Women and Child Committee);
- Support to UN Women enabled 450 women to position themselves to run in the 2022 elections, increasing their networks and capacities for future campaigns. 157 female candidates ultimately ran for office, which represented 15% of the total number of candidates running, and an almost 39% increase
- Advocacy with Parliamentary Committees influenced the passing of 18 pieces of legislation, including a Bill on Sexual Harassment.

Key Lessons
- Ongoing advocacy by the Embassy beyond the funding cycle of programme should remain part of the longer-term active programme management, particularly in contexts where long-term investment and effort is needed to achieve substantive change;
- Similarly, factoring in a longer-term plan to transition to other donors should be considered throughout a programme’s life-cycle. This is consistent with using Conflict Security and Stability Fund (CSSF) funding as seed money for other donors and funding streams, rather than considering it as long-term developmental assistance;
- Rigorously challenging implementors on programme evaluations (recognising programme ‘failure’ can be a viable option if lessons are learnt) is important to understand where and why previous attempts to achieve change have not succeeded. This challenge will be better informed if programme staff can tap into an Embassy-wide overview of the engagement of other major donors;
- Programmes which operate in extremely challenging environments should develop robust operational contingencies (e.g. to plan for and mitigate the effects of embassy evacuations) as part of their risk planning.

Key Recommendations for FY 21/22

- Long term plan needed for transitioning programmes to other funding/donors;
- Consider the sustainability of having implementers and beneficiaries which depend on a single point of failure;
- Consider carefully the level of ambitions given the challenging political context;
- Due diligence should be undertaken to ensure that programme elements haven’t been undertaken previously by other donors. If so, understand the reasons why it failed and ensure that new ideas are sufficiently different to avoid the same mistakes;
- Ensure that the Theory of Change is realistic, with a correlation between the likely outputs and significant progress against the outcomes feasible;
- Continuity and order in programme documentation (labelling, storage, chronology and version control);
- Consider whether future HMG interventions would be better targeted at a narrow section of the political governance needs or spread across a range of issues, given the likely constraints on total spend and relative inactivity of other donors in this space.