Programme Completion Review (21/22)

A. Summary Sheet
Programme Title	Lebanon: Security Programme
Programme ID	C-MNA-0021
Country and Region	Lebanon, Middle East and North Africa
IATI Unique ID	CSSF-06-000005
HMG Partners / (Lead in bold)	Foreign, Commonwealth & Development Office (FCDO), Ministry of Defence (MOD)
Total Budget	ODA: £42.77m	Non-ODA: £50.87m
Budget this FY	ODA: £9.34m	Non-ODA: £7.97m
Spend this FY	ODA: £10.85m	Non-ODA: £10.13m
Time Frame	Start Date: April 2019	End Date: March 2022

Outputs	Individual Output Rating
Output 1: Lebanese Armed Forces (LAF) officers and soldiers trained to plan and conduct urban operations that are conflict and gender sensitive and International Humanitarian Law (IHL) and Law of Armed Conflict (LOAC) compliant.	4
Output 2: LAF Land Border Regiments (LBRs) trained to plan and conduct land border operations that are conflict and gender sensitive and IHL and LOAC compliant.	4
Output 3: Intelligence led policing capability enabling Internal Security Forces (ISF) improved responsiveness to communities, aligned with community policing principles to prevent and combat crime and threats to community safety and security.	4
Output 4: At-risk youth gain access to a safe haven, individualized, targeted and gender-sensitive services and assistance with pressing basic needs that otherwise act as obstacles to rehabilitation and reintegration. The focus will be in Tripoli, Beirut and the Palestinian camps.	4
Output 5: The Conflict Security and Stability Fund (CSSF) Lebanon Security Programme operates in an adaptive way, responding to emerging challenges and opportunities.	4
Overall Rating of Output Delivery	4

Outcome Assessment	The Lebanon Security Programme (LSP) has delivered well against its outcome indicators in FY 21/22 and is a very well managed programme. The LSP has continued the effective training of the LAF LBRs and provided wide ranging support to the Lebanese ISF, including on the delivery of the ISF’s internal reform strategy, at a time of acute strain on these institutions and the country more broadly. Coordination between agencies, accountability and the capacity of agencies to conduct IHL/human rights compliant operations have improved across the reporting period. While public trust in security institutions has not increased, the backdrop of Lebanon’s severely deteriorating economic and security context and consequent rise in unrest and public safety concerns, makes this unsurprising. There is more work to be done to consolidate inroads of success in inter-agency interoperability, cooperation and donor coordination around internal security. Exit planning and sustainability has been considered last financial year and should continue to be a focus.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		Medium-High

Summary of Programme Performance
Year	2019/20		2020/21		2021/22
Programme Rating	B	B	4	Green	4	Amber
Risk Rating	High		Medium-High		Medium-High
Note: Output / Outcome score

What Support Did the UK Provide in FY 21/22?

- Trained and mentored the LAF Land Border Regiments (LBRs) to better plan and conduct pro-active, intelligence-led operations;
- Improved cooperation and interoperability between LAF and ISF. Training also sought to improve accountability, transparency and human rights performance of ISF and LAF;
- Reduced vulnerability of conflict and violence via targeted rehabilitation and communication activities with Lebanese and Palestinian communities;
- Supplied solar panels to enable Command and Control Centres to continue operation during power outages, and spare parts to ISF and LAF fleets. Purchased Personal Protective Equipment (PPE) for female soldiers deployed at the Syrian border.

Key Results for FY 21/22

- Trained 850 LAF soldiers and officers on border security operations (774 males and 76 females) and 523 LAF soldiers and officers on internal security operations. 39 non-commissioned officers were trained on Train-the-Trainer courses;
- Established two new modernised, fit-for-purpose Command and Control Centres for the ISF, at HQ and North Lebanon, which act as data-driven decision-making hubs for the ISF;
- Cooperation between LAF and ISF improved, including successful joint operations during Lebanese elections
- Across the three-year programme, 406 beneficiaries were engaged in rehabilitation/reintegration projects in Beirut and Tripoli. A total of 764 acquired vocational and employability skills (327 women and 437 men). Of those beneficiaries, 100% of male beneficiaries testified they would not engage in violent clashes for ideological/ sectarian reasons.

Key Lessons

- The ability of the programme to quickly adapt activities has been hugely important in keeping the programme relevant to the shifting and deteriorating context, including increased work on public order management to reflect growing need for ISF/ LAF engagement on protest management;
- CSSF Lebanon’s long-standing relationships with actors within security sector institutions and implementing partners means key stakeholders have a solid understanding of HMG’s objectives in Lebanon and Lebanon’s needs. Having secure funding enables them to a) build relationships they need to influence, b) deepen their/our expertise (e.g. knowledge of context, knowledge of needs, knowledge of ‘what works’), and c) test, learn, adapt, and deliver at scale;

Key Recommendations for FY 21/22

- Develop clear Key Performance Indicators (KPIs) or other indicators for the programme to indicate when it is time to transition from LAF support (e.g. establishment of 100% Lebanese run training wing for mentors);
- Given the UK’s leading role on internal security reform work in Lebanon, use influence to reinvigorate support for the donor coordination unit or other relevant coordination mechanisms;
- The Embassy has taken the strategic decision to use CSSF funding to focus on containing the current crisis in Lebanon and preventing state collapse through support to the security sector. Although challenging, where there are opportunities to build on the successes of other programmes and complement security sector reform, for example through political reform, economic reform, political participation, these should be considered.