Annual Review (21/22)
A. Summary Sheet

Programme Title	Libya Programme
Programme ID	C-MNA-0022
Country and Region	Libya, Middle East and North Africa
IATI Unique ID	CSSF-06-000006
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO)
Total Budget	ODA: £56.7m	Non-ODA: £0.22m
Budget this FY	ODA: £6m	Non-ODA: £0.1m
Spend this FY	ODA: £5.78m	Non-ODA: £0
Time Frame	Start Date: April 2018	End Date: March 2022

Outputs	Individual Output Rating
1. The threat of explosive remnants of war in target conflict-affected municipalities is decreased through mine clearance and increased awareness.	4
2. Decentralisation and more effective, inclusive local government leads to improved basic services in target areas, in increasingly more inclusive, participatory, and transparent ways	2
3. Target communities, more actively and effectively engage in civic life, shaping policies, service delivery and development planning at local and national level.	4
4. The UN peace process effectively drives progress towards peace at the national level and there is less violence and greater social cohesion at the local level.	2
5. Local mediation and peacebuilding supporting communities to reach peaceful resolutions to local challenges, creating community resilience to conflict and developing social change projects.	4
Overall Rating of Output Delivery	3

Outcome Assessment	This Programme is a key tool for tackling the drivers of conflict and instability that preserve the space needed to progress a viable and sustainable political settlement. Despite the challenges of delivering in a volatile environment, the Programme for FY 21/22 has demonstrated clear progress towards many of the stated outcomes - recovery, supporting inclusive change and social cohesion. However, increased attention must be placed on supporting a future peace process, which is key to Libya’s long-term stability.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		Medium

Summary of Programme Performance
Year	2019/20		2020/21		2021/22
Programme Rating	A	A	3	Green	3	Amber
Risk Rating	Medium		Medium-High		Medium

Note: Output / Outcome score

What Support Did the UK Provide in FY 21/22?
- With an interim unified Libyan government, and a roadmap toward elections at the end of 2021, the Libya CSSF Programme supported the UN-led peace process. This included support to the UN Support Mission in Libya (UNSMIL); helping to strengthen governance and service delivery (nationally & locally); and working to prevent local conflict from undermining peace efforts.
- The programme also continued UK support for local mediation and peacebuilding; more effective and inclusive local governance; and mine deactivation work, in support of an early recovery.
- The programme maintained flexible funds to deploy technical assistance to the political process; to provide additional support to elections; or contribute to ceasefire monitoring.
- The UK drew on the regional North African Technical Assistance Fund (NATAF) to provide technical assistance, supporting the economic track of the political process and providing improved economic analysis.
- This programme introduced new support to stabilise Libya’s electrical grid and lay the groundwork for a clean energy transition as part of a larger technical assistance programme to the Libyan power sector. This included: supporting Libya to maintain electricity supply and essential water services and advancing longer term structural reforms for the sector.

Key Results for FY 21/22
- Mine action in support of early recovery, allowing circa 257,000 people to return home.
- More effective and inclusive local government has provided responsive basic services, including sustainable and resilient water and electricity services.
- Advisor deployed in support the United Nations mission in Libya (UNSMIL).
- Supported communities to reach peaceful resolutions to local challenges, creating community resilience to conflict. Implementation of65 intra-community social cohesion initiatives across Libya.
Key Lessons
- Short-term (6 month) projects can be counterproductive. Tight timelines force implementing partners to focus on speed, rather than strategic and sustainable implementation. Long-term investment is key to affect long-term peace.
- Using a range of delivery partners and growing local ownership of the solution is more fruitful.
- Bringing in other donors to co-fund projects supports sustainable exit-plans.
- Adequate advisory support is key when designing and implementing programmes.

Key Recommendations for FY 21/22
- Continue to develop integrated working.
- Mine action work is seen positively by both political groups. A lever that could be used to support the national peace process.
- Truly flexible and adaptable programming is key in an ever-changing conflict context like Libya.
- Continue to build on long-term relationships and investments.
- Ensure programmes adopt a twin-track approach focussed on WPS objectives.
- Adequate technical advisory support to support effective programme delivery.