Annual Review (21/22)
A. Summary Sheet
Programme Title	Middle East Peace Process (MEPP) Programme
Programme ID	C-MNA-0023
Country and Region	Occupied Palestinian Territories (OPTs) and Israel, Middle East and North Africa (MENA)
IATI Unique ID	CSSF-06-000023
HMG Partners / (Lead in bold)	Foreign, Commonwealth & Development Office (FCDO)
Total Budget	ODA: £56.8m	Non-ODA: £3.5m
Budget this FY	ODA: £6m	Non-ODA: £0.5m
Spend this FY	ODA: £8.93m	Non-ODA: £0.85m
Time Frame	Start Date: April 2019	End Date: March 2022

Outputs	Individual Output Rating
Positive perceptions of, and strengthened support for, the Two State Solution (2SS) and/or a mutually agreed peaceful solution to conflict amongst key religious and other relevant constituencies.	3
Increased participation of key constituencies (including project participants) in positive discourse on peacebuilding and 2SS.	3
Effective legal assistance provided to Palestinians at risk of displacement in the West Bank and East Jerusalem.	4
Key infrastructure, particularly electricity provision, constructed in isolated parts of Area C, to facilitate continued Palestinian presence on their land.	4
Palestinian women’s and people with disabilities’ ability to achieve leadership positions in Palestinian society enhanced.	3
Provision of emergency multi-purpose cash and protection services to persons at risk and targeted, shock affected households.	4
Overall Rating of Output Delivery	4

Outcome Assessment	The programme contributed in a variety of ways to retaining the viability of a two state solution including the work in Area C and East Jerusalem. However, due to the current context and given there is a lack of a political peace process, the ambition was reduced towards ‘try to prevent further degradation of rights’, rather than actual policy change. The programme was successful in increasing the resilience and protection of the most vulnerable, although the longer-term sustainability of some of the impacts is questionable if the current context continues or worsens. Some tangible progress was made towards equality on gender and disability, with the Palestinian Council of Ministries officially considering a number of recommendations made, and progress was also made on building consensus on peace between Israelis and Palestinians, although the focus in the immediate time was towards increasing Israeli understanding of the situation. No progress was made on supporting political processes in the West Bank as the elections were cancelled, and as a result so was the proposed elections project. The programme also didn’t provide support towards making the Palestinian Authority Security Forces (PASF) more capable, accountable, sustainable and inclusive as this outcome was funded by core FCDO funds in FY21-22 rather than by CSSF.

Overall Outcome Progress Rating:					Amber
Overall Risk Rating:					Medium-High

Summary of Programme Performance
Year	2019/20		2020/21		2021/22
Programme Rating	B	B	4	Amber	4	Amber
Risk Rating	Medium		Medium-High		Medium-High
Note: Output / Outcome score

What Support Did the UK Provide in FY 21/22?

Continued to provide 1.) legal aid on evictions, demolitions and settler violence to vulnerable Palestinians in both East Jerusalem and Area C of the West Bank, 2.) electrical infrastructure to Palestinians living in Area C of the West Bank and also started to provide internet connectivity and 3.) humanitarian protection, relief, infrastructure and advocacy work for Palestinians in the West Bank.

Provided 1.) multi-purpose Cash Assistance to the most vulnerable households who were impacted by the hostilities in Gaza in May 2021, 2.) legal aid, counselling, trainings and referrals support to front-line service providers and survivors of Gender Based Violence (GBV) in the West Bank & Gaza and supported legal and policy measures related to inclusiveness in public institutions.

The non-ODA programming continued to contribute to building consensus on peace between Israelis and Palestinians to influence societal discourses regarding the conflict and improve Israeli access to important historical and contemporary information and alternative narratives.

Key Results for FY 21/22

The legal aid project prevented the displacement of 16,674 beneficiaries (8,565 Male/ 8,109 Female) in FY21-22. 77% of 2,324 Palestinians affected by settler violence and demolitions were also provided with Mental Health and Psychosocial Support services and 7 new communities in Area C of the west Bank now have access to off-grid energy (total 97).

More than 9673 direct beneficiaries (6237 females, 3436 males) received GBV support. The Palestinian Council of Ministries also officially considered a number of actionable recommendations for steps towards gender equality and for persons with disabilities.

2,190 vulnerable households impacted by the hostilities in Gaza in May 2021 were provided with Multi-purpose Cash Assistance between Oct 21 - March 22.

Key Lessons
Due to the current context given there is a lack of a peace process, many of the interventions in FY21-22 had a large focus on keeping Palestinians in situ and providing humanitarian relief in Gaza and the West Bank. Whilst the short-term results are encouraging, sustainability and longer-term value for money (VFM) is questionable is the current context doesn’t change / worsens.

As referenced in last year’s AR, a lack of understanding of, and interest in the Middle East Peace Process in Israeli society remained a key obstacle.

The team had responded to last year’s recommendation re the importance of having local partner presence on the ground; for the FY22-23 programme they will contract directly with the local partners.

Key Recommendations for FY 21/22
Regular assessment of the sustainability and VfM of interventions (in particular legal aid, infrastructure and cash payments) to review whether how/where funds are targeted and/or whether approach being taken needs to be adjusted. To note, activity should continue, recommendation is purely to periodically review how/where delivered.

Linked to the above, continue to consider whether more could be done on the advocacy front (noting the sensitivity around comms and protection of partners) and whether there is scope for acting on some of the proactive recommendations made by local partners supporting the legal aid programming (i.e. advocating on changes to laws). To note, this recommendation is purely on continue to consider whether there is scope, accepting this isn’t something the programme can do currently given the current context.

Periodically review whether there might be a possibility/appetite for the programme to support change at the institutional level (inc on peace building) in the future.

Consider opportunities for increasing gender equality in programming, including how the programme might work on pushing forward the recommended steps presented to the national drafting committee on gender equality and for persons with disabilities.

Consider how activity on gender equality in other projects is captured/reported; it was also good to see how women were part of the consultation process for the infrastructure projects. This didn’t come out as clearly in the reporting, but noted that the team are working to support the implementer to better capture this.