Programme Completion Review (21/22)

A. Summary Sheet

Programme Title	Morocco Programme
Programme ID	C-MNA-0003
Country and Region	Morocco, Middle East and North Africa
IATI Unique ID	CSSF-06-000007
HMG Partners / (Lead in bold)	Foreign, Commonwealth & Development Office (FCDO)
Total Budget	ODA: £24.4m	Non-ODA: £0
Budget this FY	ODA: £2.5m	Non-ODA: £0
Spend this FY	ODA: £2.56m	Non-ODA: £0
Time Frame	Start Date: April 2018	End Date: March 2022

Outputs	Individual Output Rating
Selected Regional Institutions (Regional Council) are supported to increase their transparency and responsiveness to citizens	3
Citizens through their organisations, are supported to increase capability to engage constructively with the state through participatory change-oriented processes	3
Programme increases capacity to generate relevant research, analysis and political access and influence (PAI)	4
Overall Rating of Output Delivery	3

Outcome Assessment	FY21/22 has seen specific challenges with focus on drawing the programme to a close in June 2022. This involved implementing project exit strategies, ensuring delivery of activities in a timely manner, while also navigating continued COVID-19 delivery issues and continued restrictions. Over the life of the programme as well as FY21/22, there has been quantifiable movement towards citizen engagement with state and transparency and responsiveness to citizens at regional institutional level. Despite context challenges, including emergency COVID travel restrictions, both FY21/22 active projects, Asarco and DAAM were able to deliver activities and the Theory of change remains relevant.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Medium-Low

Summary of Programme Performance
Year	2019/20		2020/21		2021/22
Programme Rating	A	A	4	Amber	3	Green
Risk Rating	Medium		Medium-Low		Medium-Low

Note: Output / Outcome score

What Support Did the UK Provide in FY 21/22?

The CSSF programme supported Integrated Review priority of open societies and conflict resolution with the aim of tackling the risk of conflict and instability through governance focussed interventions that reflected citizens' needs and economic realities whilst retaining a focus on marginalised groups, including women and girls. The programme had three main outcomes to try and achieve this;

- Selected state institutions (Ministry of Interior (MOI), The General Directorate of Territorial Communities (DGCT) and Regional Councils) are more capable, transparent, accountable and responsive to citizens’ needs and priorities
- Citizens, through their organisations, are better able to engage constructively with the state and signs of a more participative culture are emerging
- The Programme contributes effectively and intentionally to wider HMG objectives

Key Results for FY 21/22

- TASHAROC - Securing sustainability of some of the legacy achievements of the TASHAROC project, is the toolkit for Participatory and Inclusive Regional Public Policies and the citizen participation toolbox. Both shared with partners and the citizen participation toolbox disseminated to the regions and citizens through the DGCT website.
- 11 innovative participation mechanisms inspired from international best practice (including that of the UK) and the consultation of 188 Civil Society Organisations, cooperative and business representatives and citizens through the citizens’ jury tool in the Draa-Tafilalet region
- DAAM - Strengthened evidence of effective collaborations between civil society and Moroccan state. Through the projects noted success, international donors have reached out to DAAM to have them share their experience and build on it. An embassy presentation to donors has provided the EU with key insights into a roadmap and planning of the new 21/22 EU civil society organisation (CSO) programme.
- Civil Society Development - A testament to the projects’ impact is that every DAAM partner has been appointed to their local government led consultative structures, recognising their sectoral technical expertise.
- The local level structured dialogues have been successful with one convention with the local authorities being signed. DAAM CSO’s are now in strategic positions with local authorities involving them in parallel developmental processes.

Key Lessons

Sustainable exit strategies, created at the start of a project, have eased the process over the year as the team works towards the closure of the programme.
In the absence of funding, it has been possible to successfully maintain UK visibility, through the closely developed relationship with the Moroccan government (developed through the Westminster Foundation for Democracy project), however it is not clear how long this can be maintained without further funding.
Working collaboratively with a range of partners and encouraging synergies has supported sustainability of results and impact of the programme/project, as seen through the work on TASHAROC with the Tangiers, Tetouan-Al Hoceima and the regional council and consultative bodies, to ensure that consultative mechanisms were understood, accepted and successfully rolled out by all relevant parties in line with legislation.
Highlighted through difficult partner relationships, it is paramount to gain partner trust, while having patience and flexibility, to support open communication and the ability to pursue and maintain a professional relationship with high quality standards.
Agile political thinking/working (both as donors and partners) is fundamental in navigating complex cooperating environments. This allows better response to challenges and identifying opportunities during political transitions at both the regional and national level and unexpected contextual events such a COVID-19. Due to strong partnerships and close monitoring of the operational context (Political Economic Analysis, expand below in outcome 3 and ad hoc situational analysis) TASHAROC was able to think creatively within the framework of its objectives.

Key Recommendations for FY 21/22

- Continue to seek additional programme funds from alternative funding streams, particularly in open society sectors.
- Continue relationships with former implementing partners. Consider creation of a partner alumni network and tracker.
- Digitally maintain and regularly disseminate legacy programme essential information, achievements, contacts for current and future wider embassy use,
- Maintain profile within donor community by attending donor meetings and looking at hosting round tables discussions.
- Create and promote an evidence pack with programme key achievements, case studies and learning that could be shared across FCDO MENA Posts.