CSSF Annual Review (21/22)
A. Summary Sheet
Programme Title	Migration: Eastern Route (Turkey) Programme
Programme ID	C-MIG-0005
Country and Region	Turkey
IATI Unique ID	CSSF-01-000006
HMG Partners / (Lead in bold)	Foreign, Commonwealth & Development Office Home Office
Total Budget	ODA: £15,029,449	Non-ODA: £132,937
Budget this FY	ODA: £2,551,638	Non-ODA: £0
Spend this FY	ODA: £2,362,160	Non-ODA: £0
Time Frame	Start Date: 1 April 2017	End Date: 31 March 2023

Outputs – Assessed	Individual Output Rating
Output 1.1 - DGMM (Directorate General for Migration Management – now Presidency PMM), MoH (Ministry of Health), Ankara Municipality staff acquire knowledge - and develop guidelines - on trafficking, reproductive health for refugee women and girls	3
Output 1.3 - Service providers (DGMM, MoH, Ankara Municipality) assess and assist refugee women, girls and young refugees in a human-rights, conflict sensitive and gender compliant manner	4
Output 2.1 - Syrian schoolgirls take part in pilot research programme on targeted interventions that will assess their school attendance and provide evidence-based policy tools to the Ministry of National Education in a gender and conflict sensitive way	3
Output 2.2 - Refugees are informed about civic life, roles and responsibilities of key government institutions, and accessing services provided by institutions in Turkey	3
Output 2.3 - The capacity of DGILF and Turkish labour representatives to enhance the rights and employment conditions of foreign workers and coordinate activities in accordance with the Strategy Document and the National Action Plan on Irregular Migration is strengthened	3
Output 3.2 - Turkish Coast Guard Command (TCG) gain knowledge on irregular migration, legal frameworks and migrants' rights issues including gender sensitivity	3
Overall Rating of Output Delivery	3

Outcome Assessment	The programme showed strong progress against the majority of outcome indicators despite another challenging year given Covid-19. This is testament to the agility of the programme, made possible by the close relationship the programme team maintains with implementers and beneficiaries.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Low/Medium

Summary of Programme Performance
Year	2019/20		2020/21		2021/22
Programme Rating	A	A	Green	3	Green	3
Risk Rating	Low/Medium		Low/Medium		Low/Medium

What Support Did the UK Provide in FY 21/22?
The programme supports HMG’s efforts to work with Turkey to manage the movement of people within Europe’s wider neighbourhood, including towards the UK, through building upstream capacity; and continuing to meet the legitimate needs of refugees and asylum seekers, in accordance with UK & Turkey’s international obligations.
Key Results
- Training developed for the Social Cohesion and Life Training Project has now been accepted as a “public training module” by the Government of Turkey. It has been adapted into the Ministry of National Education’s E-Yaygin Sistem which is ready for online use in all 81 provinces of Turkey. Furthermore, the programme has helped create a pool of 4,400 certified MoNE trainers to deliver the training countrywide.
- The first ever Migrant Communication Centre was established for Ministry of Labour and Social Security (MoLSS). The Centre aims to provide first hand counselling to migrants that would like to access the labour market in Turkey.
Key Lessons
- Implementers value the agility shown by the programme in responding to the continued challenges of the Covid-19 pandemic, and contrasted this approach with other funding partners who were far less open to changes within year.
- A focus on catalytic programme has yielded results, e.g. in the rollout of social integration training course developed as part of the ASAM project to all of Turkey’s 81 provinces.
Key Recommendations
1. RESULTS MANAGEMENT: Management of results in the programme is strong, but the results flow of the programme should be strengthened so that outcomes stated in the December 2021 Theory of Change are included (and measured) in the macro results framework for the programme.
2. RISK MANAGEMENT: Risk management needs keener focus. The team should plot programme risks on a matrix and review once a month clearly escalating risks.
3. MARKET SHAPING: The market for Implementing Partners in Turkey is small due to preferences of Turkish Government institutions and restrictions on Civil Society Actors. Interviews conducted in the scope of this review suggest that the market is growing with an expanded number of CSOs and businesses now able to operate in Turkey. The team should maintain a core focus on working with Turkish Institutions on their stated priorities, but also seek to grow the delivery market by issuing some call for proposals.