Annual Review (21/22)
A. Summary Sheet
Programme Title	Peacekeeping Programme
Programme ID	C-MLS-0007
Country and Region	Multilateral
IATI Unique ID	CSSF-01-000003
HMG Partners (Lead in bold)	FCDO, MoD & Metropolitan Police
Total Budget	ODA: £2.87m	Non-ODA: £1.35m
Budget this FY	ODA: £2.87m	Non-ODA: £1.35m
Spend this FY	ODA: £2.49m	Non-ODA: £1.56m
Time Frame	Start Date: April 2016	End Date: March 2022

Strategic alignment
The Peacekeeping (PK) programme aims to support more effective and efficient UN Peacekeeping, in support of the Integrated Review commitment to reduce frequency and intensity of conflict, alleviate suffering and minimise opportunities for state and non-state actors to undermine international security. The programme does so by building on close alignment between UK PK policy, and UN Action for Peacekeeping Priorities. A significant amount of allocation supports the UN in tackling sexual exploitation and abuse (SEA) in peacekeeping, including through increased vetting and accountability of peacekeepers; clear pathways for victims of SEA to come forward within the system; and system-wide implementation of the UN Secretary–General (UN SG) zero tolerance policy.

Outputs	Individual Output Rating
Deployments: identify and deploy Military Staff Officers (MSOs) in roles which use UK expertise effectively, and support delivery of UK National Security Objectives.	4
Clear indication that funding supports UN PK mission effectiveness, based on objective performance data and evidence of impact of spend on improving mission planning and decision-making (thereby also improving impact of UK assessed (mandatory) UN PK funding (approx. £300 M).	4
PK Operations better equipped to protect civilians, as well as the safety and security of personnel (including UK deployed staff).	4
Mechanisms for greater accountability of UN PK Personnel are actively used UN system-wide, including to prevent and address sexual exploitation and abuse.	4
Mechanisms to support effective integrated planning are in place and used across PK missions.	3
Gender is mainstreamed into project design and implementation.	3
Sustainable increase in recruitment of women into senior PK roles.	4
UK actively uses the influence and relationships resulting from its project specific, Extra Budgetary ISF funding to increase UK national security.	3
Overall Rating of Output Delivery	3/4

Outcome Assessment	Steady, adequate progress on all outcomes, despite growing political and security challenges. Some projects are progressing more quickly than others, with slower progress in some areas due to the nature of multilateral organisations, which take time to reform. The combination of a move to multi-year funding, and improvements to the programme review framework should support better strategic alignment and understanding of longer-term impact.
Overall Outcome Progress Rating:		GREEN/AMBER
Overall Risk Rating:		LOW

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19 b		2019/20 b		2020/21c		2021/22c
Programme Rating	B	A	B	A	A	B	B	3	Green/ Amber	3/4	Green/ Amber
Risk Rating	Low	Low		Low		Low		Low		Low
Programmes changes during this period	There were no changes in projects funded for the F/Y 21/22. COVID-19 continued to limit some activity.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating.

What Support Did the UK Provide in FY 21/22?
- Deployment of UK military and police officers to UN missions and headquarters;
- Training for future PK troops on child protection and on UN women, peace and security policy; UK seat on steering committee of Elsie Fund in support of Women in Peacekeeping;
- Projects to support more effective PK Operations, including through improved capabilities to protect civilians, and the safety and security of peacekeepers (including UK deployed personnel); and information sharing between field missions, host countries and UN HQ.
Key Results for FY 21/22:
- Increased standardisation of PK systems for better planning, performance and decisions;
- UK-funded Comprehensive Performance Assessment System (CPAS) rolled out to all PK operations, and now using 15,000+ data points, which other UK-funded projects (Data Analytics, Unite Aware, Peacekeeping Intelligence and Strategic Force Generation Cell) feed into. This has resulted in better reporting to inform decisions of the UN Security Council, UN Secretariat, and PK missions on challenging political, conflict or security situations;
- UK-deployed officers include 15 Military Staff Officers and one Police Officer over seven UN missions, providing senior advice on planning, intelligence, operations, women’s participation.
- The PK Intelligence programme Early Warning Signalling and Action Plan has improved the security of local populations and PK forces (including UK deployed officers) in missions such as MONUSCO (Democratic Republic of Congo);
- The UK Long-Range Reconnaissance Group (LRRG) deployment to MINUSMA (Mali) has demonstrated the value-add of high-end UK capabilities in using PK intelligence to protect civilians, and peacekeeper safety and security;
- The Sexual Exploitation and Abuse (SEA) e-learning course has been completed in English (five more languages in proof); risk management tool kits are being deployed and workshops held in MINUSCA (Central African Republic).
Key Lessons
- Increased interdependency between multiple UK-funded projects strengthens systemic change.
- Targeted funding (for example on areas which support UK values such as gender equality, women in peacekeeping and accountability) can have significant impact.
- Collaborative working across HMG and cohesion between policy objectives and programme delivery supports agility, adaptability, and value for money.
Key Recommendations for FY 22/23
- The programme team should improve the measurement of programme impact, and the assessment of which funding thresholds achieve best value for money. This will allow the team better to target limited resources.
- Review and update programme design to ensure best alignment with the Integrated Review and NSC Multilateral Strategy.
- Review how the programme has delivered secondary impacts including broader change within the UN system to provide additional evidence on impact and value for money.