Annual Review (21/22)
A. Summary Sheet
Programme Title	Security Capacity Building Programme
Programme ID	C-MLS-0008
Country and Region	Multilateral
IATI Unique ID	CSSF-01-000004
HMG Partners / (Lead in bold)	FCDO, MOD, Stabilisation Unit, now the Office for Conflict, Stabilisation and Mediation (OCSM)
Total Budget	ODA: £7.73m	Non-ODA: £8.63m
Budget this FY	ODA: £0.53m	Non-ODA: £1.43m
Spend this FY	ODA: £0.36m	Non-ODA: £1.19m
Time Frame	Start Date: April 2016	End Date: March 2022

Strategic alignment
The Security Capacity Building programme contributes to the delivery of a more effective and efficient multilateral system that better delivers our National Security objectives, including the Integrated Review objective of “strengthening security and defence at home and overseas, specifically the aim to “provide diplomatic and expert support to multilateral organisations that uphold international norms on security (including) NATO and the Organisation for Security and Co-operation in Europe (OSCE)”.

Outputs	Individual Output Rating
Voluntary National Contribution	4
Voluntary National Contribution	3
Voluntary National Contribution	4
Voluntary National Contribution	3
Voluntary National Contribution	3
Voluntary National Contribution	3
Resilience Manager, UK Delegation NATO	4
UK continues to demonstrate its ongoing political and financial commitment to the Joint Comprehensive Plan of Action (JCPoA) and support to International Atomic Energy Agency in carrying out inspections and monitoring activities	4
OSCE HQ becomes a more transparent and resilient actor working with allies and partners to tackle emerging security threats.	3
Organisation for the Prohibition of Chemical Weapons (OPCW) can more effectively implement Chemical Weapons Convention and State Parties can fulfil their obligations.	4
Overall Rating of Output Delivery	4

Outcome Assessment	Overall, the programme has demonstrated that small amounts of targeted funding to multilateral security organisations in areas where the UK can provide added value; and targeting secondees in key positions, can deliver sizeable impact on how these organisations effectively support UK security priorities. Going forward, the programme’s effectiveness could be enhanced by addressing challenges resulting from short term contracts, and inadequate terms and conditions, which have caused gaps in filling posts. It is also important to note that exogenous factors such as Russia’s invasion of Ukraine had significant disruptive impact on the regular programmes of organisations like OSCE and NATO.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		Low

Summary of Programme Performance
Year	2016/17 a	2017/18 b		2018/19 b		2019/20 b		2020/21 c		2021/22 c
Programme Rating	B	A	A	A	A	A	C	4	Amber	4	Amber
Risk Rating	Medium	Medium		Medium		Medium		Low		Low
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 21/22?

The Security Capacity Building (SCB) programme aims to develop the capacity and capability of priority multilateral security organisations to respond to and counter growing threats in National Security Secretariat / Strategic Defence and Security Review priority areas including climate change, hybrid threats, violent extremism and Chemical, Biological and Nuclear threats.

The programme attempts to achieve these objectives through a mixture of personnel secondments (known as voluntary national contributions or VNCs) to NATO and OSCE, and through funding which is leading to improved policy formation and delivery on the ground by the multilaterals. The UK supports multilaterals selected by their relevance to UK national security strategies with the aim that they will become better at responding to, and countering, growing threats in UK national security priority areas.

Key Results for FY 21/22:
- Training and workshops run by UK secondee in support of effective use by NATO of the OASIS Comms model. This builds understanding of citizens of member states in support of UK national security objectives.
- UK contributed to design of a new cyber platform which greatly enhanced NATO’s ability to respond to cyber threats, leveraging Artificial Intelligence (AI) capabilities to collect and analyse large quantities of data derived from events in cyberspace.
- The threats identified by the UK’s Integrated Review (including on UK resilience) have informed the programme’s approach and helped embed this understanding to shape and improve NATO communications and strategies.
- Implemented previous programme review recommendations to focus on a smaller number of priorities and strategic objectives (informed by the Integrated Review). This led the programme team to focus in on four multilateral organisations (from seven), with fewer outputs (13 to 10) and outcomes (five to three).

Key Lessons
- This programme is a demonstration of how a small amount of funding, deployed in the right areas can deliver significant practical effectiveness improvements in support of UK interests, even in large organisations such as NATO.
- However, the programme’s effectiveness could be improved by addressing challenges resulting from a diffuse line management for secondees (leading to uncertainties around responsibilities), as well as short term contracts, which is leading to gaps.

Key Recommendations for FY 21/22
- Terms and conditions, as well as length of contracts for secondees need to be urgently reviewed to ensure secondees are effectively onboarded.
- The programme should keep under review its approach to risk, including the impact of exogenous factors e.g. conflicts or crises
- Budget reporting should be improved, with a stronger link between policy teams and the programme team.
- The results framework needs further improvements, especially on evidencing the links between Output and Outcome-level indicators.
- The programme should take a fresh look at whether there is opportunity to deliver more against gender outcomes.