Programme Completion Review (21/22)
A. Summary Sheet
Programme Title	UN Reform
Programme ID	C-MLS-0009
Country and Region	Multilateral
IATI Unique ID	CSSF-01-000019
HMG Partners / (Lead in bold)	FCDO, MOD, previously Stabilisation Unit, now the Office for Conflict, Stabilisation and Mediation (OCSM)
Total Budget	ODA: £7.98m	Non-ODA: £1.67m
Budget this FY	ODA: £1.62m	Non-ODA: £0.54m
Spend this FY	ODA: £1.59m	Non-ODA: £0.54m
Time Frame	Start Date: April 19	End Date: March 22

Strategic alignment
The UN Reform Programme supports UK interest in strengthening and improving the effectiveness of the UN system, by accelerating the implementation of UN reform - such as better leadership, efficiency, accountability and performance, including on peacekeeping, development approach in fragile states and humanitarian challenges. The programme provides targeted funding for projects coming under the UN Secretary General (UN SG) three-pillar reform approach of January 2019 (Peace and Security, Management and Development) and his Sustaining Peace agenda.

Outputs	Individual Output Rating
Quantitative risk models include economic, social, political and security indicators and insight from COVID-19 response. Improved risk frameworks, models and predictive analytics inform decision-making.	4
Stronger UN mission and UN Country Team capacities to plan and manage peace transitions in pro-active, integrated manner. Non-UN stakeholders engage in pro-active, integrated transitions planning in priority countries.	4
Information sharing of conflict analysis guidance through training materials and established network for UN field staff.	4
Governance and resource stewardship training program for senior leaders builds longer-term capability within UN Secretariat.	4
UN Secretariat and Peacekeeping Operations have increased capacity to design and develop recruitment innovation tools, training and guidance.	4
Trainings and materials are produced which operationalise the use of behavioural insight in support of a more integrated UN.	4
Stronger sexual misconduct policies across the UN through outreach, communication, training and partnership efforts.	4
Established governing practices for effective and efficient use of data and information, including on quality, ethics, security, privacy	4
Overall Rating of Output Delivery	4

Outcome Assessment	Good value for money and long-term sustainability achieved from projects targeting areas of UK priority on which we have expertise (e.g. data literacy) which also align with UN senior priorities. Achieving this impact requires sustained effort and long-term commitment.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Medium - Low

Summary of Programme Performance
Year	2019/20 a		2020/21 b		2021/22 b
Programme Rating	A	C	4	Amber/ Green	4	Amber/ Green
Risk Rating	Low/Medium		Low/Medium		Low/Medium
Note: a output / outcome scores; b scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 21/22?
- Increased capability of UN Departments and staff to support UN transition, integration, and conflict prevention in fragile settings; and strengthened capability in the UN Executive Office of the Secretary General to deliver data-driven projects on policy and standards;
- Strengthened system-wide response and implementation of concerted action to combat sexual misconduct;
- Improved governance through senior leadership training.
Key Results for FY 21/22:

The UN Reform Programme delivered the following key results:
- Enhancements to recruitment processes;
- Professionalisation of Sexual Misconduct investigations in the UN;
- Introduction of Behavioural Insights to address key impediments to UN reform;
- Delivery of bespoke courses for staff in areas of organisational reform;
- Progress on the implementation of recommendations from the UN Policy and Operational Integration Review, including in field settings;
- Catalytic seed support for priority initiatives on data transparency and data literacy;
- Good prospects for sustainability of outcomes after funding ceases, based on continued alignment with UN SG’s approach to reform, and feedback from UN staff.
Key Lessons
- Interventions under UN Reform project provide good value for money in terms of modest outlays, progress made, and ‘seed funding’ other support;
- Building capability in UN HQ (through e.g. guidance, training, process improvements, pilots) supports positive outcomes across the system, including in field settings;
- UK contributions are valued by partners for flexibility, responsiveness, active participation and thought leadership;
- Project success is highly dependent on consistent, long-term support from senior UN leaders and Member States.
Key Recommendations for FY 21/22
The programme completion review demonstrates how vital UK funding has been in increasing capacity and coordination in the UN to tackle reform. As the programme closes, the UK maintains its commitment to long-term UN reform.