Annual Review/Programme Completion Review (21/22)

A. Summary Sheet
NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Anguilla Programme (AP)
Programme ID
Country and Region	Anguilla, Caribbean
IATI Unique ID	CSSF-07-00005
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO)
Total Budget	ODA:	Non-ODA: £83.00m
Budget this FY	ODA:	Non-ODA: £18.27m
Spend this FY	ODA:	Non-ODA: £18.66m
Time Frame	Start Date: April 2018	End Date: March 2023

Outputs	Individual Output Rating
Education infrastructure restored to pre-hurricane Irma levels and built back better.	3
Health facilities restored to pre-hurricane Irma levels of functionality but with greater hurricane resilience.	4
The majority of government officials are located in appropriate, safe and hurricane resilient accommodation realising financial savings by co-locating and reducing the amount of rented accommodation.	4
Prioritised elements of critical national infrastructure are returned to full functionality and built back stronger.	3
Revenue strengthening reforms required under the Medium Term Economic & Fiscal Plan (MTEFP) implemented.	4
Overall Rating of Output Delivery	4

Outcome Assessment	Significant progress made as three primary schools, health clinics/hospital, House of Assembly, Road Bay Jetty, airport resurfacing and revenue strengthening projects are all completed and operational. Construction of the final project, Blowing Point Ferry Terminal, started in August 2021 with completion in 2022. Although programme delivery has continued to be hampered by the impact of the global pandemic on material supply chains and international shipping, these have largely been mitigated programme management.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Low

Summary of Programme Performance
Year	2019/20		2020/21		2021/22
Programme Rating	B	B	B	B	B	B
Risk Rating	Medium		Medium-Low		Medium-Low

Note: Output / Outcome score

What Support Did the UK Provide in FY 21/22?

Funding for the completion of projects to help rebuild Anguilla’s critical national infrastructure with enhanced resilience, contributing towards sustainable economic development. These consist of the core projects within the AP, in addition to the Road Bay Jetty, revenue strengthening projects, COVID-19 testing facilities, re-surfacing of the airport runway and removal of aerodrome obstacles at Anguilla’s international airport. Dedicated programme staff and technical advice.

Key Results for FY 21/22:

Education: Adrian T Hazell, Valley and Morris Vanterpool Primary Schools completed, opened and operational for the start of the September 2021 term. On the secondary school, of the five contracted packages one and three were completed apart from a lightning protection system installation. The contract to link the new school compound to the main road system has been awarded and work has commenced.

Health: All health projects have been completed and new infrastructure is operational.

Infrastructure: The Road Bay Jetty was completed in November 2021, but is not fully operational. The House of Assembly was completed in June 2021 and is fully operational. Re-surfacing of the airport runway re-surfacing has finished. Other notable work at the airport included removing electricity pylons near the end of the runway and re-routing cables underground enabling increased passenger capacity and therefore tourist arrivals.

Revenue Strengthening: All projects have been completed with support from the CSSF funded goods and services tax adviser.

Key Lessons

Strong programme governance oversight by the Senior Responsible Officer and Programme Responsible Officer ensured accountability and detailed assessment on specifications, value for money, procurement, risk management and overall management of financial and operational liabilities.

Providing external engineering expertise has been beneficial not just for the AP but in building wider capability in the construction and project management sectors.

Key Recommendations for FY 22/23

There remains a role for a dedicated programme manager to continue to engage with the Government of Anguilla (GoA) beyond March 2023, when AP spending is scheduled to end, in order to protect the UK’s investments.

Consideration should be given to funding procurement and installation of solar panels on all new AP buildings.

Resolution of secondary school contractual dispute ensuring the contractor is held to its obligations and the school is open to pupils as soon as possible.