Programme Completion Review (21/22)

A. Summary Sheet
NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Ascension Island Programme
Programme ID	Ascension Island Programme
Country and Region	Ascension Island, South Atlantic, UK Overseas Territories
IATI Unique ID	CSSF-07-000006
HMG Partners / (Lead in bold)	N/A
Total Budget	ODA:	Non-ODA: £6.58m
Budget this FY	ODA:	Non-ODA: £0.80m
Spend this FY	ODA:	Non-ODA: £0.80m
Time Frame	Start Date: March 2018	End Date: April 2022

Outputs	Individual Output Rating
Addressed critical island infrastructure with risks to life and single points of failure to island operations reduced.	4
Increased capacity and operational resilience on island to deliver improvements.	4
Produced a long-term recovery and maintenance strategy.	4
Overall Rating of Output Delivery	4

Outcome Assessment	The programme has delivered several key infrastructure projects and increased the capacity of the Ascension Island Government (AIG) to manage, in the long-term, these assets so reducing the risk of single points of failure and risk to life.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Medium

	Summary of Programme Performance
Year		2016/17a	2017/18b		2018/19b		2019/20b		2020/21c		2021/22
Programme Rating		N/A	N/A		A	A	A	A	4	Green	4	Green
Risk Rating						Medium
Programme changes during this period
Note:

What Support Did the UK Provide in FY 21/22?

Based on recommendations made in a report commissioned in FY 20/21, the Programme supported the manufacture of two wastewater plants to be sited in the capital, Georgetown, and in Two Boats Village.

Key Results for FY 21/22

Following a procurement exercise, a supplier was chosen in quarter two of FY 21/22. Contracts were completed in quarter three and the two wastewater plants are currently being manufactured offsite with delivery expected in October 2022. AIG is carrying out the civil work to clear the sites for the two new wastewater plants.

Due to the initial delay in signing the contract, an upfront payment for the two plants was reduced leaving extra funding available. At the quarter three programme board, it was decided to reallocate £0.20m from the wastewater project to the electrical rewiring project. The supplier (Concept) was already on Ascension Island working for the Ministry of Defence (MOD) under a pre-existing framework contract. This was used to procure the extra work.

Key Lessons

Key lessons include the need to focus on specific project components (such as procurement of equipment) at early stages of the financial year. This will ensure complicated purchases can be completed in good time increasing programme resilience to unforeseen delays. Having a dedicated resource on island and involvement of all major stakeholders throughout the programme is also important, particularly when stakeholders have a shared interest or use that will be impacted by the project.

The need to prioritise critical projects and determine what can be achieved within the allocated timescale and within the limitations of the programme and its funding is another key lesson.  Logistics also remain a challenging consideration, whether for materials or personnel to reach the island. Early planning and ordering are essential to ensure timely completion of projects.

Covid-19 impacted the cost of delivery for some of the components as compulsory isolation time had to be factored in. Excellent creative use of resources was gained by contractors being housed during their arrival in properties they had to refurbish which meant they were able to work during quarantine. This reduced costs.

Key Recommendations for FY 22/23

Planning around and announcement of allocated budgets would be preferable at the earliest opportunity. This enables early planning for projects and ensures materials can be ordered in good time.

Securing continuous representation of all island stakeholders, and key project post holders, including communications on the progress of projects. These partnerships will be crucial for future management and getting the best use out of the assets. The project board meetings and associated calls have meant a steady flow of information to stakeholders involved and those affected by the work.

Ensuring systems are in place to capture impact, lessons learned and wider corporate memory as personnel change.

The need to understand how other related projects (such as the Future of Ascension Island Review) will affect prioritised projects.