Annual Review/Programme Completion Review (21/22)

A. Summary Sheet
NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Border Security in the UK’s Overseas Territories (OTs)
Programme ID	OTD Border Security Programme
Country and Region	Overseas Territories (OTs)
IATI Unique ID	CSSF-07-000013
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO) / Home Office (HO) / Ministry of Defence (MOD)
Total Budget	ODA: £0.45m	Non-ODA: £1.59m
Budget this FY	ODA: as above (one year SR)	Non-ODA: as above (one year SR)
Spend this FY	ODA: £0.86m	Non-ODA: £0.94m
Time Frame	Start Date: April 2021	End Date: March 2022

Outputs	Individual Output Rating
Identification of critical infrastructure, skills to identify gaps and vulnerabilities and risk mitigation in cyber security.	3
St Helena – establish policies and guidance to support border control and immigration, local staff trained and plan in place for sustainability of training.	3
Turks and Caicos Islands (TCI) – the holistic and sustainable strengthening of TCI’s approach to border security, specific focus on the key threat presented by irregular migration.	4
Build capability of marine units and customs and immigration towards internationally recognised standards of delivery.	3
Identification of current maritime capability and required development.	3
Progress towards standardisation of training, tactics and procedures in maritime domain across Caribbean region.	2
Overall Rating of Output Delivery	3

Outcome Assessment	Clear progress on outputs contributing to most outcomes. Concentration on single territories on the maritime element of the programme has led to lower ratings in the outcomes tied to those aspects. But overall, significant progress since last FY, but there is room for improvement around tracking progress.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		Medium-High

Summary of Programme Performance
Year	2019/20		2020/21		2021/22
Programme Rating	N/A	N/A	2	Red	3	Amber
Risk Rating	N/A		Medium-Low		Medium-High

Note: Output / Outcome score

What Support Did the UK Provide in FY 21/22?

A secondee from UK Border Force was provided to TCI and two Immigration Officers were seconded to St Helena.

Multiple training courses were delivered in TCI and Cayman Islands to enhance capability of customs and immigration personnel. Further Home Office support on cyber security with National Cyber Risk Assessments for Cayman Islands and follow-up in St Helena. First annual OTs cyber conference in Miami.

A study of BVI maritime unit capability for tailoring of future support by MOD. Deployment of Cayman Islands police helicopter to TCI for four weeks to counter irregular migration threat.

Key Results for FY 21/22

Delivery and agreement of border transformation plan for TCI.

Border Force International (now Home Office International Operations) conducted a secondee assessment of the OTs to identify areas requiring support.

Training of BVI marine police unit and relationships built with local training college to support identification of future training and secondment requirements.

Creation of a cross-OT cyber community to share knowledge and expertise.

Key Lessons

Delivery partner limitations and resourcing constraints impacts on planning and delivery.

Clear strategic vision for the OTs is lacking in areas of border security. This is a cross-HMG issue and needs to be addressed through consultation across UK Government Departments.

Key Recommendations for FY 22/23

Policy vision for the OTs on border management is needed to ensure the programme is driven strategically.

The programme has made progress despite significant resource constraints among delivery partners. This needs to be addressed for the future success of the programme.

The programme would benefit from having an alternative funding stream where providers can be sourced externally, alleviating resource pressures and constraints.

Review/refinement of the Theory of Change and Results Framework to ensure capture of impacts.