Programme Completion Review (21/22)

A. Summary Sheet
NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	British Virgin Islands Territory Programme (BVITP)
Programme ID	CSSF OTD BVI
Country and Region	British Virgin Islands, Caribbean Overseas Territory
IATI Unique ID
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office, Government of the Virgin Islands (GOVI), Virgin Islands Recovery and Development Agency (RDA), Ministry of Defence (MOD), Ministry of Justice (MOJ)
Total Budget	ODA: n/a	Non-ODA: £9.70m
Budget this FY	ODA: n/a	Non-ODA: £2.05m
Spend this FY	ODA: n/a	Non-ODA: £1.97m
Time Frame	Start Date: March 2018	End Date: March 2022

Outputs	Individual Output Rating
RDA have in place the right personnel, systems and tools to enable them to deliver the projects set out in the revised Recovery Development Plan effectively, to high quality, on time and within budget, while also demonstrating that they have obtained value for money.	4
Improvements to foundational justice and law enforcement through targeted infrastructure, equipment and technical assistance to operations.	4
Provision of equipment and training to support GOVI to address priority disaster preparedness and resilience gaps.	3
Enhanced capacity, training and technology to promote transparency and efficiency in targeted areas of the public service.	3
Marine police have the equipment required to improve surveillance on the water.	4
GOVI supported to protect coral reefs and initiate use of renewable energy.	4
Overall Rating of Output Delivery	3

Outcome Assessment	The increased number and scale of projects implemented by RDA in addition to the award of contracts through GOVI of US$33m and the Caribbean Development Bank Rehabilitation and Reconstruction loan of US$19m signals RDA’s success as a project lead in GOVI major projects. The programme has procured services and equipment which have had a positive impact on law enforcement capabilities and justice operations. The Marine Unit’s fleet has increased in size and is now run by officers with better equipment and having received better training. More hours on the water have resulted in a safer environment for BVI.
Overall Outcome Progress Rating:		Amber – some evidence limited
Overall Risk Rating:		Medium

	Summary of Programme Performance
Year	2018/19			2019/20		2020/21		2021/22
Programme Rating	B		B	B	B	3	3	3	Amber
Risk Rating						Amber		Medium

Note: n/a

What Support Did the UK Provide in FY 21/22?

Funding was provided towards five outcomes: Law Enforcement, Governance, Border Security, Disaster Mitigation and Environment. Projects provided targeted equipment, training, technical assistance and expertise and some major refurbishments to buildings. The programme also offered capacity building and support to GOVI which has resulted in an increase in efficiency and accountability.

Key Results for FY 21/22:

RDA have successfully delivered major projects such as the police station refurbishments, Elmore Stoutt High School and road works recovery.

An increase in the rate and quality of intelligence gathering and investigations. The repairs to the Road Town Police Station, Financial Crimes Unit and Virgin Gorda Police Station have had a positive impact on law enforcement capabilities and justice operations by
improving working conditions significantly, including the increased safety of officers, and a positive impact on the human rights of detainees.

Increased capacity of the Marine Police to three working vessels. Four additional new maritime vessels will be delivered in November 2022.  The Marine Unit seized a large quantity of drugs through a routine search which they have reported would have been impossible without the equipment and capability funded by the programme.

The Coral Tissue Loss Disease project has received continued support through funding from the National Parks’ Trust. This important work for the protection of coral reefs will improve disaster resilience and economic value to BVI.

Key Lessons:

A more programmatic approach would facilitate planning resource, timelines, implementer engagement and ensuring value for money.

Increased use of the commercial tender process could have led to better value for money, more competitive rates, increased technical proposals and more robust monitoring and measurement processes.

Key Recommendations for FY 22/23

Increased involvement of policy/project officers for enhanced monitoring and evaluation of results and assessment of value for money.

Engage with CSSF advisers (gender, conflict sensitivity etc.) to ensure that projects are aligned with CSSF principles.