Annual Review/Programme Completion Review (21/22)

A. Summary Sheet
NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Environmental Sustainability and Climate Change (ESCC)
Programme ID	CSSF-07-000011
Country and Region	Overseas Territories (OTs)
IATI Unique ID	41010
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO) / Department for the Environment, Food and Rural Affairs (DEFRA), Maritime and Coastguard Agency (MCA), UK Hydrographic Office (UKHO), Marine Management Organisation (MMO), The Centre for Environment, Fisheries and Aquaculture Science (CEFAS), Animal and Plant Health Agency (APHA), Department for Transport (DfT), Ministry of Defence (MOD), Joint Nature Conservation Committee (JNCC)
Total Budget	ODA £1.90m	Non-ODA: £3.00m
Budget this FY	Same as above (one year SR)	Same as above (one year SR)
Spend this FY	ODA: £1.56m	Non-ODA: £3.87m
Time Frame	Start Date: April 2021	End Date: March 2022

Outputs	Individual Output Rating
For Montserrat and St. Helena - assessment of oil spill response capability through reviews, priority needs identified, and procurement of assets and training made available to address recommendations ahead of International Maritime Organisation III Code audit. Review OT legislation and assistance with implementation of marine pollution and liabilities conventions not in place.	3
Seabed mapping data collected to support Safety of Navigation (SoN) and increase in the capacity of OTs to provide Maritime Safety Information (MSI). Increase in access to seabed mapping data by OT governments to support other activities that focus on climate change resilience, sustainable environmental management and economic diversification.	4
To improve the biosecurity capacity of the UKOTs in order to reduce the threats to the environment, food security and sustainable development posed by non-native species.	4
Building a collaborative response for UK OTs to protect and conserve corals for the future.	4
Provision of tools and skills for OTs to embed the value of the natural environment into policy making.	3
A step-change initiated in native species production of St Helena Cloud Forest, planting and invasive species management in the Peaks National Park to secure remaining cloud forest and to increase area and quality of cloud forest habitat.	4
Water resources more clearly understood with priority areas for forest restoration identified to benefit water security and effective monitoring in place to develop understanding of impacts of cloud forest restoration on improvements in water capture.	3
Improved community and visitor engagement with the Peaks National Park.	4
The implementation of the Peaks Management Plan is effectively managed	4
Increased engagement of OTs ahead of COP26 on the five key COP themes	4
Overall Rating of Output Delivery	4

Outcome Assessment	This programme rating is green (two-thirds green ratings for all outcomes, one-third amber ratings) indicating that the programme is on track to meet or exceed outcome targets.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Medium-High

Summary of Programme Performance
Year	2019/20		2020/21		2021/22
Programme Rating	n/a	n/a	3	3	4	Green
Risk Rating	n/a		Medium-High		Medium-High
Note: Output / Outcome score

What Support Did the UK Provide in FY 21/22?

Support to help OTs comply with international maritime obligations through better hydrographic governance and the ability to deal with maritime pollution incidents. Improved understanding of environmental protection including biosecurity for invasive species and coral monitoring. Priority climate change projects across twelve OTs, in line with COP26.

Key Results for FY 21/22:

Implementation of the first year of the Cloud Forest project in St Helena, including activities around micro-propagation laboratory set-up and establishment of water and environmental baseline monitoring.

Increased engagement on coral conservation across the Caribbean OTs.

Development of contingency plans, crucial policies and legislation to support biosecurity activities.

Provision of tools for policymaking on disaster resilience including nature-based mapping in decision making.

Key Lessons

The need to be aware of partner and Governors Offices’ limitations in terms of resourcing and the need to plan to CSSF financial year start. The correct use of end of year reporting to capture impacts and value for money. The importance of using communication opportunities, including through Governors’ Offices, to promote CSSF programme activities.

Key Recommendations for FY 22/23

Improving end of year reporting from Posts and beneficiaries to help recognise programme impact.

Prioritisation of future CSSF funding in line with policy needs, and clear boundaries with other environmental funding sources.