Annual Review (21/22 Ver.) - Summary Sheet

Programme Title	CSSF Philippines
Programme ID	CSSF-09-000007
Country and Region	Philippines, South East Asia
IATI Unique ID	CSSF-09-000007
HMG Partners / (Lead in bold)	Foreign Commonwealth and Development Office
Total Budget	ODA: £12.5m	Non-ODA: £0
Budget this FY	ODA: £2.5m	Non-ODA: £0
Spend this FY	ODA: £2,502,371	Non-ODA: £0
Time Frame	Start Date: April 2020	End Date: March 2025

Outputs	Scale of Delivery
1. Bangsamoro Parliament acquire skills and knowledge to enact quality and inclusive legislation and perform effective oversight.	4
2. Bangsamoro women acquire skills and opportunities to politically engage at all levels across the region. There are policies that address women's issues in the region	4
3. Bangsamoro citizens understand the new parliamentary system, and their democratic functions and rights.	4
4. Bangsamoro citizens, especially in the island provinces, are fully aware of the BTA’s COVID-19 vaccination programme and vaccine confidence increases.	4
Overall Scale of Output Delivery	4

Outcome Assessment	The programme is likely to achieve sufficient progress against the desired outcome by the end of the current programme period (2025). In FY21/22, solid progress was made against all four intermediate outcomes. After two years of supporting Covid-19 response, a decision was taken to cease funding further activity on this strand in FY22/23 and focus on the core programme objective of supporting the ‘governance track’ of the Bangsamoro Autonomous Region of Muslim Mindanao (BARMM) peace process. This strategic clarity will allow the programme to continue building on progress already made in a complex operating environment.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Medium

Summary of Programme Performance
Year	2017/18b	2018/19b		2019/20b		2020/21c		2021/22c
Programme Rating	N/A	N/A		N/A		4	Green/Amber	4	Green/Amber
Risk Rating					Medium-high		Medium-high
Programme changes during this period		This FY, the programme remained adaptive in its programming by addressing the risks of the peace process by partially supporting its normalisation track and engaging with the International Contact Group.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?

FY21/22 was year two of this programme, which aims to address the key drivers of conflict and instability in the region. Interventions primarily focussed on four interconnected strands to support the ‘political/governance track’ of the Bangsamoro Peace Process, which established the Bangsamoro Autonomous Region of Muslim Mindanao (BARMM). These four strands were: capacity building for the new regional parliament; strengthening women’s political participation; increasing awareness among citizens in BARMM of the new parliamentary system; COVID-19 support to the new region. The programme also contributed to the ‘normalisation track’ through the Bangsamoro Normalisation Trust Fund (BNTF). Additional small-scale allocations were applied to conflict analysis, supporting the International Contact Group (ICG) for Mindanao, and platform/staff/MEL costs.

The CSSF Philippines programme funded seven projects in 21/22:

Project/Line Item	Implementing Partner	Allocation
Capacity building for Bangsamoro Transition Authority (BTA) Parliament	Westminster Foundation for Democracy (WFD)	£0.718m
Strengthening women’s participation in the Bangsamoro region.	UNDP / Catholic Relief Services (CRS)	£0.300m / £0.199m
Raising awareness about the new parliamentary system for citizens of the BARMM	The Asia Foundation (TAF)	£0.400m
COVID response	United Nation’s Children Fund (UNICEF)	£0.450m
Contribution to the Bangsamoro Normalisation Trust Fund (BNTF)^	World Bank	£0.275m
Conflict analysis	Conciliation Resources	£0.075m
Support to International Contact Group	Conciliation Resources	£0.017m
Plus Platform, Staff Costs & external MEL support	-	£0.066m
	Total Allocation	£2.5m

Key Results for FY 21/22:
- Further progress made in supporting the political/governance track of the BARMM peace process:
  - Bangsamoro Transition Authority (BTA) supported in refining its three remaining priority codes: the Electoral code, the Local Governance Code, and the Indigenous Peoples’ Code. Support was also provided in the development of an additional five bills: the Bangsamoro Veteran Mujahideen Bill; Bangsamoro Labor and Employment code; Rules of Procedure; Bangsamoro Gender and Development Code; and Freedom of Information Bill.
  - Bangsamoro Parliament supported in the development of a three-year communication and outreach strategy.
  - 12 Civil Society Organisations (CSOs) trained in parliament and governance, with priority policy issues identified for collaboration and advocacy.
  - 546 women supported in capacity building activities aimed at strengthening their participation in politics and peacebuilding.
  - 24 members of local media trained on reporting on the BTA to enhance contextualised reporting.
- Continued support/adaptation in response to urgent health needs:
  - Approximately 5m individuals reached with risk messaging on Covid-19 and the related vaccine rollout.
  - Covid-19 vaccine acceptance in targeted communities in the island provinces increased from 30% to 97%.

Key Lessons

The likelihood of programme success increases where programme strategy is clear and ambition is closely aligned with available resource and wider UK/local interests. Changes in context, delivery effectiveness and programme management all contribute to success, however strategic clarity is the key determinant. The Philippines CSSF programme is a positive example of setting a clear strategy playing to UK strengths and interests, buttressed by realistic, measurable and achievable targets, allowing a clear demonstration of progress against planned outcomes.

A narrow strategy does not preclude adaptation and responsiveness. The Philippines CSSF programme was able to build in a time-limited Covid-19 response element which, whilst not perfectly aligned with the Theory of Change, contributed to programme success and wider UK national interest without distracting from core business. This is a good example of adhering to CSSF fund level principles – responding with agility, being catalytic/short term rather than ‘developmental’/long-term in mindset, and integrating programme activity with wider UK interests/activity.

Key Recommendations for FY 22/23

Strategy: Maintain the existing strategic focus and avoid expanding into new strands of activity. Given the fluctuating context, a light refresh of programme strategy to test assumptions and ensure ongoing alignment, followed by an update of the Theory of Change and Results Framework, would be beneficial.

Donor coordination: Develop a stakeholder map capturing both active and planned programme activity in the BARMM. Utilise this to develop an options paper outlining potential donor-led coordination structures before determining next steps.

Sustainability: Prepare an internal (FCDO) roundtable to consider the question ‘what does successful programme exit look like?’. Use the output to then develop simple (one page) sustainability/exit plans for all ongoing projects, in consultation with implementing partners (IPs), which are aligned with the HMG vision

Monitoring, Evaluation and Learning (MEL): Re-engage external MEL support to assist with general strategy and MEL support, development and delivery of a MEL workplan including structured learning and targeted support to IPs, and ongoing MEL capacity building for both IPs and the programme team.

Conflict sensitivity: Undertake a JACS or ‘JACS-lite’ next FY in order to take stock of the changing context, feed recommendations into final year programme design and support longer-term thinking around potential UK support to the BARMM.