Annual Review (FY21/22)

A. Summary Sheet

Programme Title	Western Balkans Stability Programme
Programme ID	C-WBK-0005
Country and Region	Western Balkans: Albania, Bosnia & Herzegovina (BiH), Kosovo, Montenegro, North Macedonia and Serbia
IATI Unique ID	CSSF-10-000002
HMG Partners / (Lead in bold)	Foreign Commonwealth and Development Office (FCDO)
Total Budget	ODA: N/A	Non-ODA: N/A
Budget this FY	ODA: £14.60m	Non-ODA: N/A
Spend this FY	ODA: £14.63m	Non-ODA: N/A
Time Frame	Start Date: 1 April 2019	End Date: 31 March 2023

Outcomes[1]	Individual Outcome Rating
R1: The foundations of division – real or perceived – become less relevant to communities; who place greater emphasis on working across these divides on issues of importance	3
R2: Youth and communities vulnerable to violent extremism demonstrate increased resilience to violent extremism influences	3
R3: Those most affected by social trauma of conflict receive the necessary support to reintegrate into daily life	4
R4: Selected institutions are more effective in promoting reconciliation, building peace and addressing discrimination	4
DJ 2: Political parties that act in the interests of citizens and are responsive to their demands and election processes that make the government genuinely accountable to the electorate	3
DJ 4: Rule of Law institutions increasingly provide equitable justice to the standards demanded from citizens; with opportunities for corruption reduced	4
Overall Rating of Outcome Delivery	4
[1] For the purposes of this annual review (AR), the report template has been altered to match the Stability Programme’s results framework. AR ‘Outputs’ have become ‘Outcomes’ and AR ‘Outcomes’ have become ‘Higher Outcomes’. Only Higher Outcomes that had live projects in this financial year have been included.

Higher Outcome Assessment	With the change in CSSF focus, and significant portion of Stability projects moving over to the FCDO baseline in April 2022, it was agreed that the main review tool for 21/22 would be an Outcome Harvest looking at all years but of which 21/22 would be part. / The independent Outcome Harvest completed in May 2022 concluded that there was strong evidence of moderate to strong contribution towards achieving intermediary outcomes from which we also infer that some progress was made for the above higher outcomes in the sample projects selected.
Overall Higher Outcome Progress Rating:		Amber
Overall Risk Rating:		Medium-Low

Summary of Programme Performance
Year	2019/20		2020/21		2021/22
Programme Rating	A	B	4	Amber	4	Amber
Risk Rating	Medium		Medium-Low		Medium-Low
Note: Outcome / Higher Outcome score

What Support Did the UK Provide in FY 21/22?
The Stability Programme spent £14.6m in 2021/22 across 45 projects covering six countries in the Western Balkans in support of building citizens’ trust in the functioning of the state and judiciary, and increased community/societal resilience to divisive discourse.

Key Results for FY 21/22:
Positive feedback from Outcome Harvest Sample, with evidence of moderate to strong contribution towards achieving intermediary outcomes.

Key Lessons
- Projects are more likely to be successful where there is a strong partnership with beneficiaries and Embassies and alignment with UK priorities and interests.
- Administrative/management burden: The amount of administration required to oversee and manage a suite of implementing partners across multiple programming themes continued to be a challenge with ongoing Covid-19 (C-19) limiting activities and monitoring.
- These difficulties were compounded by gaps in institutional knowledge, combined with UK staff churn and absences resulting from C-19. This is an argument for fewer, larger projects. With many thematic issues to address and a growing number of smaller projects, staff resources were increasingly stretched.
- The thematic focus remains too broad. If Country Plans are not able to give focus and reduce thematic areas for programming, there is significant risk that financial resources are spread too thin and too many small interventions will not add up to the change we seek.
- Mitigations: Work with programme teams to ensure new initiatives are focused; Work with policy colleagues to define what objectives are 'must v want' to programme against; Work with the Western Balkans Monitoring, Evaluation and Learning (MEL) Provider to target monitoring approach to ensure projects are making the required change.

Key Recommendations for FY 22/23
- For projects moving to the new Freedom and Resilience Programme, to take forward lessons learnt into new Programme.
- Assimilate new team quickly and ensure regular engagement between central team and staff at Post to ensure project activities continue to fit under new Programme’s results framework
- Have a dedicated person for stability to monitor financial progress as a whole, whilst good financial monitoring at project level, programme level monitoring has room for improvement.

Outcome harvest recommendations include:
- Ensuring there are strong links between the project outcome and stability programme outcomes. Focusing on this ensures a stronger causal pathway from project activities to stability outcomes.
- Programme outcomes need to be realistic as there is often a gap in ambition between stability outcomes and project outcomes/activities. Lower levels of ambition may be appropriate when there are short timeframes, limited resources and challenging political economies.