## Sheet1
GMPP ID Number | Project Name | Department | Annual Report Category | Description / Aims | IPA Delivery Confidence Assessment (A Delivery Confidence Assessment of the project at a fixed point in time, using a three-point scale, Red – Amber – Green; definitions in the IPA Annual Report on Major Projects) | SRO Delivery Confidence Assessment (A Delivery Confidence Assessment of the project at a fixed point in time, using a three-point scale, Red – Amber – Green; definitions in the IPA Annual Report on Major Projects) | Departmental commentary on actions planned or taken on the IPA RAG rating. | Project - Start Date (Latest Approved Start Date) | Project - End Date (Latest Approved End Date) | Departmental narrative on schedule, including any deviation from planned schedule (if necessary) | Financial Year Baseline (£m) (including Non-Government Costs) | Financial Year Forecast (£m) (including Non-Government Costs) | Financial Year Variance (%) | Departmental narrative on budget/forecast variance for 2023/24 (if variance is more than 5%) | TOTAL Baseline Whole Life Costs (£m) (including Non-Government Costs) | Departmental Narrative on Budgeted Whole Life Costs | TOTAL Baseline Benefits (£m) | Departmental Narrative on Budgeted Benefits
HMRC_0291_2324-Q3 | VOA Business Systems Transformation | VOA | Government Transformation and Service Delivery | VOA Business Systems Transformation Programme is the VOA's pivotal digital transformation programme, which aims to re-design the VOA's core business processes and replace its outdated and end-of-life core valuation and data IT platforms. It will transform the VOA into a more flexible, efficient, and agile organisation able to respond to policy initiatives and deliver sustainable 3 yearly non-domestic rating revaluations. | Red |  | The Infrastructure Project Authority's Delivery Confidence Assessment rating at 23/24-Q4 is Red. This is primarily due to the following factors. The overall SRO Delivery Confidence Assessment for the BST Programme is Red. The IPA assessed the Programme as Red in the most recent IPA Gate Review. At the time of the IPA assessment, BST Council Tax delivery was deemed viable, but BST Non-Domestic Rating (NDR) was undergoing a substantial reset. Completion of NDR reset will provide greater confidence around longer term delivery. Significant progress has been made in addressing all of the findings identified. | 2019-11-11 | 2026-03-31 | The project's end-date at 23/24-Q4 is 2026-03-31. This is primarily due to the following factors. The Programme's release of the Geospatial platform in 2023 is due to be followed by the delivery of the Council Tax value stream in 2024, which remains on track. Council Tax covers a taxbase of 26.5 million properties equating to 95% of properties and data. Delivery of Council Tax into the business is Q3 FY24-25 including the migration of all relevant business data and integrated technology. The delivery of the Non-Domestic Rating value stream is currently expected to be delivered and rolled out by the end of FY25-26. The detailed delivery schedule will be confirmed in due course. | 41.56 | 41.56 | 0 | The budget variance is inferior or equal to 5%. | 236 | The project's departmental-agree Whole Life Cost at 23/24-Q4 is 236m. This is primarily due to the following factors. Whole life costs have been reviewed and revised at Full Business Case (FBC) stage. | 274 | The project's departmental-agree monetised benefits at 23/24-Q4 is 274m.
HMRC_0143_2223-Q2 | VOA Non - Domestic Rating Reforms Programme | VOA | Government Transformation and Service Delivery | The Non-Domestic Rating Reforms Programme (NDRR) continues to make good progress. It concluded its Alpha phase in April 2024 with a successful GDS assessment and has now moved into Beta. Improvement Relief, a headline measure from the Government's Business Rates Review and the Non-Domestic Rating Act (NDR) 2023, was delivered on 1 April 2024. The NDR Act has successfully completed its Parliamentary passage, gaining Royal Assent in autumn 2023. The Programme's Outline Business Case (OBC) has received internal approvals and is undergoing Treasury approval. An AO assessment has been completed, confirming that the programme meets the requirements of Managing Public Money. A summary will be published by the end of April. | Amber |  | The Infrastructure Project Authority's Delivery Confidence Assessment rating at 23/24-Q4 is Amber. This is primarily due to the following factors. The overall Delivery Confidence Assessment for the NDR Reforms Programme is Amber. Work is ongoing to address risks in relation to long-term funding certainty, programme capability and capacity, and dependence on technology change in other programmes. | 2022-04-01 | 2029-03-31 00:00:00 | The project's end-date at 23/24-Q4 is 2029-03-31. This is primarily due to the following factors. The Programme has developed its plan based on the preferred option in the business case. The schedule remains on track. Dates for the introduction of new customer requirements and the disclosure of additional information on valuations will be confirmed in due course. | - | - | - |  | 286 | Compared to financial year 22/23-Q4, the project's departmental-agree Whole Life Cost at 23/24-Q4 increased from 110m. to 286m. This is primarily due to the following factors. Whole life costs have been reviewed and revised at Outline Business Case (OBC) stage. | 333 | Compared to financial year 22/23-Q4, the project's departmental-agree monetised benefits at 2324-Q4 increased from 0m. to 333m.