## Cover
Building Safety Remediation Data Release, England: 31 December 2024
Back to Contents
Background
This publication provides data on 1) the remediation progress across MHCLG’s Building Safety Remediation portfolio, covering buildings in the ACM programme, Building Safety Fund, Cladding Safety Scheme, developer remediation contract and reported by registered providers of social housing, 2) Progress with remediation of high-rise (18 metres and over in height) residential buildings (including student accommodation and hotels) and publicly owned buildings with ACM cladding systems unlikely to meet Building Regulations in the ACM programme, 3) the progress of the Waking Watch Relief Fund and Waking Watch Replacement Fund, 4) progress with remediation of high-rise residential buildings with non-ACM cladding systems assessed as eligible for funding from the Building Safety Fund , 5) Progress with the applications for and remediation of medium-rise (11 – 18 metres in height) residential buildings in England and high-rise residential buildings outside of London with non-ACM cladding systems in the Cladding Safety Scheme, 6) progress of remediation of residential buildings 11 metres and over in height with life-safety defects under the developer remediation contract, 7) progress of remediation of residential buildings 11 metres and over in height with unsafe cladding reported by registered providers of social housing, 8) enforcement action taken by local authorities against 11m+ residential buildings with cladding defects under the Housing Act 2004.
Tables on the ACM programme, BSF, CSS, developer remediation contract and social housing surveys include buildings which can be in multiple schemes or data collections so counting across tables can result in double counting. Tab Combined_2 provides an overall summary of all remediation progress, without double counting.
Publication dates
The data tables in this spreadsheet were originally published on 23 January 2025.
The next publication is scheduled for 20 February 2025.
Useful Information
Further information on the data collection, data quality and definitions is available in the Technical Note published alongside these statistics.
Technical Note
Contact details
We are committed to improving and broadening this data release further in the months ahead and would welcome feedback both on the content of this data release and what could be further done in the future.
BuildingSafetyData2@communities.gov.uk
NewsDesk@communities.gov.uk
Date published: 23 January 2025

## Table_of_Contents
Building Safety Remediation Data Release Contents
Worksheet Name	Worksheet Title
Cover	Background information about the statistics.
Notes	Notes found in the tables.
ACM_1	Number of buildings identified with ACM cladding systems unlikely to meet Building Regulations, by tenure, 31 December 2024
ACM_2	Remediation status of buildings with ACM cladding systems unlikely to meet Building Regulations by tenure, England, 31 December 2024
ACM_3	Remediation status of buildings yet to complete ACM remediation by tenure, England, 31 December 2024
ACM_4	ACM remediation progress by local authority, England, 31 December 2024
ACM_5	ACM remediation progress by tenure for Greater Manchester, London and the Rest of England, 31 December 2024
ACM_6	ACM remediation progress by date identified with unsafe ACM cladding and by tenure, England, 31 December 2024
ACM_7	Number of dwellings in buildings identified with unsafe ACM cladding by remediation status, England, 31 December 2024
ACM_8	ACM remediation progress by sources of funding, England, 31 December 2024
ACM_9	Application progress of ACM buildings funded by the Private Sector Cladding Remediation Fund within and outside of London, England, 31 December 2024
ACM_10	Funding approved and expenditure by the Private Sector Cladding Remediation Fund and Social Sector Cladding Remediation Fund, England, 31 December 2024
ACM_11	Number of buildings identified with ACM cladding systems unlikely to meet Building Regulations, time series, 31 December 2024
WWRF_1	Waking Watch Relief and Replacement Fund applications, buildings and approved funding, 31 December 2024
WWRF_2	Waking Watch Relief Fund applications, buildings and approved funding by administering authority, 31 December 2024
WWRF_3	Waking Watch Replacement Fund applications, buildings and approved funding by administering authority, 31 December 2024
BSF_1	Remediation status of eligible buildings within BSF by tenure, England, 31 December 2024
BSF_2	BSF remediation progress of eligible buildings by region, England, 31 December 2024
BSF_3	BSF number of eligible buildings with funding approved and expenditure amounts by tenure, England, 31 December 2024
BSF_4	BSF remediation progress of eligible buildings by local authority, England, 31 December 2024
BSF_5	Remediation status of eligible buildings within BSF, time series, England, 31 December 2024
Combined_1	Remediation progress for buildings with unsafe ACM or being remediated in the Building Safety Fund, England, 31 December 2024
Combined_2	Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, 31 December 2024
Combined_3	Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, by local authority, England, 31 December 2024
Combined_4	Estimated number of dwellings in buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys by remediation status, England, 31 December 2024
Combined_5	Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, by tenure, 31 December 2024
Combined_6	Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, time series, 31 December 2024
Combined_7	Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, by region, 31 December 2024
CSS_1	Application status of buildings within the CSS, England, 31 December 2024
CSS_2	CSS remediation progress by region, England, 31 December 2024
CSS_3	CSS remediation progress by height, England, 31 December 2024
CSS_4	CSS remediation progress by tenure, England, 31 December 2024
CSS_5	CSS number of eligible buildings by funding allocations, expenditure and tenure, England, 31 December 2024
CSS_6	CSS remediation progress, time series, England, 31 December 2024
Social_1	Remediation status of buildings with cladding defects monitored under the social housing surveys, England, 31 December 2024
Social_2	Provider by provider breakdown of building stock and buildings requiring External Wall System (EWS) remediation, England, 30 September 2024
Social_3	Provider by provider breakdown of buildings, by assessment status, England, 30 September 2024
Social_4	Provider by provider breakdown of buildings, by remediation status, England, 30 September 2024
Social_5	Remediation status of buildings with cladding defects monitored under the social housing surveys, time series, England, 30 November 2024
Developer_1	Remediation status of buildings covered by the developer remediation contracts by height group, England, 31 December 2024
Developer_2	Estimated cost of buildings requiring works under the developer remediation contract by height, England, 31 December 2024
Developer_3	Developer by developer breakdown of buildings covered by the developer remediation contract, by number of buildings and remediation requirements, England, 31 October 2024
Developer_4	Developer by developer breakdown of buildings which are covered by the developer remediation contract requiring remediation, by remediation status, England, 31 October 2024
Developer_5	Developer by developer breakdown of buildings requiring remediation, which have not started works, with start dates England, 31 October 2024
Developer_6	Developer by developer breakdown of buildings requiring remediation, which have not started works, with start dates by Financial Year England, 31 October 2024
Developer_7	Developer by developer breakdown of buildings requiring remediation, which had not started works in the previous quarter England, 31 October 2024
Developer_8	Developer by developer breakdown of buildings requiring remediation, which have not completed works, with completion dates England, 31 October 2024
Developer_9	Developer by developer breakdown of buildings requiring remediation, which have not completed works, with completion dates by Financial Year England, 31 October 2024
Developer_10	Developer by developer breakdown of buildings requiring remediation, which had not completed works in the previous quarter England, 31 October 2024
Developer_11	Developer by developer breakdown of buildings, covered by the developer remediation contract and require remediation (excluding completed buildings), by engagement method, England, 31 October 2024
Developer_12	Remediation status of buildings requiring works under the developer remediation contract, time series, England, 30 November 2024
Enforcement_1	Enforcement action taken by local authorities against 11m+ buildings under the Housing Act (2004) by remediation programme status, England, 12 December 2024
Enforcement_2	Building inspections conducted by local authorities, England, 12 December 2024
Enforcement_3	Statutory notices served by local authorities under the Housing Act (2004), England, 12 December 2024
Enforcement_4	Number of building inspections by local authorities supported by the Joint Inspection Team, England, 12 December 2024
JIT_1	Number of Joint Inspection Team training sessions attended by local authorities, England, April 2021 - 31 December 2024

## Notes
Notes
Back to Contents
Note	Note Explanation	Note Location
[note 1]	Vacant buildings detailed in this table are included in table ACM_1 and ACM_2.	ACM_3
[note 2]	This table excludes local authorities with fewer than 10 high-rise residential buildings, regardless of whether they have unsafe cladding, and groups local authority figures into bands. These disclosure control measures are in place to prevent the identification of one or more buildings with cladding systems unlikely to meet Building Regulations in these areas.	ACM_4, Enforcement_1, Enforcement_2, Enforcement_3, Enforcement_4
[note 3]	Yet to complete remediation includes all dwellings in buildings that are yet to complete remediation works on-site	ACM_7
[note 4]	Social Sector Fund: Payments are made as cash grants, and will be payable in two tranches. The government will pay 80% of eligible costs at stage one. Once building owners confirm that they have tendered for the removal and replacement of cladding systems and work has started on site, we will make the first payment. Then we will pay the remaining 20% of eligible costs once building owners have submitted further evidence and confirmed final costs.	ACM_8
[note 5]	Private Sector Fund: The majority of private sector buildings receiving government funding for ACM remediation are funded through the Private Sector Cladding Remediation Fund. Payments from the Private Sector Cladding Remediation Fund will be made as cash grants and will be made on the basis of monthly valuations of work carried out on site, with an appropriate degree of due diligence, mirroring industry standard practice. Following Practical Completion the government will withhold a final payment which will be made on completion of the defects liability period. Eighteen private sector buildings are receving government funding from the Building Safety Fund, so do not appear in the totals in table ACM_9, but do in ACM_8.	ACM_8, ACM_9
[note 6]	The approved figure for the Private and Social Sector ACM Cladding Remediation Funds incorporates tendering support for applicants and approved project cost overrun. This figure reflects funding for the costs of remediation of unsafe ACM cladding only.	ACM_10
[note 7]	The Private Sector ACM Cladding Remediation Fund approved funding figure does not yet include any funds that will be reimbursed by developers who have signed the Pledge in relation to buildings they had a role in developing or refurbishing which have received government funding. All eligible applications to the Private Sector ACM Cladding Remediation Fund will be funded.	ACM_10
[note 8]	Expenditure for the Private and Social Sector ACM Cladding Remediation Funds is based on grant payments made by Delivery Partners to the applicant.	ACM_10
[note 9]	Private Sector ACM Cladding Remediation Fund (PSCRF) expenditure includes spend for non-ACM remediation works on buildings with unsafe ACM cladding funded through the PSCRF and therefore can exceed the amount approved which reflects unsafe ACM cladding remediation costs only.	ACM_10
[note 10]	Total figures may not sum due to rounding.	ACM_11, WWRF_1, WWRF_2, WWRF_3, BSF_1, BSF_2, BSF_3, BSF_5, Combined_4
[note 11]	The first tranche of the Waking Watch Relief Fund was administered by eight local/combined authorities alongside MHCLG. Further information on funding allocations by administering authority is available in the Waking Watch Relief Fund guidance at https://www.gov.uk/guidance/waking-watch-replacement-fund-2023	WWRF_2
[note 12]	The Waking Watch Replacement Fund was administered by five local/combined authorities alongside MHCLG. Further information on funding allocations by administering authority is available in the Waking Watch Replacement Fund guidance at https://www.gov.uk/guidance/waking-watch-replacement-fund-2023	WWRF_3
[note 13]	Remediation complete figures in this table include buildings that have completed remediation but are still awaiting building control sign off.	BSF_2, CSS_1, CSS_2, CSS_3, CSS_4, CSS_6, Combined_2, Combined_3, Combined_4, Combined_5, Combined_6, Combined_7
[note 14]	Private sector and social sector financial viability buildings can receive pre-tender support allocation in addition to their full applications funding, but not all buildings receive this therefore these numbers cannot be added together to directly give a total.	BSF_3
[note 15]	This table includes allocation figures for buildings which have only non-ACM cladding and buildings which have both non-ACM and ACM cladding.	BSF_3
[note 16]	For buildings with both ACM and non-ACM cladding in this table, 'Remediation not Started' is assigned for buildings that have not started works on either type of cladding. 'Remediation Started' is assigned for buildings where work has started on remediating at least one type of cladding. 'Remediation complete: awaiting building control sign off' is assigned for buildings that have completed remediation but sign off is required for work on remediating at least one type of cladding. 'Remediation complete' is assigned for buildings that have completed, and received sign off, on works for the remediation of both types of cladding.	Combined_1
[note 17]	Buildings can be in multiple schemes and data collections. These tables show the unique number of buildings across the schemes without double counting buildings where they are in multiple schemes. The total here will be lower than the summed total number of buildings reported in each scheme.	Combined_1, Combined_2, Combined_3, Combined_4, Combined_5, Combined_6, Combined_7
[note 18]	Where buildings are in multiple programmes, a combined remediation stage is first assigned for buildings in more than one of the ACM programme, BSF and CSS. 'In programme' is assigned for buildings that are eligible for but have not started works in any programme, or on one type of cladding (ACM or non-ACM). 'Remediation Underway' is assigned for buildings where work has started on remediation in at least one programme, or on one type of cladding. 'Remediation complete' is assigned for buildings that have completed remediation on site in all programmes or on all types of cladding. / For further overlaps, remediation stages are assigned from programmes in priority order: ACM, BSF, CSS (or a combined stage across these programmes), developer returns, social housing returns.	Combined_2, Combined_3, Combined_4, Combined_5, Combined_6, Combined_7
[note 19]	Enforcement action is where an inspection under the Housing Act 2004's Housing Health and Safety Rating System has been organised/undertaken, and includes where a statutory notice has also then been served.	Enforcement_1
[note 20]	The Housing Health and Safety Rating System (HHSRS) is a risk-based assessment evaluation tool to help local authorities identify and protect against potential risks and hazards to health and safety from any deficiencies identified in residential premises. Each hazard has a weighting which will help determine whether the building is rated as having risks which are either category 1 or category 2. Where a risk is deemed to be category 1, a local authority has a duty to take enforcement action; where a risk is deemed to be category 2, an authority has the power to take action.	Enforcement_2
[note 21]	The Government-funded Joint Inspection Team, hosted by the Local Government Association, carries out building inspections on behalf of local authorities and provides expert advice to local authorities on enforcement on buildings with unsafe cladding.	Enforcement_4
[note 22]	The number of training sessions for Wandsworth and Richmond are combined as Merton, Wandsworth and Richmond operate a joint service where Merton officers attend training on behalf of Richmond and Wandsworth.	JIT_1
[note 23]	Buildings confirmed by delivery partners to be transferred to developers or the Cladding Safety Scheme have been withdrawn from the Building Safety Fund, which has led to a decrease in the number of eligible buildings in the Fund. The number of eligible buildings may continue to decrease as more buildings are confirmed as developer or CSS transfers out of the fund.	BSF_1, BSF_2, BSF_4, BSF_5
[note 24]	The Building Safety Fund first opened to registrations from June to July 2020 receiving registrations from 3,488 buildings. In July 2022 the Building Safety Fund reopened to new applications; this remains open to new applications from buildings in London over 18 metres in height (high-rise buildings outside of London can apply for remediation via the Cladding Safety Scheme). Buildings from both application periods are now combined as one Building Safety Fund, so numbers include both application periods. It is possible for a building to submit a new application to the fund after having completed remediation if it originally applied in 2020, therefore buildings could be double counted. As of 30 November 2024 one building had undertaken remediation work from both application periods, so is double counted.	BSF_1, BSF_2, BSF_3, BSF_4, BSF_5
[note 25]	Some buildings have an unknown remediation status reported by the developer. These have been interpreted as ‘Remediation not started – no plans in place’.	Developer_1, Developer_4, Developer_12
[note 26]	The buildings reported in this table as requiring remediation are estimated by MHCLG using information provided by developers in their data return and other data available within the department. In this table, a building is defined as requiring works under the developer remediation contract if it is either self-reported by the developer as requiring works; is an eligible building in the BSF or ACM and the developer has agreed to re-imburse the funds; has had money paid out by the BSF or ACM; or has a self-reported work status of either: works completed, works started, or works not started but plans in place. / They therefore differ from other published tables which reference only to the number of 'self-reported' buildings requiring works.	Developer_1, Developer_12
[note 27]	The numbers reported in this table are a subset of the buildings which are self-reported by the developer as requiring remediation and which are not being completed through government funds, unless they have Other Non-External Wall systems defects which the developer is remediating directly. The tables shows the number of buildings which have not yet started works; this is a combination of buildings which are 'Remediation not started - Plans in Place' and 'Remediation not started - No Plans in Place', 'Plans under Development' or where no status was provided. The table shows the estimated or actual start date of works, where available. / This differs from the numbers provided in Developer_1 as it only looks at buildings which have not yet started remediation work, but have an estimated or actual start date included in the return and the buildings requiring works are calculated differently as per [note 26].	Developer_5, Developer_6
[note 28]	This column represents buildings requiring works which are being remediatd through government funds, for example the Building Safety Fund (BSF) or ACM Cladding Remedation Fund. The funds will reimbursed by the developer after completion. Buildings being completed through government funds but which have Other Non-External Wall systems defects are excluded as the developer is remediating these directly themselves.	Developer_3
[note 29]	The tables report data for 54 developers who have signed the Developer Remediation Contract. Data for one developer who has gone into administration is not included in this release. / The tables report on data submitted by developers to MHCLG and is correct as at 31 October 2024, except for one developer (Frasers Property) who did not submit data within the deadline. For this developer, the data reported in this release uses the data they submitted as at 31 July 2024. / Where tables show the breakdown of data for each developer, some information has been supressed, as seen in the row 'Other (combined total for all developers with five or fewer buildings each' summarises information of 12 developers with five or fewer buildings, this includes: Abbey Developments, Allison Homes, Bloor, CG Fry, Courdace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata and William Davis. This data has been supressed due to the number of buildings being fewer than six and is represented in the data with a dash (-) in the data.	Developer_1, / Developer_2, / Developer_3, Developer_4, Developer_5, Developer_6, Developer_7, Developer_8, Developer_9, Developer_10, Developer_11, / Developer_12
[note 31]	This column excludes buildings requiring works which are being completed through government funds and reimbursed by the developer (see Note 28), as the developer cannot influence the pace of remediation on these buildings. However, those buildings being completed through government funds but which have Other Non-Externall Wall systems defects are included as the developer is remediating these directly themselves.	Developer_3, Developer_4
[note 32]	The data here is comprised of 'Don't know', 'Don't know - no assessment made' and blanks in response to the field 'Does this building require works?' regardless of whether the building has had an assessment or not.	Developer_3
[note 33]	The total estimated cost of remediation is based on the actual or estimated cost of remediating EWS and non-EWS defects, as reported by developers, and an assumed average where a cost has not been reported (averages are based on the developer-reported costs, by height).	Developer_2
[Note 34]	Data is taken from a building level survey issued to Registered Providers of Social Housing on their 11 metre plus buildings and is correct as at 30 September 2024. / Landlords were asked to respond to the survey for buildings in which they are the responsible entity. A 'Responsible Entity' is the organisation that has the legal obligation or right to carry out the remediation works. The Responsible Entity may be the building’s freeholder or head leaseholder, registered provider of social housing or a management company or Right To Manage (RTM) company that has primary responsibility for the repair of the property. / As a result, buildings within the survey may comprise of mixed tenure dwellings e.g., private leasehold and social rented dwellings, however remedial works will fall under the responsibility of the responding landlord. / Furthermore, landlords were asked to provide information on any life critical fire safety (LCFS) defects, which the survey defined as defects, shrinkages, faults or other failings in a building that give rise to fire safety risks. These are identified by: / 1) a Fire Risk Appraisal of External Wall construction (FRAEW) undertaken in accordance with PAS 9980 that assesses the external wall construction or cladding as not “medium - tolerable” (or better); or / 2) a fire risk assessment (FRA) that assesses the relevant parts of the building as high risk or medium risk or equivalent according to industry standards.	Social_1; Social_5
[Note 35]	A building with EWS 'cladding defects' is defined as a building which has at least one Life-critical Fire-safety defect relating to an External Wall System (EWS) cladding defect. These buildings may also include non-cladding associated defects.	Social_1; Social_2; Social_3; Social_4; Social_5
[Note 36]	The number of buildings identified as 'Remediation complete' may not match the number of social buildings being reported and complete under the BSF, ACM, CSS or developer contract due to the following: / 1) Non-responses to building level survey issued to Registered Providers of Social Housing - a small number or landlords did not respond to the survey, which means some buildings remediated through other remediation schemes may not be captured. / 2) Differences in how buildings are reported in the building level survey issued to Registered Providers of Social Housing - some buildings which have already completed remediation via other schemes have been reported as having no Life-Critical Fire-Safety defects in the survey, as the latest fire safety assessment has concluded that the the building is safe. Subsequently, the landlord has reported that no defects are present in the survey and have left the remediation category blank.	Social_1
[Note 37]	The data here includes buildings in the building level survey issued to Registered Providers of Social Housing, which may have also applied and are eligible for other remediation schemes e.g., ACM, BSF, CSS and developer contract. These are not excluded from the Social Housing Sector Management Information tables (Social_1).	Social_1
[note 38]	The total number of social high-rise buildings receiving government funding for the remediation of ACM cladding currently includes 2 buildings that fall under the developer remediation contract. These buildings will either be transferred from government funds, or will remain in the funds with developers reimbursing the department for the remediation costs.	ACM_8
[note 39]	The total number of social high-rise buildings not receiving government funding for the remediation of ACM cladding currently includes 1 building that falls under the developer remediation contract.	ACM_8
[note 40]	The total number of private high-rise buildings receiving government funding for the remediation of ACM cladding currently includes 20 buildings that fall under the developer remediation contract. These buildings will either be transferred from government funds, or will remain in the funds with developers reimbursing the department for the remediation costs.	ACM_8
[note 41]	The total number of private high-rise buildings not receiving government funding for the remediation of ACM cladding currently includes 69 buildings that fall under the developer remediation contract.	ACM_8
[note 42]	Data for the ACM, BSF and CSS are updated monthly. Developer data and data reported by Registered Providers of social housing are updated quarterly.	Combined_2, Combined_3, Combined_4, Combined_5, Combined_6, Combined_7
[note 43]	The number of buildings associated with particular expenditures paid out may also include buildings where a full reimbursement of funding has taken place, including those where required under the developer contract.	BSF_3
[note 44]	Buildings receive expenditure funding in stages and therefore these figures should not be used to calculate the average expenditure paid out to each building.	BSF_3, CSS_5
[note 45]	In this table where a local authority has 5 or fewer eligible BSF buildings, the numbers provided are banded. In all other cases the numbers are provided. These disclosure control measures are in place to prevent the identification of one or more buildings with cladding systems unlikely to meet Building Regulations in these areas.	BSF_4
[note 47]	One building with a live application to the CSS are in Northern Ireland, the remainder are in England.	CSS_1
[note 48]	Four eligible buildings in the CSS are in Northern Ireland, the remainder are in England.	CSS_1, CSS_2, CSS_3, CSS_4
[Note 50]	The data in this table is derived from the building level survey which has been submitted by Registered Providers of Social Housing on their 11 metre plus buildings and is correct as at 30 September 2024. It covers buildings in England over 11m which contain at least 1 unit of social housing for which the social housing provider is the Responsible Entity. / Some buildings in this table may have applied and are eligible for other remediation schemes e.g., ACM, BSF, CSS and developer contract.	Social_2; Social_3; Social_4
[Note 51]	Registered social housing providers who have five or fewer 11m+ buildings (which may or may not require EWS life-critical fire-safety works) have been grouped together in the ‘Other RPs’ row in the data table, in order to avoid inadvertently identifying individual buildings with EWS life-critical fire-safety defects.	Social_2; Social_3; Social_4
[Note 52]	A building works assessments should comply with the requirements of the Fire Safety Order, for example a Fire Risk Assessment or Fire Risk Appraisal of External Walls assessment (FRAEW).	Social_2; Social_3
[Note 54]	Buildings reported as having completed remediation in the building level survey may require reassessment to confirm the building is now safe.	Social_1; Social_4
[note 55]	These buildings are the subset of buildings which in the last developer data return (as at 31 July 2024) required remediation works and had not started remediation, but had reported start date due between 1 August 2024 and 31 October 2024. This table displays their current remediation status based on the data as at 31 October 2024.	Developer_7
[note 56]	The numbers reported in this table are a subset of the buildings which are self-reported by the developer as requiring remediation and which are not being completed through government funds, unless they have Other Non-External Wall systems defects the developer is remediating directly. The tables shows the number of buildings which have not yet completed remediation; this is a combination of buildings which are 'Remediation not started - Plans in Place' and 'Remediation not started - No Plans in Place', 'Remediation Started'. The table shows the estimated or actual completion date of works, where available. / This differs from the numbers provided in Developer_1 as it only looks at buildings which have not yet completed remediation work, but have an estimated or actual completion date included in the return and the buildings requiring works are calculated differently as per [note 26].	Developer_8, Developer_9
[Note 57]	Funding allocations of Full Applications Approved has reduced from previously published figures. This is the result of a data reconciliation exercise, where buildings transferring from the BSF to the Responsible Actors Scheme and Cladding Safety Scheme have had their BSF funding allocation removed.	BSF_3
[Note 58]	The 'Other' tenure includes buildings that are recorded in the ACM programme as student, hotel or public buildings.	Combined_5
[Note 59]	The estimates in this table include buildings which are: / a) reported in the latest survey (as at 30 September 2024) as having unsafe cladding at the time of their most recent assessment; / b) reported in the latest survey (as at 30 September 2024) as having unsafe cladding found since June 2017 but prior to the most recent survey, which have since been remediated; / c) being monitored under another government programme (BSF, ACM, CSS or RAS) due to having unsafe cladding.	Social_1
[Note 60]	Until May 2024, private sector funding allocations and expenditures included buildings which have successful social sector financial viability claims. This is because both private sector and social sector financial viability buildings receive full government funding, whereas those in the social sector receive partial funding dependant on the number of eligible leaseholders who pay a service charge. For full details please refer to the accompanying technical note.	[BSF_3]
[Note 61]	Until the May 2024 data release, social sector buildings with a successful financial viability claim were included in the "Private" figures due to them receiving funding for all work, rather than a percentage based on the number of leaseholders that pay a service charge. These buildings are now split out into the "social sector financially viability" category. Further details on the difference between these can be found in the accompanying technical note.	[BSF_1]
[Note 62]	This table depicts the number of buildings that are estimated to require works which have transferred from the Building Safety Fund (BSF). This figure is based on the developer's dataset definition of a building and differs to the number reported by the BSF because of difference in building definitions.	Developer_1
[Note 63]	The estimates in this table include buildings which are reported in the latest survey (as at 30 September 2024) as having unsafe cladding at the time of their most recent works assessment. They do not include buildings which are reported in the latest survey (30 September 2024) as having unsafe cladding found since June 2017, which have since been remediated. / They also do not include buildings that were identified through other government programmes (BSF, ACM, CSS or RAS) which have not been reported by social housing providers as having unsafe cladding.	Social_1; Social 2; Social_3; Social 4
[Note 64]	The December 2018 and December 2019 ACM remediation progress figures did not include the breakdowns for 'remediation started - cladding removed' and 'works complete awaiting building control signoff'. Those buildings which had started remediation and removed unsafe cladding are included in the 'remediation started' category, and those that were awaiting building control sign off may have been included in the 'completed remediation' category	ACM_11
[Note 65]	Up to October 2023 combined remediation progress in the Building Safety Fund (BSF) and ACM programme is shown. Between June 2023 and September 2023 there was a decrease in the number of buildings due to buildings transferring from the BSF to being remediated by developers. From October 2023 onwards combined remediation progress is shown across the BSF, ACM programme, Cladding Safety Scheme, developer remediation contract and as reported by registered providers of social housing.	Combined_6
[Note 66]	Between June 2023 and July 2023 there was a decrease in the number of buildings due to buildings transferring from the BSF to being remediated by developers.	BSF_5
[Note 67]	This table is updated quarterly with the latest data and therefore may not align with monthly figures where the programme data is updated.	Developer_12
[Note 68]	The estimates in this table include buildings which are reported in the latest survey (as at 30 September 2024) as having unsafe cladding: / a) at the time of their most recent assessment. / b) found since June 2017 but prior to the most recent survey, which have since been remediated. / The estimates in this table do not include buildings that were identified through other government programmes (BSF, ACM, CSS or RAS) which have not been reported by social housing providers as having unsafe cladding.	Social_1; Social 2; Social 4
[Note 69]	In previous Building Safety Remediation releases, this table was known as 'Building inspections conducted by local authorities'. As of the August 2024 release, this table reports the category assigned from the most recent building inspection.	Enforcement_2
[Note 70]	The Mar-24 and Jun-24 estimates are not comparable to previous quarters due to a change in methodology in reporting social housing sector remediation. Since Mar-24, the estimates include buildings which have been reported by Registered Providers to have completed remediation since June 2017 but prior to the most recent assessment. They also include social buildings the department has identified in other remediation programmes as having unsafe cladding and are also being monitored in those programmes.	Social_5
[Note 71]	This table excludes local authorities with fewer than 10 11m+ buildings monitored with unsafe cladding. These disclosure control measures are in place to prevent the identification of one or more buildings with unsafe cladding in these areas.	Combined_3
[Note 73]	As of the November 2024 data release, there is only one column covering Level 2 training. This is a sum of the data from Level 2 Part 1 and Level 2 Part 2. To make comparisons with previous JIT training data, the values in columns C and D should be totalled.	JIT_1
[Note 74]	These buildings are the subset of buildings which in the last developer data return (as at 31 July 2024) required remediation works and had not completed remediation, but had reported completion date due between 1 August 2024 and 31 October 2024. This table displays their current remediation status based on the data as at 31 October 2024.	Developer_10
[Note 75]	The reported number of buildings to have started or completed remediation works has fallen between August 2024 data release and November 2024 data release mainly due to data revisions from some Registered Providers of social housing following the addition of more detailed questions on start and completion dates.	Social_5

## ACM_1
Number of buildings identified with ACM cladding systems unlikely to meet Building Regulations, by tenure, 31 December 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Tenure	Number of buildings this month	Number of buildings last month	Monthly change
Social sector residential	162	162	0
Private sector residential	252	252	0
Student accommodation	60	60	0
Hotels	32	32	0
Publicly-owned buildings	8	8	0
Total buildings	514	514	0

## ACM_2
Remediation status of buildings with ACM cladding systems unlikely to meet Building Regulations by tenure, England, 31 December 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each tenure.
Remediation Category	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: all tenures / Number	Total: all tenures / Percentage (%)
Completed Remediation	134	83%	197	78%	55	92%	27	84%	7	88%	420	82%
Works complete awaiting building control signoff	9	6%	12	5%	2	3%	2	6%	1	13%	26	5%
Remediation started - cladding removed	18	11%	10	4%	0	0%	1	3%	0	0%	29	6%
Remediation started	0	0%	14	6%	2	3%	1	3%	0	0%	17	3%
Remediation plans in place	1	1%	17	7%	1	2%	0	0%	0	0%	19	4%
Reported an intent to remediate	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Remediation plan unclear	0	0%	1	0%	0	0%	1	3%	0	0%	2	0%
Total buildings	162	100%	252	100%	60	100%	32	100%	8	100%	514	100%

## ACM_3
Remediation status of buildings yet to complete ACM remediation by tenure, England, 31 December 2024
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category for vacant buildings	Social sector residential	Private sector residential	Student accommodation	Hotels	Publicly-owned buildings
Works complete awaiting building control signoff - Vacant	0	1	0	0	0
Remediation started - cladding removed - Vacant	0	0	0	0	0
Remediation started - Vacant	0	0	0	0	0
Remediation plans in place - Vacant	0	0	0	0	0
Reported an intent to remediate - Vacant	0	1	0	0	0
Remediation plan unclear - Vacant	0	0	0	0	0
Total vacant buildings	0	2	0	0	0

Remediation Category for occupied buildings	Social sector residential	Private sector residential	Student accommodation	Hotels	Publicly-owned buildings
Works complete awaiting building control signoff	9	11	2	2	1
Remediation started - cladding removed	18	10	0	1	0
Remediation started	0	14	2	1	0
Remediation plans in place	1	17	1	0	0
Reported an intent to remediate	0	0	0	0	0
Remediation plan unclear	0	1	0	1	0
Total occupied buildings	28	53	5	5	1

## ACM_4
ACM remediation progress by local authority, England, 31 December 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Local Authority [note_2]	Number of buildings identified with ACM cladding systems (unlikely to meet Building Regulations)	Number of buildings with ACM cladding systems (unlikely to meet Building Regulations) yet to be remediated	Percentage of buildings with ACM cladding systems completed remediation	Percentage of buildings with ACM cladding systems started or completed remediation
Barking and Dagenham	1 to 5	None	100%	100%
Barnet	6 to 10	1 to 5	Between 50% and 99%	100%
Bedford	1 to 5	None	100%	100%
Birmingham	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Bournemouth, Christchurch and Poole	1 to 5	1 to 5	Less than 50%	100%
Bradford	1 to 5	None	100%	100%
Brent	11 to 20	11 to 20	Less than 50%	Between 50% and 99%
Brighton and Hove	1 to 5	None	100%	100%
Bristol, City of	6 to 10	None	100%	100%
Bromley	1 to 5	None	100%	100%
Calderdale	1 to 5	None	100%	100%
Camden	6 to 10	6 to 10	Less than 50%	Between 50% and 99%
City of London	1 to 5	None	100%	100%
Croydon	6 to 10	1 to 5	Between 50% and 99%	100%
Dacorum	1 to 5	None	100%	100%
Doncaster	1 to 5	None	100%	100%
Ealing	1 to 5	1 to 5	Between 50% and 99%	100%
Elmbridge	1 to 5	None	100%	100%
Gateshead	1 to 5	None	100%	100%
Greenwich	Over 20	1 to 5	Between 50% and 99%	100%
Hackney	11 to 20	1 to 5	Between 50% and 99%	100%
Hammersmith and Fulham	6 to 10	None	100%	100%
Haringey	6 to 10	1 to 5	Between 50% and 99%	100%
Harrow	1 to 5	None	100%	100%
Havering	1 to 5	None	100%	100%
Hillingdon	1 to 5	1 to 5	Between 50% and 99%	Between 50% and 99%
Hounslow	1 to 5	None	100%	100%
Islington	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Kensington and Chelsea	1 to 5	None	100%	100%
Kingston upon Thames	1 to 5	None	100%	100%
Kirklees	1 to 5	None	100%	100%
Lambeth	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Leeds	6 to 10	None	100%	100%
Leicester	1 to 5	None	100%	100%
Lewisham	1 to 5	1 to 5	Between 50% and 99%	100%
Lincoln	1 to 5	None	100%	100%
Liverpool	11 to 20	1 to 5	Between 50% and 99%	100%
Luton	1 to 5	1 to 5	Less than 50%	100%
Manchester	Over 20	1 to 5	Between 50% and 99%	100%
Medway	1 to 5	None	100%	100%
Merton	1 to 5	None	100%	100%
Milton Keynes	1 to 5	None	100%	100%
Newcastle upon Tyne	6 to 10	None	100%	100%
Newham	Over 20	11 to 20	Between 50% and 99%	Between 50% and 99%
Norwich	6 to 10	1 to 5	Between 50% and 99%	100%
Nottingham	6 to 10	None	100%	100%
Oldham	1 to 5	None	100%	100%
Plymouth	1 to 5	None	100%	100%
Portsmouth	1 to 5	1 to 5	Between 50% and 99%	100%
Reading	1 to 5	1 to 5	Between 50% and 99%	100%
Redbridge	1 to 5	None	100%	100%
Salford	Over 20	6 to 10	Between 50% and 99%	100%
Sandwell	1 to 5	None	100%	100%
Sefton	1 to 5	None	100%	100%
Sheffield	6 to 10	1 to 5	Between 50% and 99%	100%
Slough	6 to 10	1 to 5	Between 50% and 99%	100%
Southend-on-Sea	1 to 5	1 to 5	Less than 50%	Less than 50%
Southwark	11 to 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Stockton-on-Tees	1 to 5	None	100%	100%
Sunderland	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Sutton	1 to 5	1 to 5	Between 50% and 99%	100%
Tower Hamlets	Over 20	6 to 10	Between 50% and 99%	Between 50% and 99%
Trafford	1 to 5	None	100%	100%
Waltham Forest	1 to 5	None	100%	100%
Wandsworth	11 to 20	1 to 5	Between 50% and 99%	100%
Westminster	11 to 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Windsor and Maidenhead	1 to 5	None	100%	100%
Wolverhampton	1 to 5	None	100%	100%

## ACM_5
ACM remediation progress by tenure for Greater Manchester, London and the Rest of England, 31 December 2024
Back to Contents
This worksheet contains three tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings for each tenure.
Manchester	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	38	81%	16	89%	5	100%	2	100%	0	0%	61	85%
Works complete awaiting building control signoff	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation started - cladding removed	9	19%	2	11%	0	0%	0	0%	0	0%	11	15%
Remediation started	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Plans in place	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	47	100%	18	100%	5	100%	2	100%	0	0%	72	100%

London	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	64	78%	138	78%	13	87%	11	73%	0	0%	226	78%
Works complete awaiting building control signoff	9	11%	4	2%	1	7%	2	13%	1	100%	17	6%
Remediation started - cladding removed	9	11%	8	4%	0	0%	1	7%	0	0%	18	6%
Remediation started	0	0%	10	6%	0	0%	1	7%	0	0%	11	4%
Plans in place	0	0%	16	9%	1	7%	0	0%	0	0%	17	6%
Responded with intent	0	0%	1	1%	0	0%	0	0%	0	0%	1	0%
Remediation plan unclear	0	0%	1	1%	0	0%	0	0%	0	0%	1	0%
Total buildings	82	100%	178	100%	15	100%	15	100%	1	100%	291	100%

Rest of England	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	32	97%	43	77%	37	93%	14	93%	7	100%	133	88%
Works complete awaiting building control signoff	0	0%	8	14%	1	3%	0	0%	0	0%	9	6%
Remediation started - cladding removed	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation started	0	0%	4	7%	2	5%	0	0%	0	0%	6	4%
Plans in place	1	3%	1	2%	0	0%	0	0%	0	0%	2	1%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	0	0%	0	0%	1	7%	0	0%	1	1%
Total buildings	33	100%	56	100%	40	100%	15	100%	7	100%	151	100%

## ACM_6
ACM remediation progress by date identified with unsafe ACM cladding and by tenure, England, 31 December 2024
Back to Contents
This worksheet contains four tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings for each tenure.
Identified by 31 December 2019	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	128	83%	170	90%	51	98%	25	93%	7	88%	381	89%
Works complete awaiting building control signoff	8	5%	5	3%	1	2%	1	4%	1	13%	16	4%
Remediation started - cladding removed	18	12%	6	3%	0	0%	1	4%	0	0%	25	6%
Remediation started	0	0%	5	3%	0	0%	0	0%	0	0%	5	1%
Plans in place	0	0%	1	1%	0	0%	0	0%	0	0%	1	0%
Responded with intent	0	0%	1	1%	0	0%	0	0%	0	0%	1	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	154	100%	188	100%	52	100%	27	100%	8	100%	429	100%

Identified by 31 December 2020	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	129	83%	187	88%	52	96%	26	90%	7	88%	401	87%
Works complete awaiting building control signoff	9	6%	8	4%	2	4%	2	7%	1	13%	22	5%
Remediation started - cladding removed	18	12%	8	4%	0	0%	1	3%	0	0%	27	6%
Remediation started	0	0%	6	3%	0	0%	0	0%	0	0%	6	1%
Plans in place	0	0%	2	1%	0	0%	0	0%	0	0%	2	0%
Responded with intent	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	156	100%	212	100%	54	100%	29	100%	8	100%	459	100%

Identified by 31 December 2021	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	133	83%	193	85%	53	95%	27	87%	7	88%	413	85%
Works complete awaiting building control signoff	9	6%	9	4%	2	4%	2	6%	1	13%	23	5%
Remediation started - cladding removed	18	11%	10	4%	0	0%	1	3%	0	0%	29	6%
Remediation started	0	0%	10	4%	0	0%	1	3%	0	0%	11	2%
Plans in place	0	0%	3	1%	1	2%	0	0%	0	0%	4	1%
Responded with intent	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	160	100%	226	100%	56	100%	31	100%	8	100%	481	100%

Identified by 31 December 2022	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	133	83%	195	84%	53	95%	27	87%	7	88%	415	85%
Works complete awaiting building control signoff	9	6%	11	5%	2	4%	2	6%	1	13%	25	5%
Remediation started - cladding removed	18	11%	10	4%	0	0%	1	3%	0	0%	29	6%
Remediation started	0	0%	11	5%	0	0%	1	3%	0	0%	12	2%
Plans in place	0	0%	3	1%	1	2%	0	0%	0	0%	4	1%
Responded with intent	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Remediation plan unclear	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Total buildings	160	100%	232	100%	56	100%	31	100%	8	100%	487	100%

Identified by 31 December 2023	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	134	83%	195	82%	53	91%	27	87%	7	88%	413	83%
Works complete awaiting building control signoff	9	6%	12	5%	2	3%	2	6%	1	13%	28	6%
Remediation started - cladding removed	18	11%	10	4%	0	0%	1	3%	0	0%	31	6%
Remediation started	0	0%	12	5%	2	3%	1	3%	0	0%	14	3%
Plans in place	0	0%	6	3%	1	2%	0	0%	0	0%	7	1%
Responded with intent	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Remediation plan unclear	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Total buildings	161	100%	237	100%	58	100%	31	100%	8	100%	495	100%

All buildings identified	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	134	83%	197	78%	55	92%	27	84%	7	88%	420	82%
Works complete awaiting building control signoff	9	6%	12	5%	2	3%	2	6%	1	13%	26	5%
Remediation started - cladding removed	18	11%	10	4%	0	0%	1	3%	0	0%	29	6%
Remediation started	0	0%	14	6%	2	3%	1	3%	0	0%	17	3%
Plans in place	1	1%	17	7%	1	2%	0	0%	0	0%	19	4%
Responded with intent	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Remediation plan unclear	0	0%	1	0%	0	0%	1	3%	0	0%	2	0%
Total buildings	162	100%	252	100%	60	100%	32	100%	8	100%	514	100%

## ACM_7
Number of dwellings in buildings identified with unsafe ACM cladding by remediation status, England, 31 December 2024
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of dwellings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
All dwellings	Dwellings in social sector buildings: estimate	Dwellings in private sector buildings: Low estimate	Dwellings in private sector buildings: High estimate	Total dwellings: Low estimate	Total dwellings: High estimate
Remediation completed total	10,100	16,600	19,900	26,700	30,000
Remediation completed	9,800	15,900	19,100	25,700	28,900
Works complete awaiting building control signoff	300	700	800	1,000	1,000
Yet to complete remediation [note_3]	1,800	3,500	3,700	5,300	5,500
Occupied and yet to complete remediation	1,800	3,500	3,600	5,300	5,400
Total	11,900	20,100	23,500	32,000	35,500

Leasehold dwellings	Dwellings in social sector buildings: estimate	Dwellings in private sector buildings: Low estimate	Dwellings in private sector buildings: High estimate	Total dwellings: Low estimate	Total dwellings: High estimate
Remediation completed total	2,800	16,600	19,900	19,400	22,700
Remediation completed	2,800	15,900	19,100	18,600	21,900
Works complete awaiting building control signoff	100	700	800	800	900
Yet to complete remediation [note_3]	500	3,500	3,700	4,000	4,200
Occupied and yet to complete remediation	500	3,500	3,600	4,000	4,100
Total	3,300	20,100	23,500	23,400	26,900

## ACM_8
ACM remediation progress by sources of funding, England, 31 December 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category	In social fund / [note 4]	Not in social fund	Private: government funded / [note 5]	Private: not government funded
Remediation completed	127	7	87	110
Works complete awaiting building control signoff	9	0	5	7
Remediation started - cladding removed	8	10	10	0
Remediation started	0	0	8	6
Plans in place	0	1	16	1
Responded with intent	0	0	0	1
Remediation plan unclear	0	0	0	1
Total	144	18	126	126

## ACM_9
Application progress of ACM buildings funded by the Private Sector Cladding Remediation Fund within and outside of London, England, 31 December 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Category	Number of buildings inside London	Number of buildings outside London
No contact with delivery partners	0	0
Preparing application	0	0
Eligibility application submitted	0	0
Eligibility approved	0	0
Applications approved: for pre-contract support	2	1
Full cost application submitted	0	0
Applications approved: for full costs	66	39
TOTAL	68	40

## ACM_10
Funding approved and expenditure by the Private Sector Cladding Remediation Fund and Social Sector Cladding Remediation Fund, England, 31 December 2024
Back to Contents
This worksheet contains one table. All figures are GBP £ million.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Funding	Social Sector / (£ million)	Private Sector / (£ million)
Approved [note_6, note_7]	297	235
Expenditure [note_8, note_9]	271	320

## ACM_11
Number of buildings identified with ACM cladding systems unlikely to meet Building Regulations, time series, 31 December 2024
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category [note 64]	Dec-18 / Number	Dec-19 / Number	Dec-20 / Number	Dec-21 / Number	Dec-22 / Number	Jan-23 / Number	Feb-23 / Number	Mar-23 / Number	Apr-23 / Number	May-23 / Number	Jun-23 / Number	Jul-23 / Number	Aug-23 / Number	Sep-23 / Number	Oct-23 / Number	Nov-23 / Number	Dec-23 / Number	Jan-24 / Number	Feb-24 / Number	Mar-24 / Number	Apr-24 / Number	May-24 / Number	Jun-24 / Number	Jul-24 / Number	Aug-24 / Number	Sep-24 / Number	Oct-24 / Number	Nov-24 / Number	Dec-24 / Number
Completed Remediation	67	135	216	289	354	357	357	357	359	360	364	367	368	369	369	388	397	399	401	401	405	406	408	411	412	415	416	416	420
Works complete awaiting building control signoff			33	64	53	50	51	51	51	52	51	52	54	53	53	34	28	31	32	32	30	30	29	27	30	28	28	28	26
Remediation started - cladding removed			48	57	35	36	36	37	38	38	38	36	35	37	38	39	37	35	33	33	33	33	32	33	31	30	31	31	29
Remediation started	101	123	120	39	21	21	21	21	19	18	15	15	13	13	13	15	14	15	19	21	19	18	18	17	17	17	15	17	17
Remediation plans in place	171	104	32	15	13	12	11	12	12	14	14	15	15	15	15	14	13	14	9	7	8	8	8	8	8	19	20	18	19
Reported an intent to remediate	40	78	11	15	9	9	11	10	10	7	7	5	5	3	3	1	2	1	1	1	1	1	1	1	1	1	1	1	1
Remediation plan unclear	58	10	2	2	2	3	3	2	1	1	1	1	2	2	4	5	5	1	1	1	2	2	2	2	4	3	3	3	2
Total buildings	437	450	462	481	487	488	490	490	490	490	490	491	492	492	495	496	496	496	496	496	498	498	498	499	503	513	514	514	514

Remediation Category [note 10]	Dec-18 / Percentage (%)	Dec-19 / Percentage (%)	Dec-20 / Percentage (%)	Dec-21 / Percentage (%)	Dec-22 / Percentage (%)	Jan-23 / Percentage (%)	Feb-23 / Percentage (%)	Mar-23 / Percentage (%)	Apr-23 / Percentage (%)	May-23 / Percentage (%)	Jun-23 / Percentage (%)	Jul-23 / Percentage (%)	Aug-23 / Percentage (%)	Sep-23 / Percentage (%)	Oct-23 / Percentage (%)	Nov-23 / Percentage (%)	Dec-23 / Percentage (%)	Jan-24 / Percentage (%)	Feb-24 / Percentage (%)	Mar-24 / Percentage (%)	Apr-24 / Percentage (%)	May-24 / Percentage (%)	Jun-24 / Percentage (%)	Jul-24 / Percentage (%)	Aug-24 / Percentage (%)	Sep-24 / Percentage (%)	Oct-24 / Percentage (%)	Nov-24 / Percentage (%)	Dec-24 / Percentage (%)
Completed Remediation	15%	30%	47%	60%	73%	73%	73%	73%	73%	73%	74%	75%	75%	75%	75%	78%	80%	80%	81%	81%	81%	82%	82%	82%	82%	81%	81%	81%	82%
Works complete awaiting building control signoff			7%	13%	11%	10%	10%	10%	10%	11%	10%	11%	11%	11%	11%	7%	6%	6%	6%	6%	6%	6%	6%	5%	6%	5%	5%	5%	5%
Remediation started - cladding removed			10%	12%	7%	7%	7%	8%	8%	8%	8%	7%	7%	8%	8%	8%	7%	7%	7%	7%	7%	7%	6%	7%	6%	6%	6%	6%	6%
Remediation started	23%	27%	26%	8%	4%	4%	4%	4%	4%	4%	3%	3%	3%	3%	3%	3%	3%	3%	4%	4%	4%	4%	4%	3%	3%	3%	3%	3%	3%
Remediation plans in place	39%	23%	7%	3%	3%	2%	2%	2%	2%	3%	3%	3%	3%	3%	3%	3%	3%	3%	2%	1%	2%	2%	2%	2%	2%	4%	4%	4%	4%
Reported an intent to remediate	9%	17%	2%	3%	2%	2%	2%	2%	2%	1%	1%	1%	1%	1%	1%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%
Remediation plan unclear	13%	2%	0%	0%	0%	1%	1%	0%	0%	0%	0%	0%	0%	0%	1%	1%	1%	0%	0%	0%	0%	0%	0%	0%	1%	1%	1%	1%	0%
Total buildings	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%

## WWRF_1
Waking Watch Relief and Replacement Fund applications, buildings and approved funding, 31 December 2024
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Tranche	Applications	Buildings	Approved Applications	Approved Buildings	Leasehold dwellings in approved buildings	Approved Funding / (£ million)	Mean Waking Watch cost per month per dwelling in approved buildings / (£)	Median Waking Watch cost per month per dwelling in approved buildings / (£)	Buildings with alarm installation complete
Waking Watch Relief Fund	329	468	212	320	24,700	27.3	169	104	304
Waking Watch Replacement Fund 2022	38	67	25	47	2,200	2.4	216	210	42
Total [note_10]	367	535	237	367	26,900	29.7	172	106	346

## WWRF_2
Waking Watch Relief Fund applications, buildings and approved funding by administering authority, 31 December 2024
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Administering Authority [note_11]	Applications	Approved Applications	Rejected Applications	Withdrawn Applications	Pending Applications	Application rejection rate / Percentage (%)	Application approval rate / Percentage (%)	Buildings	Approved Buildings	Building approval rate / Percentage (%)	Approved buildings / (% share)	Approved Funding / (£ million)	Mean funding per building / (£)	Median funding per building / (£)
Birmingham	9	8	1	0	0	11%	89%	9	8	89%	3%	1.6	200,826	180,147
Bristol	3	2	1	0	0	33%	67%	3	2	67%	1%	0.1	46,256	46,256
Greater London Authority	110	65	29	16	0	26%	59%	171	111	65%	35%	8.3	74,911	64,551
Greater Manchester Combined Authority	25	20	5	0	0	20%	80%	38	33	87%	10%	2.5	75,477	76,928
Leeds	10	9	0	1	0	0%	90%	12	11	92%	3%	1.8	162,466	124,500
Liverpool	18	17	1	0	0	6%	94%	19	18	95%	6%	1.7	94,400	63,784
Newcastle	3	3	0	0	0	0%	100%	3	3	100%	1%	0.4	128,496	163,181
Sheffield	6	5	0	1	0	0%	83%	7	6	86%	2%	0.5	88,753	87,828
MHCLG (1st Tranche)	35	21	14	0	0	40%	60%	55	39	71%	12%	2.7	69,807	65,577
MHCLG (2nd Tranche)	60	27	32	1	0	53%	45%	70	34	49%	11%	3.8	112,303	81,624
MHCLG (3rd Tranche)	50	35	14	1	0	28%	70%	81	55	68%	17%	3.9	70,341	57,389
MHCLG Total	145	83	60	2	0	41%	57%	206	128	62%	40%	10.4	81,324	65,486
Total [note_10]	329	212	97	20	0	29%	64%	468	320	68%	100%	27.3	85,371	67,894

## WWRF_3
Waking Watch Replacement Fund 2022 applications, buildings and approved funding by administering authority, 31 December 2024
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Administering Authority [note_12]	Applications	Approved Applications	Rejected Applications	Withdrawn Applications	Pending Applications	Application rejection rate / Percentage (%)	Application approval rate / Percentage (%)	Buildings	Approved Buildings	Building approval rate / Percentage (%)	Approved buildings / (% share)	Approved Funding / (£ million)	Mean funding per building / (£)	Median funding per building / (£)
Birmingham	2	2	0	0	0	0%	100%	4	4	100%	9%	0.4	89,328	87,683
MHCLG	25	21	1	3	0	4%	84%	46	40	87%	85%	1.8	45,360	26,643
Greater Manchester Combined Authority	11	2	9	0	0	82%	18%	17	3	18%	6%	0.2	65,206	46,743
Leeds	0	0	0	0	0	0%	0%	0	0	0%	0%	0	0	0
Liverpool	0	0	0	0	0	0%	0%	0	0	0%	0%	0	0	0
Sheffield	0	0	0	0	0	0%	0%	0	0	0%	0%	0	0	0
Total [note_10]	38	25	10	3	0	26%	66%	67	47	70%	100%	2.4	50,369	30,209

## BSF_1
Remediation status of eligible buildings within BSF by tenure, England, 31 December 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each tenure.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 24].
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note 23][note 61]	Social sector residential (leaseholder) / Number	Social sector residential (leaseholder) / Percentage (%)	Social Sector Financial Viability / Number	Social Sector Financial Viability / Percentage (%)	Social Sector Total / Number	Social Sector Total / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Total residential Number	Total residential Percentage (%)
Remediation complete	60	35%	4	20%	64	33%	165	27%	229	28%
Remediation complete: awaiting building control sign-off	16	9%	5	25%	21	11%	114	19%	135	17%
Remediation started	40	23%	0	0%	40	21%	117	19%	157	19%
Remediation plans in place	30	17%	4	20%	34	18%	109	18%	143	18%
Intent to remediate	27	16%	7	35%	34	18%	111	18%	145	18%
Total buildings [note 10]	173	100%	20	100%	193	100%	616	100%	809	100%

## BSF_2
BSF remediation progress of eligible buildings by region, England, 31 December 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each region.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 24].
Some cells refer to notes which can be found in the 'Notes' worksheet.
Region [note 23]	Eligible Buildings in the BSF / Number	Eligible Buildings in the BSF / Percentage(%)	Not Started Remediation / Number	Not Started Remediation / Percentage(%)	Started Remediation / Number	Started Remediation / Percentage(%)	Completed Remediation [note_13] / Number	Completed Remediation [note_13] / Percentage(%)	Eligible Buildings that have Completed Remediation / Percentage (%)	Eligible BSF buildings that have started or completed remediation / Percentage (%)
North West	93	11%	7	2%	28	18%	58	16%	62%	92%
London	554	68%	267	93%	94	60%	193	53%	35%	52%
East of England	16	2%	2	1%	3	2%	11	3%	69%	88%
East Midlands	15	2%	2	1%	5	3%	8	2%	53%	87%
North East	7	1%	2	1%	2	1%	3	1%	43%	71%
South East	45	6%	1	0%	2	1%	42	12%	93%	98%
South West	24	3%	3	1%	9	6%	12	3%	50%	88%
West Midlands	12	1%	1	0%	2	1%	9	2%	75%	92%
Yorkshire and The Humber	43	5%	3	1%	12	8%	28	8%	65%	93%
Total [note 10]	809	100%	288	100%	157	100%	364	100%	45%	64%

## BSF_3
BSF number of eligible buildings by funding allocations, expenditure and tenure, England, 31 December 2024
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables.
All figures are for number of buildings or financial amounts in GBP £ million.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 24].
Some cells refer to notes which can be found in the 'Notes' worksheet.
Some cells in this table are empty because data is not available for these variables.
Table BSF_3a: Number of buildings and amount of funding allocated by funding type and tenure for buildings eligible for the BSF .
Funding Allocations [note_15][note_57][note_60]	Private Sector Residential / Number of Buildings [Note 14]	Private Sector Residential / (£ millions)	Social Sector Financial Viability Number of Buildings [Note 14]	Social Sector Financial Viability (£ millions)	Social Sector Residential (leaseholder) / Number of Buildings	Social Sector Residential (leaseholder) / (£ millions)	Total Funding / (£ millions)
Full Applications Approved	458	1,860	5	5
Pre-Tender Support Allocations	718	297	5	2
Total [note 10]		2,157		7	114	232	2,397

Table BSF_3b: Amount of expenditure from the BSF by tenure.
Expenditure [note_43][note_44][note_60]	Private Sector Residential / Number of Buildings	Private Sector Residential / (£ millions)	Social Sector Financial Viability Number of Buildings	Social Sector Financial Viability (£ millions)	Social Sector Residential (leaseholder) / Number of Buildings	Social Sector Residential (leaseholder) / (£ millions)	Total Number of Buildings	Total Expenditure / (£ millions)
Expenditure Paid	766	1,578	9	7	95	183	870	1,768

## BSF_4
BSF remediation progress of eligible buildings by local authority, England, 31 December 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings.[note_23, note_24]
Some cells refer to notes which can be found in the 'Notes' worksheet.
Local Authority [note_45]	Eligible Buildings in the BSF / Number	Eligible Buildings in the BSF yet to be remediated / Number	Completed Remediation / Percentage(%)	Started or Completed Remediation / Percentage(%)
Adur	1-5	0	100%	100%
Ashford	1-5	1-5	Less than 50%	100%
Barking and Dagenham	8	6	25%	75%
Barnet	1-5	1-5	Less than 50%	50-99%
Barnsley	1-5	0	100%	100%
Bexley	1-5	1-5	Less than 50%	100%
Birmingham	10	8	20%	100%
Bolton	1-5	1-5	50-99%	100%
Bournemouth, Christchurch and Poole	1-5	1-5	50-99%	100%
Bradford	1-5	1-5	Less than 50%	100%
Brent	22	20	9%	45%
Brighton and Hove	1-5	1-5	Less than 50%	100%
Bristol, City of	13	10	23%	77%
Bromley	8	1-5	38%	38%
Buckinghamshire	1-5	0	100%	100%
Calderdale	1-5	1-5	Less than 50%	100%
Cambridge	1-5	1-5	50-99%	100%
Camden	16	14	13%	44%
Chelmsford	1-5	0	100%	100%
City of London	1-5	1-5	Less than 50%	Less than 50%
Coventry	1-5	1-5	Less than 50%	Less than 50%
Croydon	16	12	25%	50%
Dorset	1-5	1-5	Less than 50%	100%
Ealing	9	8	11%	67%
Eastbourne	6	1-5	100%	100%
Enfield	6	6	0%	50%
Gateshead	1-5	1-5	50-99%	100%
Greenwich	15	12	20%	60%
Hackney	40	34	15%	53%
Hammersmith and Fulham	9	8	11%	11%
Haringey	7	1-5	43%	71%
Harrow	1-5	1-5	Less than 50%	50-99%
Havering	1-5	1-5	50-99%	100%
Hillingdon	9	9	0%	0%
Hounslow	16	12	25%	56%
Ipswich	6	1-5	50%	67%
Isle of Wight	1-5	1-5	Less than 50%	100%
Islington	25	24	4%	36%
Kensington and Chelsea	12	10	17%	58%
Kingston upon Thames	1-5	1-5	Less than 50%	Less than 50%
Kirklees	1-5	0	100%	100%
Lambeth	21	16	24%	48%
Lancaster	1-5	0	100%	100%
Leeds	31	17	45%	90%
Leicester	1-5	1-5	Less than 50%	50-99%
Lewes	1-5	0	100%	100%
Lewisham	8	7	13%	50%
Liverpool	19	16	16%	74%
Luton	1-5	1-5	Less than 50%	100%
Manchester	52	30	42%	98%
Mansfield	1-5	1-5	Less than 50%	100%
Medway	1-5	1-5	Less than 50%	100%
Merton	7	1-5	29%	43%
Middlesbrough	1-5	1-5	50-99%	100%
Milton Keynes	1-5	1-5	Less than 50%	50-99%
Newcastle upon Tyne	1-5	1-5	Less than 50%	50-99%
Newham	75	63	16%	45%
North Somerset	1-5	1-5	Less than 50%	100%
North Yorkshire	1-5	1-5	Less than 50%	100%
Nottingham	9	1-5	56%	100%
Peterborough	1-5	0	100%	100%
Plymouth	1-5	1-5	Less than 50%	100%
Portsmouth	1-5	1-5	50-99%	100%
Preston	1-5	0	100%	100%
Reading	13	1-5	85%	92%
Redbridge	7	1-5	57%	57%
Richmond upon Thames	1-5	0	100%	100%
Rother	1-5	1-5	Less than 50%	100%
Salford	15	1-5	67%	100%
Sevenoaks	1-5	1-5	Less than 50%	100%
Sheffield	1-5	1-5	Less than 50%	100%
Slough	1-5	1-5	Less than 50%	100%
Southampton	1-5	0	100%	100%
Southend-on-Sea	1-5	0	100%	100%
Southwark	38	31	18%	47%
Stevenage	1-5	1-5	50-99%	100%
Stockport	1-5	0	100%	100%
Sunderland	1-5	1-5	Less than 50%	Less than 50%
Surrey Heath	1-5	0	100%	100%
Sutton	1-5	1-5	Less than 50%	50-99%
Swindon	1-5	1-5	Less than 50%	100%
Tower Hamlets	117	86	26%	58%
Trafford	1-5	1-5	Less than 50%	Less than 50%
Wakefield	1-5	0	100%	100%
Waltham Forest	1-5	1-5	Less than 50%	Less than 50%
Wandsworth	12	8	33%	92%
Watford	1-5	0	100%	100%
Westminster	26	19	27%	62%
Worcester	1-5	1-5	Less than 50%	100%

## BSF_5
Remediation status of eligible buildings within BSF, time series, England, 31 December 2024
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 24].
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category [note_23, note_66]	Dec-21 / Number	Dec-22 / Number	Jan-23 / Number	Feb-23 / Number	Mar-23 / Number	Apr-23 / Number	May-23 / Number	Jun-23 / Number	Jul-23 / Number	Aug-23 / Number	Sep-23 / Number	Oct-23 / Number	Nov-23 / Number	Dec-23 / Number	Jan-24 / Number	Feb-24 / Number	Mar-24 / Number	Apr-24 / Number	May-24 / Number	Jun-24 / Number	Jul-24 / Number	Aug-24 / Number	Sep-24 / Number	Oct-24 / Number	Nov-24 / Number	Dec-24 / Number
Remediation complete	0	10	11	11	28	37	37	39	46	49	101	124	135	141	143	155	158	168	176	190	200	210	217	220	223	229
Remediation complete: awaiting building control sign-off	18	86	93	97	96	102	107	114	117	122	84	75	77	90	107	106	106	109	111	112	121	116	124	132	134	135
Remediation started	150	247	254	268	266	261	263	264	253	254	258	260	268	255	246	237	247	245	235	222	197	191	176	166	164	157
Remediation not yet started	813	860	850	839	826	814	818	803	534	513	525	517	494	464	451	440	423	393	389	345	283	288	292	292	288	288
Total buildings	981	1203	1208	1215	1216	1214	1225	1220	950	938	968	976	974	950	947	938	934	915	911	869	801	805	809	810	809	809

Remediation Category [note_23, note_66]	Dec-21 / Percentage (%)	Dec-22 / Percentage (%)	Jan-23 / Percentage (%)	Feb-23 / Percentage (%)	Mar-23 / Percentage (%)	Apr-23 / Percentage (%)	May-23 / Percentage (%)	Jun-23 / Percentage (%)	Jul-23 / Percentage (%)	Aug-23 / Percentage (%)	Sep-23 / Percentage (%)	Oct-23 / Percentage (%)	Nov-23 / Percentage (%)	Dec-23 / Percentage (%)	Jan-24 / Percentage (%)	Feb-24 / Percentage (%)	Mar-24 / Percentage (%)	Apr-24 Percentage (%)	May-24 Percentage (%)	Jun-24 Percentage (%)	Jul-24 Percentage (%)	Aug-24 Percentage (%)	Sep-24 Percentage (%)	Oct-24 Percentage (%)	Nov-24 / Percentage (%)	Dec-24 / Percentage (%)
Remediation complete	0%	1%	1%	1%	2%	3%	3%	3%	5%	5%	10%	13%	14%	15%	15%	17%	17%	18%	19%	22%	25%	26%	27%	27%	28%	28%
Remediation complete: awaiting building control sign-off	2%	7%	8%	8%	8%	8%	9%	9%	12%	13%	9%	8%	8%	9%	11%	11%	11%	12%	12%	13%	15%	14%	15%	16%	17%	17%
Remediation started	15%	21%	21%	22%	22%	21%	21%	22%	27%	27%	27%	27%	28%	27%	26%	25%	26%	27%	26%	26%	25%	24%	22%	20%	20%	19%
Remediation not yet started	83%	71%	70%	69%	68%	67%	67%	66%	56%	55%	54%	53%	51%	49%	48%	47%	45%	43%	43%	40%	35%	36%	36%	36%	36%	36%
Total buildings [note_10]	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%

## Combined_1
Remediation progress for buildings with unsafe ACM or being remediated in the Building Safety Fund, England, 31 December 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_16, note_17]	ACM cladding only / Number	ACM cladding only / Percentage (%)	Non-ACM cladding only in the BSF / Number	Non-ACM cladding only in the BSF / Percentage (%)	Both ACM and non-ACM cladding in the BSF / Number	Both ACM and non-ACM cladding in the BSF / Percentage (%)	Total / Number	Total / Percentage (%)
Remediation completed	356	87%	187	27%	41	39%	584	48%
Works complete awaiting building control signoff	20	5%	126	18%	9	9%	155	13%
Remediation started	27	7%	133	19%	39	37%	199	16%
Remediation not started	6	1%	257	37%	16	15%	279	23%
Total	409	100%	703	100%	105	100%	1217	100%

## Combined_2
Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, 31 December 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_13, note_17, note_18, note_42]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total / Number	Total / Percentage (%)
Remediation complete (including those awaiting building control signoff)	340	16%	1,132	38%	1,472	29%
Remediation underway	408	20%	523	18%	931	19%
In programme	1,319	64%	1,289	44%	2,608	52%
Total	2,067	100%	2,944	100%	5,011	100%

## Combined_3
Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, by local authority, England, 31 December 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Local Authority [note_13, note_17, note_18, note_42, note_71]	Buildings monitored	In programme / Percentage(%)	Remediation Underway / Percentage(%)	Completed Remediation / Percentage(%)
Barking and Dagenham	11-50	57%	12%	31%
Barnet	51-100	52%	12%	36%
Basingstoke and Deane	11-50	39%	39%	22%
Bexley	11-50	41%	47%	13%
Birmingham	201-400	23%	9%	69%
Bournemouth, Christchurch and Poole	11-50	27%	43%	30%
Bradford	11-50	76%	0%	24%
Brent	51-100	49%	13%	37%
Brighton and Hove	11-50	69%	18%	13%
Bristol, City of	101-200	81%	11%	8%
Bromley	11-50	38%	48%	14%
Cambridge	11-50	67%	17%	17%
Camden	51-100	56%	17%	27%
Chelmsford	11-50	10%	5%	85%
Coventry	11-50	100%	0%	0%
Croydon	51-100	51%	25%	25%
Dacorum	11-50	42%	53%	5%
Dartford	11-50	38%	46%	15%
Ealing	51-100	41%	12%	47%
Eastbourne	11-50	50%	0%	50%
Enfield	11-50	65%	0%	35%
Gateshead	11-50	55%	9%	36%
Greenwich	101-200	62%	9%	29%
Hackney	201-400	65%	12%	23%
Hammersmith and Fulham	11-50	58%	11%	31%
Haringey	51-100	68%	17%	16%
Harrow	11-50	50%	12%	38%
Hastings	11-50	92%	8%	0%
Havering	11-50	33%	50%	17%
Hertsmere	11-50	29%	59%	12%
Hillingdon	11-50	89%	0%	11%
Hounslow	51-100	49%	10%	41%
Ipswich	11-50	58%	21%	21%
Islington	101-200	66%	12%	22%
Kensington and Chelsea	51-100	35%	40%	25%
Kirklees	11-50	78%	6%	17%
Lambeth	101-200	59%	14%	27%
Leeds	51-100	39%	27%	34%
Leicester	11-50	76%	8%	16%
Lewisham	101-200	60%	16%	24%
Liverpool	51-100	48%	17%	35%
Luton	11-50	73%	18%	9%
Maidstone	11-50	31%	25%	44%
Manchester	101-200	45%	13%	42%
Medway	11-50	25%	19%	56%
Merton	11-50	40%	35%	25%
Milton Keynes	11-50	48%	40%	12%
Newcastle upon Tyne	11-50	44%	6%	50%
Newham	101-200	59%	14%	27%
North Somerset	11-50	47%	40%	13%
Norwich	11-50	39%	11%	50%
Nottingham	11-50	53%	6%	42%
Oxford	11-50	42%	0%	58%
Plymouth	11-50	60%	23%	17%
Portsmouth	51-100	33%	34%	33%
Reading	11-50	25%	18%	57%
Redbridge	11-50	55%	17%	28%
Richmond upon Thames	11-50	38%	56%	6%
Salford	51-100	24%	32%	44%
Sheffield	11-50	41%	13%	47%
Slough	11-50	48%	7%	44%
Solihull	11-50	71%	0%	29%
Southampton	101-200	31%	62%	6%
Southwark	101-200	62%	12%	26%
Stevenage	11-50	69%	15%	15%
Sunderland	11-50	50%	0%	50%
Sutton	11-50	22%	44%	33%
Thanet	11-50	50%	0%	50%
Tower Hamlets	over 400	50%	21%	29%
Trafford	11-50	64%	0%	36%
Waltham Forest	11-50	61%	14%	24%
Wandsworth	51-100	46%	8%	45%
West Northamptonshire	11-50	100%	0%	0%
Westminster	51-100	52%	6%	42%
Woking	11-50	35%	62%	4%
Wolverhampton	11-50	77%	0%	23%

## Combined_4
Estimated number of dwellings in buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys by remediation status, England, 31 December 2024
Back to Contents
This worksheet contains one table. All figures are for number of dwellings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
All dwellings [note_10, note_13, note_17, note_18, note_42]	Estimated dwellings in 11-18m buildings	Estimated dwellings in 18m+ buildings	Estimated Total dwellings
Remediation complete (including those awaiting building control signoff)	12,000	80,000	92,000
Remediation underway	12,000	45,000	57,000
In programme	38,000	86,000	124,000
Total	61,000	211,000	272,000

## Combined_5
Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, by tenure, 31 December 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_13, note_17, note_18, note_42]	Private / Number	Private / Percentage (%)	Social / Number	Social / Percentage (%)	Other [note 58] / Number	Other / Percentage (%)	Total / Number	Total / Percentage (%)
Remediation complete (including those awaiting building control signoff)	669	29%	710	27%	93	94%	1,472	29%
Remediation underway	454	20%	473	18%	4	4%	931	19%
In programme	1,193	52%	1,413	54%	2	2%	2,608	52%
Total	2,316	100%	2,596	100%	99	100%	5,011	100%

## Combined_6
Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, time series, 31 December 2024
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category [note_13,note_16, note_17, note_18, note_42, note_65]	Dec-22 / Number	Jan-23 / Number	Feb-23 / Number	Mar-23 / Number	Apr-23 / Number	May-23 / Number	Jun-23 / Number	Jul-23 / Number	Aug-23 / Number	Sep-23 / Number	Oct-23 / Number	Nov-23 / Number	Dec-23 / Number	Jan-24 / Number	Feb-24 / Number	Mar-24 / Number	Apr-24 / Number	May-24 / Number	Jun-24 / Number	Jul-24 / Number	Aug-24 / Number	Sep-24 / Number	Oct-24 / Number	Nov-24 / Number	Dec-24 / Number
Remediation complete (including those awaiting building control signoff)	448	456	461	477	492	499	508	523	535	544	703	777	797	815	863	976	991	1,088	1,332	1,350	1,392	1,412	1,436	1,463	1,472
Remediation underway	301	308	322	321	317	319	320	308	304	311	809	826	811	871	952	992	984	978	969	949	985	1,000	983	934	931
In programme	853	844	834	820	806	806	791	519	501	509	2,285	2,221	2,231	2,286	2,277	2,361	2,361	2,308	2,312	2,331	2,394	2,409	2,415	2,601	2,608
Total	1,602	1,608	1,617	1,618	1,615	1,624	1,619	1,350	1,340	1,364	3,797	3,824	3,839	3,972	4,092	4,329	4,336	4,374	4,613	4,630	4,771	4,821	4,834	4,998	5,011

Remediation Category [note_13, note_16, note_17, note_18, note_42, note_65]	Dec-22 / Percentage (%)	Jan-23 / Percentage (%)	Feb-23 / Percentage (%)	Mar-23 / Percentage (%)	Apr-23 / Percentage (%)	May-23 / Percentage (%)	Jun-23 / Percentage (%)	Jul-23 / Percentage (%)	Aug-23 / Percentage (%)	Sep-23 / Percentage (%)	Oct-23 / Percentage (%)	Nov-23 / Percentage (%)	Dec-23 / Percentage (%)	Jan-24 / Percentage (%)	Feb-24 / Percentage (%)	Mar-24 / Percentage (%)	Apr-24 / Percentage (%)	May-24 / Percentage (%)	Jun-24 / Percentage (%)	Jul-24 / Percentage (%)	Aug-24 / Percentage (%)	Sep-24 / Percentage (%)	Oct-24 / Percentage (%)	Nov-24 / Percentage (%)	Dec-24 / Percentage (%)
Remediation complete (including those awaiting building control signoff)	28%	28%	29%	29%	30%	31%	31%	39%	40%	40%	19%	20%	21%	21%	21%	23%	23%	25%	29%	29%	29%	29%	30%	29%	29%
Remediation underway	19%	19%	20%	20%	20%	20%	20%	23%	23%	23%	21%	22%	21%	22%	23%	23%	23%	22%	21%	20%	21%	21%	20%	19%	19%
In programme	53%	52%	52%	51%	50%	50%	49%	38%	37%	37%	60%	58%	58%	58%	56%	55%	54%	53%	50%	50%	50%	50%	50%	52%	52%
Total	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%

## Combined_7
Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, by region, 31 Decemer 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each region.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Region [note_13, note_16, note_17, note_18, note_42]	Total buildings monitored / Number	Total buildings monitored / Percentage(%)	In programme / Number	In programme / Percentage(%)	Remediation underway / Number	Remediation underway / Percentage(%)	Remediation complete (including those awaiting building control signoff) / Number	Remediation complete (including those awaiting building control signoff) / Percentage(%)	Buildings monitored that have completed Remediation / Percentage (%)	Buildings monitored that have started or completed remediation / Percentage (%)
North West	443	9%	185	7%	84	9%	174	12%	39%	58%
London	2,736	55%	1,515	58%	449	48%	772	52%	28%	45%
East of England	238	5%	114	4%	60	6%	64	4%	27%	52%
East Midlands	89	2%	62	2%	6	1%	21	1%	24%	30%
North East	81	2%	38	1%	4	0%	39	3%	48%	53%
South East	624	12%	264	10%	214	23%	146	10%	23%	58%
South West	331	7%	226	9%	66	7%	39	3%	12%	32%
West Midlands	297	6%	119	5%	18	2%	160	11%	54%	60%
Yorkshire and The Humber	172	3%	85	3%	30	3%	57	4%	33%	51%
Total	5,011	100%	2,608	100%	931	100%	1,472	100%	29%	48%

## CSS_1
Application status of buildings within the CSS, England, 31 December 2024
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings for each tenure.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Pre - eligible buildings [note_47, note_48]	Number	Percentage (%)
Pre - application	2,101	87%
Live application	314	13%
Total pre-eligible buildings	2,415	100%

Eligible buildings [note_13]	Number	Percentage (%)
Works not started	472	90%
Works started	36	7%
Works completed	17	3%
Total eligible buildings	525	100%

## CSS_2
CSS remediation progress by region, England, 31 December 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings unless otherwise stated.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Region [note_48, note_13]	Eligible Buildings in the CSS / Number	Not Started Remediation / Number	Started Remediation / Number	Completed Remediation / Number	Eligible Buildings that have Completed Remediation / Percentage (%)	Eligible CSS buildings that have started or completed remediation / Percentage (%)
North West	83	81	1	1	1%	2%
London	185	156	19	10	5%	16%
East of England	42	37	4	1	2%	12%
East Midlands	30	29	0	1	3%	3%
North East	13	13	0	0	0%	0%
South East	65	56	6	3	5%	14%
South West	46	44	1	1	2%	4%
West Midlands	18	18	0	0	0%	0%
Yorkshire and The Humber	39	35	4	0	0%	10%
Northern Ireland	4	3	1	0	0%	25%
Total	525	472	36	17	3%	10%

## CSS_3
CSS remediation progress by height, England, 31 December 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings unless otherwise stated.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_48, note_13]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)
Remediation complete	16	5%	1	1%
Remediation started	30	9%	6	3%
In programme	302	87%	170	96%
Total buildings	348	100%	177	100%

## CSS_4
CSS remediation progress by tenure, England, 31 December 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings unless otherwise stated.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_48, note_13]	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)
Remediation complete	9	6%	8	2%
Remediation started	15	11%	21	5%
In programme	117	83%	355	92%
Total buildings	141	100%	384	100%

## CSS_5
CSS number of eligible buildings by funding allocations, expenditure and tenure, England, 31 December 2024
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables.
All figures are for number of buildings or financial amounts in GBP £ million.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Table CSS_5a: Number of buildings and amount of funding allocated by funding type and tenure for buildings eligible for the BSF
Funding Allocations	Private Sector Residential / Number of Buildings [Note 14]	Private Sector Residential / (£ millions)	Social Sector Residential / Number of Buildings	Social Sector Residential / (£ millions)	Total Funding / (£ millions)
Works Package Approved	82	297.7	26	29.0	326.7
Pre-Tender Support Allocations	309	85.8	17	2.9	88.7
Total [note 10]	319	383.5	43	31.9	415.4

Table CSS_5b: Amount of expenditure from the CSS by tenure
Expenditure [note_44]	Private Sector Residential / Number of Buildings	Private Sector Residential / (£ millions)	Social Sector Residential / Number of Buildings	Social Sector Residential / (£ millions)	Total Number of Buildings	Total Expenditure / (£ millions)
Expenditure Paid	309	98.3	22	5.4	331	103.7

## CSS_6
CSS remediation progress, time series, England, 31 December 2024
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings unless otherwise stated or percentage of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category [note_48, note_13]	Oct-23 Number	Nov-23 Number	Dec-23 Number	Jan-24 Number	Feb-24 Number	Mar-24 Number	Apr-24 Number	May-24 Number	Jun-24 / Number	Jul-24 / Number	Aug-24 / Number	Sep-24 / Number	Oct-24 / Number	Nov-24 / Number	Dec-24 Number
Remediation complete	0	0	0	0	0	0	0	0	0	0	0	0	14	16	17
Remediation started	0	0	0	0	1	2	2	2	6	8	10	22	17	30	36
In programme	48	75	104	127	151	168	199	222	282	371	395	410	429	446	472
Total buildings	48	75	104	127	152	170	201	224	288	379	405	432	460	492	525

Remediation Category [note_48, note_13]	Oct-23 Percentage (%)	Nov-23 Percentage (%)	Dec-23 Percentage (%)	Jan-24 Percentage (%)	Feb-24 Percentage (%)	Mar-24 Percentage (%)	Apr-24 Percentage (%)	May-24 Percentage (%)	Jun-24 Percentage (%)	Jul-24 Percentage (%)	Aug-24 Percentage (%)	Sep-24 Percentage (%)	Oct-24 Percentage (%)	Nov-24 / Percentage (%)	Dec-24 Percentage (%)
Remediation complete	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	3%	3%	3%
Remediation started	0%	0%	0%	0%	1%	1%	1%	1%	2%	2%	2%	5%	4%	6%	7%
In programme	100%	100%	100%	100%	99%	99%	99%	99%	98%	98%	98%	95%	93%	91%	90%
Total buildings	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%

## Developer_1
Remediation status of buildings requiring works under the developer remediation contract by height group, England, 31 December 2024
Back to Contents
This worksheet contains three tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings identified as requiring works under the Developer Remediation Contract.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category - All Defect Types [Note 25, Note 26, Note 29]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete	153	19%	204	22%	357	20%
Remediation complete - awaiting building control sign-off	30	4%	52	6%	82	5%
Remediation started	161	20%	250	27%	411	24%
Remediation not Started - Plans in Place	200	25%	230	25%	430	25%
Remediation not Started - No Plans in Place	272	33%	193	21%	465	27%
Total	816	100%	929	100%	1,745	100%

Remediation Category - Cladding Defects [Note 25, Note 26, Note 29]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete	133	20%	198	23%	331	22%
Remediation complete - awaiting building control sign-off	18	3%	48	6%	66	4%
Remediation started	147	22%	246	28%	393	26%
Remediation not Started - Plans in Place	168	25%	222	25%	390	25%
Remediation not Started - No Plans in Place	198	30%	157	18%	355	23%
Total	664	100%	871	100%	1,535	100%

Remediation Category - BSF Transfers [Note 25, Note 26, Note 29, Note 62]	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete	32	7%
Remediation complete - awaiting building control sign-off	14	3%
Remediation started	121	27%
Remediation not Started - Plans in Place	126	28%
Remediation not Started - No Plans in Place	63	14%
No life-critical fire-safety defects reported	88	20%
Total buildings	444	100%

## Developer_2
Estimated cost of buildings requiring works under the developer remediation contract by height, England, 31 December 2024
Back to Contents
This worksheet contains one table. All figures are for estimated cost of buildings identified as requiring works under the Developer Remediation Contract in GBP £ million.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Cost Category [Note 29, Note 33]	11-18m / (£ millions)	18m+ / (£ millions)	Total / (£ millions)
Total estimated cost of works	934	2,795	3,729

## Developer_3
Developer by developer breakdown of buildings covered by the developer remediation contract, by number of buildings and remediation requirements, England, 31 October 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 October 2024.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Developer [Note 29]	Number of buildings for which the developer has accepted responsibility under the contract	Number of buildings being remediated solely under a government remediation scheme, for which the developer will reimburse taxpayers [Note 28]	Number of buildings assessed and found to require remediation, and which will be remediated by the developer directly (rather than being remediated through a government fund, with cost re-imbursed by developer) [Note 31]	Number of buildings where it is not known whether remediation is required [Note 32]	Number of buildings where no remediation is required	Number of buildings where the developer has declared that no info raised that there may be defects under clause 5.4d(i) or clause 5.4d(ii) of the developer remediation contract
Total	4683	147	1492	1177	1772	95
Abbey Developments Limited	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	54	14	1	37	2	0
Ballymore Limited	85	16	9	0	13	47
Barratt Developments PLC	702	10	208	380	104	0
Bellway PLC	499	23	152	256	68	0
The Berkeley Group Holdings PLC	820	11	69	23	717	0
Bewley Group Limited	9	2	3	0	4	0
Bloor Investments Limited	-	-	-	-	-	-
The British Land Company PLC	16	0	2	0	14	0
Cala Group (Holdings) Limited	22	0	11	10	1	0
Canary Wharf Group PLC	13	0	0	0	13	0
C.G. Fry and Son Limited	-	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	8	0	0	0	8	0
Crest Nicholson Holdings PLC	287	3	144	126	14	0
Croudace Homes Group Limited	-	-	-	-	-	-
Dandara Living Holdings Limited	21	6	13	0	2	0
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-
Fairview Holdings Limited	119	3	57	5	36	18
Frasers Property (UK) Ltd	23	5	0	10	8	0
Galliard Group Limited	105	0	23	12	70	0
MJ Gleeson PLC	17	1	13	2	1	0
Grosvenor Group Limited	16	0	8	0	0	8
Hill Holdings Limited	90	1	16	15	58	0
Hopkins Home Group Limited	-	-	-	-	-	-
Jelson Holdings Limited	7	0	2	3	2	0
Keepmoat Limited	-	-	-	-	-	-
Land Securities Group PLC	42	3	4	26	9	0
Lendlease Europe Holdings Limited	91	1	33	22	35	0
Pegasus Homes (formerly Lifestory Group)	18	0	1	0	17	0
London Square Development (Holdings) Limited	40	0	38	1	1	0
Miller Homes Limited	37	0	23	0	1	13
Morris Homes Group Limited	6	0	2	0	4	0
Morgan Sindall Group PLC (parent company for Lovell and Muse)	120	7	18	3	92	0
Persimmon Public Limited Company	70	3	47	6	14	0
Redrow PLC	128	3	110	14	1	0
Regal Holdco Limited (parent company for Regal London)	15	0	0	0	15	0
Rowland Group Limited	-	-	-	-	-	-
Rydon Group Holdings Limited	25	3	3	0	19	0
Sorbon Group Limited (parent company for Shanly Homes)	26	0	14	0	12	0
St Modwen Group Holdings Company Limited	13	3	2	5	3	0
Story Homes Limited	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-
Taylor Wimpey PLC	422	8	182	147	85	0
Telford Homes Limited	144	3	102	3	36	0
Tilia Homes Limited	8	0	8	0	0	0
Vistry Group PLC	299	10	109	32	148	0
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-
Weston Group PLC	88	1	21	2	64	0
McCarthy & Stone Limited	61	0	3	3	55	0
Seven Capital PLC	23	1	19	1	0	2
Wates Group Limited	24	1	8	7	8	0
Watkin Jones PLC	14	0	6	8	0	0
Bouygues (UK) Limited	35	4	4	17	10	0
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	21	1	4	1	8	7

## Developer_4
Developer by developer breakdown of buildings which are covered by the developer remediation contract requiring remediation, by remediation status, England, 31 October 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 October 2024.
Some cells refer to notes which can be found in the 'Notes' worksheet.
		Remediation Status
		Proportion of buildings being remediated by the developer directly where remediation is...
		…not yet started		... started or complete		... started		...complete, awaiting building control sign-off		...complete
Developer [Note 25, Note 29]	Total number of buildings assessed and found to require remediation, and which will be remediated by the developer directly [Note 31]	Number	Percentage	Number	Percentage‎	Number	Percentage	Number	Percentage‎	Number	Percentage‎
Total	1492	840	56%	652	44%	360	24%	67	4%	225	15%
Abbey Developments Limited	-	-	-	-	-	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	1	1	100%	0	0%	0	0%	0	0%	0	0%
Ballymore Limited	9	2	22%	7	78%	0	0%	0	0%	7	78%
Barratt Developments PLC	208	124	60%	84	40%	28	13%	47	23%	9	4%
Bellway PLC	152	70	46%	82	54%	55	36%	0	0%	27	18%
The Berkeley Group Holdings PLC	69	22	32%	47	68%	7	10%	2	3%	38	55%
Bewley Group Limited	3	1	33%	2	67%	1	33%	0	0%	1	33%
Bloor Investments Limited	-	-	-	-	-	-	-	-	-	-	-
The British Land Company PLC	2	0	0%	2	100%	2	100%	0	0%	0	0%
Cala Group (Holdings) Limited	11	11	100%	0	0%	0	0%	0	0%	0	0%
Canary Wharf Group PLC	0	0	-	0	-	0	-	0	-	0	-
C.G. Fry and Son Limited	-	-	-	-	-	-	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	0	0	-	0	-	0	-	0	-	0	-
Crest Nicholson Holdings PLC	144	40	28%	104	72%	103	72%	1	1%	0	0%
Croudace Homes Group Limited	-	-	-	-	-	-	-	-	-	-	-
Dandara Living Holdings Limited	13	0	0%	13	100%	13	100%	0	0%	0	0%
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-	-	-	-	-
Fairview Holdings Limited	57	24	42%	33	58%	11	19%	2	4%	20	35%
Frasers Property (UK) Ltd	0	0	-	0	-	0	-	0	-	0	-
Galliard Group Limited	23	7	30%	16	70%	1	4%	1	4%	14	61%
MJ Gleeson PLC	13	9	69%	4	31%	4	31%	0	0%	0	0%
Grosvenor Group Limited	8	7	88%	1	13%	0	0%	0	0%	1	13%
Hill Holdings Limited	16	8	50%	8	50%	1	6%	0	0%	7	44%
Hopkins Home Group Limited	-	-	-	-	-	-	-	-	-	-	-
Jelson Holdings Limited	2	0	0%	2	100%	0	0%	2	100%	0	0%
Keepmoat Limited	-	-	-	-	-	-	-	-	-	-	-
Land Securities Group PLC	4	3	75%	1	25%	1	25%	0	0%	0	0%
Lendlease Europe Holdings Limited	33	25	76%	8	24%	6	18%	0	0%	2	6%
Pegasus Homes (formerly Lifestory Group)	1	1	100%	0	0%	0	0%	0	0%	0	0%
London Square Development (Holdings) Limited	38	38	100%	0	0%	0	0%	0	0%	0	0%
Miller Homes Limited	23	15	65%	8	35%	0	0%	8	35%	0	0%
Morris Homes Group Limited	2	0	0%	2	100%	1	50%	0	0%	1	50%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	18	6	33%	12	67%	6	33%	0	0%	6	33%
Persimmon Public Limited Company	47	26	55%	21	45%	17	36%	0	0%	4	9%
Redrow PLC	110	84	76%	26	24%	18	16%	0	0%	8	7%
Regal Holdco Limited (parent company for Regal London)	0	0	-	0	-	0	-	0	-	0	-
Rowland Group Limited	-	-	-	-	-	-	-	-	-	-	-
Rydon Group Holdings Limited	3	3	100%	0	0%	0	0%	0	0%	0	0%
Sorbon Group Limited (parent company for Shanly Homes)	14	5	36%	9	64%	6	43%	0	0%	3	21%
St Modwen Group Holdings Company Limited	2	1	50%	1	50%	1	50%	0	0%	0	0%
Story Homes Limited	-	-	-	-	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-	-	-	-	-
Taylor Wimpey PLC	182	107	59%	75	41%	31	17%	1	1%	43	24%
Telford Homes Limited	102	98	96%	4	4%	1	1%	0	0%	3	3%
Tilia Homes Limited	8	7	88%	1	13%	1	13%	0	0%	0	0%
Vistry Group PLC	109	60	55%	49	45%	18	17%	3	3%	28	26%
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-	-	-	-	-
Weston Group PLC	21	0	0%	21	100%	21	100%	0	0%	0	0%
McCarthy & Stone Limited	3	0	0%	3	100%	3	100%	0	0%	0	0%
Seven Capital PLC	19	19	100%	0	0%	0	0%	0	0%	0	0%
Wates Group Limited	8	4	50%	4	50%	2	25%	0	0%	2	25%
Watkin Jones PLC	6	6	100%	0	0%	0	0%	0	0%	0	0%
Bouygues (UK) Limited	4	3	75%	1	25%	1	25%	0	0%	0	0%
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	4	3	75%	1	25%	0	0%	0	0%	1	25%

## Developer_5
Developer by developer breakdown of buildings requiring remediation, which have not started works, with start dates England, 31 October 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 October 2024.
Some cells refer to notes which can be found in the 'Notes' worksheet.
		Buildings that require remediation by the developer which have not yet started, with a start date…

		…within the next 12 months		…after the next 12 months		…start date unclear
Developer [Note 27, Note 29]	Total number of buildings being remediated by the developer directly where remediation has not started	Number	Percentage‎	Number	Percentage	Number	Percentage
Total	840	489	58%	115	14%	236	28%
Abbey Developments Limited	-	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	1	0	0%	0	0%	1	100%
Ballymore Limited	2	2	100%	0	0%	0	0%
Barratt Developments PLC	124	93	75%	24	19%	7	6%
Bellway PLC	70	40	57%	20	29%	10	14%
The Berkeley Group Holdings PLC	22	22	100%	0	0%	0	0%
Bewley Group Limited	1	1	100%	0	0%	0	0%
Bloor Investments Limited	-	-	-	-	-	-	-
The British Land Company PLC	0	0	-	0	-	0	-
Cala Group (Holdings) Limited	11	0	0%	0	0%	11	100%
Canary Wharf Group PLC	0	0	-	0	-	0	-
C.G. Fry and Son Limited	-	-	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	0	0	-	0	-	0	-
Crest Nicholson Holdings PLC	40	22	55%	0	0%	18	45%
Croudace Homes Group Limited	-	-	-	-	-	-	-
Dandara Living Holdings Limited	0	0	-	0	-	0	-
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-
Fairview Holdings Limited	24	11	46%	0	0%	13	54%
Frasers Property (UK) Ltd	0	0	-	0	-	0	-
Galliard Group Limited	7	1	14%	4	57%	2	29%
MJ Gleeson PLC	9	7	78%	0	0%	2	22%
Grosvenor Group Limited	7	0	0%	0	0%	7	100%
Hill Holdings Limited	8	3	38%	0	0%	5	63%
Hopkins Home Group Limited	-	-	-	-	-	-	-
Jelson Holdings Limited	0	0	-	0	-	0	-
Keepmoat Limited	-	-	-	-	-	-	-
Land Securities Group PLC	3	0	0%	0	0%	3	100%
Lendlease Europe Holdings Limited	25	24	96%	0	0%	1	4%
Pegasus Homes (formerly Lifestory Group)	1	1	100%	0	0%	0	0%
London Square Development (Holdings) Limited	38	37	97%	0	0%	1	3%
Miller Homes Limited	15	9	60%	2	13%	4	27%
Morris Homes Group Limited	0	0	-	0	-	0	-
Morgan Sindall Group PLC (parent company for Lovell and Muse)	6	3	50%	0	0%	3	50%
Persimmon Public Limited Company	26	23	88%	0	0%	3	12%
Redrow PLC	84	40	48%	44	52%	0	0%
Regal Holdco Limited (parent company for Regal London)	0	0	-	0	-	0	-
Rowland Group Limited	-	-	-	-	-	-	-
Rydon Group Holdings Limited	3	3	100%	0	0%	0	0%
Sorbon Group Limited (parent company for Shanly Homes)	5	0	0%	0	0%	5	100%
St Modwen Group Holdings Company Limited	1	0	0%	0	0%	1	100%
Story Homes Limited	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-
Taylor Wimpey PLC	107	64	60%	4	4%	39	36%
Telford Homes Limited	98	29	30%	10	10%	59	60%
Tilia Homes Limited	7	6	86%	0	0%	1	14%
Vistry Group PLC	60	39	65%	4	7%	17	28%
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-
Weston Group PLC	0	0	-	0	-	0	-
McCarthy & Stone Limited	0	0	-	0	-	0	-
Seven Capital PLC	19	2	11%	2	11%	15	79%
Wates Group Limited	4	2	50%	0	0%	2	50%
Watkin Jones PLC	6	3	50%	1	17%	2	33%
Bouygues (UK) Limited	3	0	0%	0	0%	3	100%
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	3	2	67%	0	0%	1	33%

## Developer_6
Developer by developer breakdown of buildings requiring remediation, which have not started works, with start dates by Financial Year England, 31 October 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 October 2024.
Some cells refer to notes which can be found in the 'Notes' worksheet.
		For buildings which have not yet started, start profiles by financial year...				Buildings which have not yet started, with...

Developer [Note 27, Note 29]	Total number of buildings being remediated by the developer directly where remediation has not started	2024-2025	2025-2026	2026-2027	2027-2028	.. no start date provided	... start date prior to 2024-2025
Total	840	275	299	63	0	184	19
Abbey Developments Limited	-	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	1	0	0	0	0	1	0
Ballymore Limited	2	0	2	0	0	0	0
Barratt Developments PLC	124	32	74	11	0	5	2
Bellway PLC	70	14	38	8	0	10	0
The Berkeley Group Holdings PLC	22	10	12	0	0	0	0
Bewley Group Limited	1	1	0	0	0	0	0
Bloor Investments Limited	-	-	-	-	-	-	-
The British Land Company PLC	0	0	0	0	0	0	0
Cala Group (Holdings) Limited	11	0	0	0	0	11	0
Canary Wharf Group PLC	0	0	0	0	0	0	0
C.G. Fry and Son Limited	-	-	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	0	0	0	0	0	0	0
Crest Nicholson Holdings PLC	40	26	0	0	0	14	0
Croudace Homes Group Limited	-	-	-	-	-	-	-
Dandara Living Holdings Limited	0	0	0	0	0	0	0
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-
Fairview Holdings Limited	24	12	0	0	0	9	3
Frasers Property (UK) Ltd	0	0	0	0	0	0	0
Galliard Group Limited	7	2	4	0	0	1	0
MJ Gleeson PLC	9	8	0	0	0	1	0
Grosvenor Group Limited	7	0	0	0	0	7	0
Hill Holdings Limited	8	3	0	0	0	5	0
Hopkins Home Group Limited	-	-	-	-	-	-	-
Jelson Holdings Limited	0	0	0	0	0	0	0
Keepmoat Limited	-	-	-	-	-	-	-
Land Securities Group PLC	3	0	0	0	0	3	0
Lendlease Europe Holdings Limited	25	8	17	0	0	0	0
Pegasus Homes (formerly Lifestory Group)	1	1	0	0	0	0	0
London Square Development (Holdings) Limited	38	37	0	0	0	0	1
Miller Homes Limited	15	5	6	0	0	4	0
Morris Homes Group Limited	0	0	0	0	0	0	0
Morgan Sindall Group PLC (parent company for Lovell and Muse)	6	4	0	0	0	0	2
Persimmon Public Limited Company	26	17	6	0	0	0	3
Redrow PLC	84	6	40	38	0	0	0
Regal Holdco Limited (parent company for Regal London)	0	0	0	0	0	0	0
Rowland Group Limited	-	-	-	-	-	-	-
Rydon Group Holdings Limited	3	2	1	0	0	0	0
Sorbon Group Limited (parent company for Shanly Homes)	5	3	0	0	0	2	0
St Modwen Group Holdings Company Limited	1	0	0	0	0	1	0
Story Homes Limited	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-
Taylor Wimpey PLC	107	49	37	1	0	20	0
Telford Homes Limited	98	14	23	2	0	59	0
Tilia Homes Limited	7	6	0	0	0	1	0
Vistry Group PLC	60	11	30	3	0	8	8
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-
Weston Group PLC	0	0	0	0	0	0	0
McCarthy & Stone Limited	0	0	0	0	0	0	0
Seven Capital PLC	19	0	4	0	0	15	0
Wates Group Limited	4	2	1	0	0	1	0
Watkin Jones PLC	6	0	4	0	0	2	0
Bouygues (UK) Limited	3	0	0	0	0	3	0
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	3	2	0	0	0	1	0

## Developer_7
Developer by developer breakdown of buildings requiring remediation, which had not started works in the previous quarter England, 31 October 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 October 2024.
Some cells refer to notes which can be found in the 'Notes' worksheet.
		For buildings which had not started last quarter, but were due to start this quarter, current remediation status...
Developer [Note 29, Note 55]	Total number of buildings which were forecast to start in the last quarter	... Have not started remediation	Have not started (%)	...Have started remediation	Have started remediation (%)
Total	183	164	90%	19	10%
Abbey Developments Limited	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	0	0	-	0	-
Ballymore Limited	0	0	-	0	-
Barratt Developments PLC	35	23	66%	12	34%
Bellway PLC	5	4	80%	1	20%
The Berkeley Group Holdings PLC	12	12	100%	0	0%
Bewley Group Limited	0	0	-	0	-
Bloor Investments Limited	-	-	-	-	-
The British Land Company PLC	0	0	-	0	-
Cala Group (Holdings) Limited	0	0	-	0	-
Canary Wharf Group PLC	0	0	-	0	-
C.G. Fry and Son Limited	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	0	0	-	0	-
Crest Nicholson Holdings PLC	14	14	100%	0	0%
Croudace Homes Group Limited	-	-	-	-	-
Dandara Living Holdings Limited	0	0	-	0	-
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-
Fairview Holdings Limited	5	5	100%	0	0%
Frasers Property (UK) Ltd	0	0	-	0	-
Galliard Group Limited	0	0	-	0	-
MJ Gleeson PLC	8	8	100%	0	0%
Grosvenor Group Limited	0	0	-	0	-
Hill Holdings Limited	0	0	-	0	-
Hopkins Home Group Limited	-	-	-	-	-
Jelson Holdings Limited	0	0	-	0	-
Keepmoat Limited	-	-	-	-	-
Land Securities Group PLC	0	0	-	0	-
Lendlease Europe Holdings Limited	3	3	100%	0	0%
Pegasus Homes (formerly Lifestory Group)	1	1	100%	0	0%
London Square Development (Holdings) Limited	38	38	100%	0	0%
Miller Homes Limited	1	1	100%	0	0%
Morris Homes Group Limited	0	0	-	0	-
Morgan Sindall Group PLC (parent company for Lovell and Muse)	5	3	60%	2	40%
Persimmon Public Limited Company	10	10	100%	0	0%
Redrow PLC	6	6	100%	0	0%
Regal Holdco Limited (parent company for Regal London)	0	0	-	0	-
Rowland Group Limited	-	-	-	-	-
Rydon Group Holdings Limited	0	0	-	0	-
Sorbon Group Limited (parent company for Shanly Homes)	4	3	75%	1	25%
St Modwen Group Holdings Company Limited	0	0	-	0	-
Story Homes Limited	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-
Taylor Wimpey PLC	26	23	88%	3	12%
Telford Homes Limited	1	1	100%	0	0%
Tilia Homes Limited	4	4	100%	0	0%
Vistry Group PLC	1	1	100%	0	0%
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-
Weston Group PLC	0	0	-	0	-
McCarthy & Stone Limited	0	0	-	0	-
Seven Capital PLC	1	1	100%	0	0%
Wates Group Limited	1	1	100%	0	0%
Watkin Jones PLC	0	0	-	0	-
Bouygues (UK) Limited	0	0	-	0	-
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	2	2	100%	0	0

## Developer_8
Developer by developer breakdown of buildings requiring remediation, which have not completed works, with completion dates England, 31 October 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 October 2024.
Some cells refer to notes which can be found in the 'Notes' worksheet.
		Buildings that require remediation by the developer which have not yet completed, with a completion date…
		…within the next 12 months		…after the next 12 months		…completion date unclear
Developer [Note 29, Note 56]	Total number of buildings being remediated by the developer directly where remediation has not yet completed	Number	Percentage‎	Number	Percentage	Number2	Pecentage
Total	1200	277	23%	606	51%	317	26%
Abbey Developments Limited	-	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	1	0	0%	0	0%	1	100%
Ballymore Limited	2	0	0%	2	100%	0	0%
Barratt Developments PLC	152	30	20%	111	73%	11	7%
Bellway PLC	125	16	13%	86	69%	23	18%
The Berkeley Group Holdings PLC	29	12	41%	10	34%	7	24%
Bewley Group Limited	2	0	0%	0	0%	2	100%
Bloor Investments Limited	-	-	-	-	-	-	-
The British Land Company PLC	2	2	100%	0	0%	0	0%
Cala Group (Holdings) Limited	11	0	0%	0	0%	11	100%
Canary Wharf Group PLC	0	0	-	0	-	0	-
C.G. Fry and Son Limited	-	-	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	0	0	-	0	-	0	-
Crest Nicholson Holdings PLC	143	45	31%	63	44%	35	24%
Croudace Homes Group Limited	-	-	-	-	-	-	-
Dandara Living Holdings Limited	13	1	8%	12	92%	0	0%
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-
Fairview Holdings Limited	35	20	57%	2	6%	13	37%
Frasers Property (UK) Ltd	0	0	-	0	-	0	-
Galliard Group Limited	8	2	25%	5	63%	1	13%
MJ Gleeson PLC	13	12	92%	0	0%	1	8%
Grosvenor Group Limited	7	0	0%	0	0%	7	100%
Hill Holdings Limited	9	3	33%	0	0%	6	67%
Hopkins Home Group Limited	-	-	-	-	-	-	-
Jelson Holdings Limited	0	0	-	0	-	0	-
Keepmoat Limited	-	-	-	-	-	-	-
Land Securities Group PLC	4	0	0%	0	0%	4	100%
Lendlease Europe Holdings Limited	31	10	32%	21	68%	0	0%
Pegasus Homes (formerly Lifestory Group)	1	1	100%	0	0%	0	0%
London Square Development (Holdings) Limited	38	0	0%	0	0%	38	100%
Miller Homes Limited	15	4	27%	7	47%	4	27%
Morris Homes Group Limited	1	1	100%	0	0%	0	0%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	12	5	42%	2	17%	5	42%
Persimmon Public Limited Company	43	10	23%	33	77%	0	0%
Redrow PLC	102	10	10%	89	87%	3	3%
Regal Holdco Limited (parent company for Regal London)	0	0	-	0	-	0	-
Rowland Group Limited	-	-	-	-	-	-	-
Rydon Group Holdings Limited	3	1	33%	2	67%	0	0%
Sorbon Group Limited (parent company for Shanly Homes)	11	4	36%	0	0%	7	64%
St Modwen Group Holdings Company Limited	2	2	100%	0	0%	0	0%
Story Homes Limited	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-
Taylor Wimpey PLC	138	36	26%	80	58%	22	16%
Telford Homes Limited	99	2	2%	37	37%	60	61%
Tilia Homes Limited	8	5	63%	0	0%	3	38%
Vistry Group PLC	78	17	22%	39	50%	22	28%
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-
Weston Group PLC	21	19	90%	0	0%	2	10%
McCarthy & Stone Limited	3	0	0%	0	0%	3	100%
Seven Capital PLC	19	0	0%	0	0%	19	100%
Wates Group Limited	6	4	67%	1	17%	1	17%
Watkin Jones PLC	6	0	0%	4	67%	2	33%
Bouygues (UK) Limited	4	1	25%	0	0%	3	75%
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	3	2	67%	0	0%	1	33%

## Developer_9
Developer by developer breakdown of buildings requiring remediation, which have not completed works, with completion dates by Financial Year England, 31 October 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings for each developer that has signed the developer remediation contract, as of 31 October 2024.
Some cells refer to notes which can be found in the 'Notes' worksheet.
		For buildings which have not yet completed, completion profiles by financial year...					Buildings which have not yet completed, with...

Developer [Note 29, Note 56]	Total number of buildings being remediated by the developer directly where remediation has not yet completed	2024-2025	2025-2026	2026-2027	2027-2028	2028-2029	.. no completiondate provided	... completion date prior to 2024-2025
Total	1200	150	324	280	129	25	267	25
Abbey Developments Limited	-	-	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	1	0	0	0	0	0	1	0
Ballymore Limited	2	0	0	2	0	0	0	0
Barratt Developments PLC	152	16	33	62	30	0	9	2
Bellway PLC	125	12	23	16	33	21	14	6
The Berkeley Group Holdings PLC	29	6	16	3	0	0	4	0
Bewley Group Limited	2	0	0	0	0	0	2	0
Bloor Investments Limited	-	-	-	-	-	-	-	-
The British Land Company PLC	2	1	1	0	0	0	0	0
Cala Group (Holdings) Limited	11	0	0	0	0	0	11	0
Canary Wharf Group PLC	0	0	0	0	0	0	0	0
C.G. Fry and Son Limited	-	-	-	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	0	0	0	0	0	0	0	0
Crest Nicholson Holdings PLC	143	22	43	42	1	0	33	2
Croudace Homes Group Limited	-	-	-	-	-	-	-	-
Dandara Living Holdings Limited	13	0	1	3	5	4	0	0
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-	-
Fairview Holdings Limited	35	14	12	0	0	0	4	5
Frasers Property (UK) Ltd	0	0	0	0	0	0	0	0
Galliard Group Limited	8	3	1	0	4	0	0	0
MJ Gleeson PLC	13	6	6	0	0	0	1	0
Grosvenor Group Limited	7	0	0	0	0	0	7	0
Hill Holdings Limited	9	3	0	0	0	0	6	0
Hopkins Home Group Limited	-	-	-	-	-	-	-	-
Jelson Holdings Limited	0	0	0	0	0	0	0	0
Keepmoat Limited	-	-	-	-	-	-	-	-
Land Securities Group PLC	4	0	0	0	0	0	4	0
Lendlease Europe Holdings Limited	31	0	20	11	0	0	0	0
Pegasus Homes (formerly Lifestory Group)	1	0	1	0	0	0	0	0
London Square Development (Holdings) Limited	38	0	0	0	0	0	38	0
Miller Homes Limited	15	0	6	5	0	0	4	0
Morris Homes Group Limited	1	0	1	0	0	0	0	0
Morgan Sindall Group PLC (parent company for Lovell and Muse)	12	7	1	2	0	0	2	0
Persimmon Public Limited Company	43	6	20	17	0	0	0	0
Redrow PLC	102	8	21	38	32	0	0	3
Regal Holdco Limited (parent company for Regal London)	0	0	0	0	0	0	0	0
Rowland Group Limited	-	-	-	-	-	-	-	-
Rydon Group Holdings Limited	3	1	1	1	0	0	0	0
Sorbon Group Limited (parent company for Shanly Homes)	11	6	0	0	0	0	5	0
St Modwen Group Holdings Company Limited	2	2	0	0	0	0	0	0
Story Homes Limited	-	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-	-
Taylor Wimpey PLC	138	13	61	41	3	0	20	0
Telford Homes Limited	99	1	5	26	8	0	59	0
Tilia Homes Limited	8	0	5	0	0	0	3	0
Vistry Group PLC	78	7	29	10	13	0	14	5
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-	-
Weston Group PLC	21	10	11	0	0	0	0	0
McCarthy & Stone Limited	3	1	0	0	0	0	0	2
Seven Capital PLC	19	0	0	0	0	0	19	0
Wates Group Limited	6	3	2	0	0	0	1	0
Watkin Jones PLC	6	0	3	1	0	0	2	0
Bouygues (UK) Limited	4	0	1	0	0	0	3	0
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	3	2	0	0	0	0	1	0

## Developer_10
Developer by developer breakdown of buildings requiring remediation, which had not completed works in the previous quarter England, 31 October 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 October 2024.
Some cells refer to notes which can be found in the 'Notes' worksheet.
		Buildings which require remediation directly by the developer and were due to complete in the last quarter which…
Developer [Note 29, Note 74]	Total number of buildings which were forecast to complete in the last quarter	... Have not completed remediation	Have not completed remediation (%)	... Have completed remediation	Have completed remediation (%)
Total	59	42	71%	17	29%
Abbey Developments Limited	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	0	0	-	0	-
Ballymore Limited	0	0	-	0	-
Barratt Developments PLC	9	4	44%	5	56%
Bellway PLC	2	2	100%	0	0%
The Berkeley Group Holdings PLC	6	4	67%	2	33%
Bewley Group Limited	0	0	-	0	-
Bloor Investments Limited	-	-	-	-	-
The British Land Company PLC	0	0	-	0	-
Cala Group (Holdings) Limited	0	0	-	0	-
Canary Wharf Group PLC	0	0	-	0	-
C.G. Fry and Son Limited	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	0	0	-	0	-
Crest Nicholson Holdings PLC	3	3	100%	0	0%
Croudace Homes Group Limited	-	-	-	-	-
Dandara Living Holdings Limited	0	0	-	0	-
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-
Fairview Holdings Limited	4	3	75%	1	25%
Frasers Property (UK) Ltd	0	0	-	0	-
Galliard Group Limited	1	0	0%	1	100%
MJ Gleeson PLC	3	3	100%	0	0%
Grosvenor Group Limited	0	0	-	0	-
Hill Holdings Limited	0	0	-	0	-
Hopkins Home Group Limited	-	-	-	-	-
Jelson Holdings Limited	0	0	-	0	-
Keepmoat Limited	-	-	-	-	-
Land Securities Group PLC	0	0	-	0	-
Lendlease Europe Holdings Limited	2	0	0%	2	100%
Pegasus Homes (formerly Lifestory Group)	0	0	-	0	-
London Square Development (Holdings) Limited	0	0	-	0	-
Miller Homes Limited	0	0	-	0	-
Morris Homes Group Limited	0	0	-	0	-
Morgan Sindall Group PLC (parent company for Lovell and Muse)	3	3	100%	0	0%
Persimmon Public Limited Company	1	1	100%	0	0%
Redrow PLC	3	0	0%	3	100%
Regal Holdco Limited (parent company for Regal London)	0	0	-	0	-
Rowland Group Limited	-	-	-	-	-
Rydon Group Holdings Limited	0	0	-	0	-
Sorbon Group Limited (parent company for Shanly Homes)	5	5	100%	0	0%
St Modwen Group Holdings Company Limited	0	0	-	0	-
Story Homes Limited	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-
Taylor Wimpey PLC	2	1	50%	1	50%
Telford Homes Limited	2	2	100%	0	0%
Tilia Homes Limited	0	0	-	0	-
Vistry Group PLC	10	8	80%	2	20%
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-
Weston Group PLC	2	2	100%	0	0%
McCarthy & Stone Limited	0	0	-	0	-
Seven Capital PLC	0	0	-	0	-
Wates Group Limited	1	1	100%	0	0%
Watkin Jones PLC	0	0	-	0	-
Bouygues (UK) Limited	0	0	-	0	-
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	0	0	-	0	-

## Developer_11
Developer by developer breakdown of buildings, covered by the developer remediation contract and require remediation (excluding completed buildings), by engagement method, England, 31 October 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 October 2024.
Some cells refer to notes which can be found in the 'Notes' worksheet.
	Buildings where the developer or 'responsible entity' has engaged with the leaseholders, freeholders, residents, occupiers and other users regarding works for buildings being remediated directly by the developer, excluding completed buildings, by...					Number of buildings being remediated by the developers, excluding completed buildings	Sum of communication
	... the Responsible Entity		... directly		... directly and by the Responsible Entity		... unconfirmed how
Developer [Note 29]	Number	Percentage	Number	Percentage‎	Number	Percentage	Number	Percentage‎	Number	Percentage‎
Total	754	63%	38	3%	137	11%	147	12%	1200	90%
Abbey Developments Limited	-	-	-	-	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	0	0%	0	0%	0	0%	1	100%	1	100%
Ballymore Limited	2	100%	0	0%	0	0%	0	0%	2	100%
Barratt Developments PLC	0	0%	0	0%	0	0%	141	93%	152	93%
Bellway PLC	124	99%	0	0%	0	0%	0	0%	125	99%
The Berkeley Group Holdings PLC	27	93%	0	0%	2	7%	0	0%	29	100%
Bewley Group Limited	2	100%	0	0%	0	0%	0	0%	2	100%
Bloor Investments Limited	-	-	-	-	-	-	-	-	-	-
The British Land Company PLC	2	100%	0	0%	0	0%	0	0%	2	100%
Cala Group (Holdings) Limited	8	73%	0	0%	1	9%	0	0%	11	82%
Canary Wharf Group PLC	0	-	0	-	0	-	0	-	0	-
C.G. Fry and Son Limited	-	-	-	-	-	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	0	-	0	-	0	-	0	-	0	-
Crest Nicholson Holdings PLC	108	76%	0	0%	0	0%	0	0%	143	76%
Croudace Homes Group Limited	-	-	-	-	-	-	-	-	-	-
Dandara Living Holdings Limited	0	0%	0	0%	13	100%	0	0%	13	100%
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-	-	-	-
Fairview Holdings Limited	0	0%	1	3%	34	97%	0	0%	35	100%
Frasers Property (UK) Ltd	0	-	0	-	0	-	0	-	0	-
Galliard Group Limited	7	88%	0	0%	1	13%	0	0%	8	100%
MJ Gleeson PLC	8	62%	2	15%	3	23%	0	0%	13	100%
Grosvenor Group Limited	0	0%	5	71%	2	29%	0	0%	7	100%
Hill Holdings Limited	4	44%	0	0%	1	11%	0	0%	9	56%
Hopkins Home Group Limited	-	-	-	-	-	-	-	-	-	-
Jelson Holdings Limited	0	-	0	-	0	-	0	-	0	-
Keepmoat Limited	-	-	-	-	-	-	-	-	-	-
Land Securities Group PLC	0	0%	0	0%	0	0%	0	0%	4	0%
Lendlease Europe Holdings Limited	0	0%	0	0%	0	0%	0	0%	31	0%
Pegasus Homes (formerly Lifestory Group)	0	0%	1	100%	0	0%	0	0%	1	100%
London Square Development (Holdings) Limited	38	100%	0	0%	0	0%	0	0%	38	100%
Miller Homes Limited	6	40%	0	0%	5	33%	0	0%	15	73%
Morris Homes Group Limited	1	100%	0	0%	0	0%	0	0%	1	100%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	5	42%	0	0%	7	58%	0	0%	12	100%
Persimmon Public Limited Company	42	98%	0	0%	0	0%	0	0%	43	98%
Redrow PLC	90	88%	12	12%	0	0%	0	0%	102	100%
Regal Holdco Limited (parent company for Regal London)	0	-	0	-	0	-	0	-	0	-
Rowland Group Limited	-	-	-	-	-	-	-	-	-	-
Rydon Group Holdings Limited	3	100%	0	0%	0	0%	0	0%	3	100%
Sorbon Group Limited (parent company for Shanly Homes)	0	0%	0	0%	11	100%	0	0%	11	100%
St Modwen Group Holdings Company Limited	0	0%	0	0%	0	0%	0	0%	2	0%
Story Homes Limited	-	-	-	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-	-	-	-
Taylor Wimpey PLC	138	100%	0	0%	0	0%	0	0%	138	100%
Telford Homes Limited	76	77%	1	1%	22	22%	0	0%	99	100%
Tilia Homes Limited	7	88%	0	0%	0	0%	0	0%	8	88%
Vistry Group PLC	41	53%	14	18%	15	19%	0	0%	78	90%
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-	-	-	-
Weston Group PLC	13	62%	0	0%	8	38%	0	0%	21	100%
McCarthy & Stone Limited	0	0%	0	0%	0	0%	0	0%	3	0%
Seven Capital PLC	0	0%	0	0%	0	0%	5	26%	19	26%
Wates Group Limited	0	0%	1	17%	5	83%	0	0%	6	100%
Watkin Jones PLC	0	0%	0	0%	6	100%	0	0%	6	100%
Bouygues (UK) Limited	0	0%	0	0%	1	25%	0	0%	4	25%
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	2	67%	1	33%	0	0%	0	0%	3	100%

## Developer_12
Remediation status of buildings requiring works under the developer remediation contract, time series, England, 30 November 2024
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings identified as requiring works under the Developer Remediation Contract.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category - All Defect Types [Note 25, Note 26, Note 29, Note 67]	Oct-23 Number	Oct-23 Percentage (%)	Jan-24 Number	Jan-24 Percentage (%)	Apr-24 Number	Apr-24 Percentage (%)	Jul-24 Number	Jul-24 Percentage (%)	Oct-24 Number	Oct-24 Percentage (%)
Remediation complete	262	19%	307	20%	362	23%	410	25%	439	25%
Remediation started	211	16%	317	21%	365	23%	359	22%	411	24%
Remediation not Started - Plans in Place	506	38%	512	34%	371	24%	455	28%	430	25%
Remediation not Started - No Plans in Place	366	27%	364	24%	471	30%	402	25%	466	27%
Total buildings	1345	100%	1500	100%	1569	100%	1626	100%	1746	100%

Remediation Category - Cladding Defects [Note 25, Note 26, Note 29, Note 67]	Oct-23 Number	Oct-23 Percentage (%)	Jan-24 Number	Jan-24 Percentage (%)	Apr-24 Number	Apr-24 Percentage (%)	Jul-24 Number	Jul-24 Percentage (%)	Oct-24 Number	Oct-24 Percentage (%)
Remediation complete	245	19%	284	20%	340	24%	381	26%	397	26%
Remediation started	200	16%	303	22%	337	24%	334	23%	393	26%
Remediation not Started - Plans in Place	476	37%	481	34%	345	24%	418	29%	390	25%
Remediation not Started - No Plans in Place	352	28%	335	24%	406	28%	316	22%	356	23%
Total buildings	1273	100%	1403	100%	1428	100%	1449	100%	1536	100%

## Social_1
Remediation status of buildings with cladding defects monitored under the social housing surveys, England, 31 December 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each tenure.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category - Social Buildings with Unsafe Cladding [Note 34] [Note 35] [Note 37] [Note 59]	11-18m buildings	11-18m buildings	18m+ buildings	18m+ buildings	Total buildings	Total buildings
	Number	Percentage (%)	Number	Percentage (%)	Number	Percentage (%)
Remediation complete [Note 54]	181	15%	484	35%	665	26%
Remediation complete - Awaiting building control sign-off	24	2%	39	3%	63	2%
Remediation started	263	21%	185	14%	448	17%
Remediation works planned	421	34%	426	31%	847	33%
Remediation plans unclear from survey	349	28%	234	17%	583	22%
Total buildings [Note 36]	1,238	100%	1,368	100%	2,606	100%

Social Buildings with Unsafe Cladding identified since June 2017, as reported by Social Housing Providers [Note 34] [Note 35] [Note 37] [Note 68]	11-18m buildings	11-18m buildings	18m+ buildings	18m+ buildings	Total buildings	Total buildings
	Number	Percentage (%)	Number	Percentage (%)	Number	Percentage (%)
Remediation complete - Prior to the most recent assessment	134	11%	366	29%	500	20%
Remediation complete - Since the most recent assessment [Note 54]	65	5%	79	6%	144	6%
Remediation started	262	21%	183	14%	445	18%
Remediation works planned	417	34%	414	33%	831	33%
Remediation plans unclear from survey	345	28%	227	18%	572	23%
Total buildings	1,223	100%	1,269	100%	2,492	100%

Remediation Category - Social Buildings with Unsafe Cladding at the Time of their Most Recent Assessment, as reported by Social Housing Providers [Note 34] [Note 35] [Note 37] [Note 63]	11-18m buildings	11-18m buildings	18m+ buildings	18m+ buildings	Total buildings	Total buildings
	Number	Percentage (%)	Number	Percentage (%)	Number	Percentage (%)
Remediation complete [Note 54]	41	4%	43	5%	84	4%
Remediation complete - Awaiting building control sign-off	24	2%	36	4%	60	3%
Remediation started	262	24%	183	20%	445	22%
Remediation works planned	417	38%	414	46%	831	42%
Remediation plans unclear from survey	345	32%	227	25%	572	29%
Total buildings	1,089	100%	903	100%	1,992	100%

## Social_2
Provider by provider breakdown of building stock and buildings requiring External Wall System (EWS) remediation, England, 30 September 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each social housing provider that has submitted a building level survey, as of 30 September 2024
Some cells refer to notes which can be found in the 'Notes' worksheet.
Providers with more than five buildings over 11 metres [Note 50] [Note 51]	Total number of buildings over 11 metres	Number of buildings identified as having EWS life-critical fire-safety defects since June 2017 [Note_35] [Note_68]	% buildings identified as having EWS life-critical fire-safety defects since June 2017	Number of buildings assessed as having EWS life-critical fire-safety defects at the time of their most recent assessment [Note_35] [Note_52] [Note_63]	% buildings assessed as having EWS life-critical fire-safety defects at the time of their most recent assessment
Total (all providers)	17511	2492	14%	1992	11%
A2Dominion Housing Group Limited	208	44	21%	44	21%
Abri Group Limited	39	6	15%	2	5%
Accent Group Limited	7	2	29%	0	0%
Acis Group Limited	20	0	0%	0	0%
Agudas Israel Housing Association Limited	19	0	0%	0	0%
Anchor Hanover Group	36	10	28%	10	28%
Ashford Borough Council	16	0	0%	0	0%
Ashton Pioneer Homes Limited	10	0	0%	0	0%
Aster Group Limited	43	6	14%	4	9%
B3 Living Limited	11	5	45%	5	45%
Beyond Housing Limited	10	0	0%	0	0%
Birkenhead Forum Housing Association Limited	9	0	0%	0	0%
Birmingham City Council	205	146	71%	22	11%
Bolton at Home Limited	9	0	0%	0	0%
Bournemouth, Christchurch and Poole Council	15	2	13%	0	0%
bpha Limited	27	5	19%	2	7%
Brighter Places	15	0	0%	0	0%
Brighton and Hove City Council	81	0	0%	0	0%
Bristol City Council	126	108	86%	108	86%
Broadland Housing Association Limited	10	2	20%	1	10%
Bromford Housing Group Limited	11	1	9%	1	9%
Cambridge City Council	15	2	13%	2	13%
Central Bedfordshire Council	9	1	11%	1	11%
Christian Action (Enfield) Housing Association Limited	13	3	23%	3	23%
Citizen Housing Group Limited	60	2	3%	2	3%
City of Doncaster Council	9	9	100%	9	100%
City of London Corporation	23	0	0%	0	0%
City of Westminster Council	411	1	0%	1	0%
Clarion Housing Group Limited	548	122	22%	122	22%
Curo Group (Albion) Limited	149	0	0%	0	0%
Dacorum Borough Council	15	4	27%	4	27%
Dudley Metropolitan Borough Council	49	0	0%	0	0%
East End Homes Limited	43	7	16%	6	14%
Eastlight Community Homes Limited	16	0	0%	0	0%
Ekaya Housing Association Limited	10	0	0%	0	0%
Epping Forest District Council	10	1	10%	0	0%
Estuary Housing Association Limited	94	1	1%	1	1%
Exeter City Council	7	0	0%	0	0%
Fairhazel Co-operative Limited	12	0	0%	0	0%
First Choice Homes Oldham Limited	7	2	29%	0	0%
Flagship Housing Group Limited	18	1	6%	1	6%
ForHousing Limited	26	11	42%	5	19%
Gateshead Metropolitan Borough Council	25	0	0%	0	0%
Gateway Housing Association Limited	23	1	4%	1	4%
Gentoo Group Limited	32	11	34%	5	16%
Golding Homes Limited	8	3	38%	3	38%
Gosport Borough Council	6	0	0%	0	0%
Gravesham Borough Council	7	0	0%	0	0%
Great Places Housing Group Limited	17	5	29%	4	24%
GreenSquareAccord Limited	21	18	86%	17	81%
Haringey London Borough Council	91	46	51%	46	51%
Harlow District Council	18	2	11%	2	11%
Hastoe Housing Association Limited	6	3	50%	3	50%
Heart of Medway Housing Association Limited	8	6	75%	0	0%
Hexagon Housing Association Limited	21	20	95%	20	95%
HFL Homes Limited	6	0	0%	0	0%
Hightown Housing Association Limited	20	2	10%	2	10%
Home Group Limited	73	19	26%	19	26%
Housing 21	19	0	0%	0	0%
Housing For Women	20	0	0%	0	0%
Hyde Housing Association Limited	195	61	31%	36	18%
Incommunities Limited	32	11	34%	11	34%
Irwell Valley Housing Association Limited	13	5	38%	5	38%
Islington and Shoreditch Housing Association Limited	45	14	31%	7	16%
Jigsaw Homes Group Limited	19	11	58%	9	47%
Karbon Homes Limited	34	15	44%	15	44%
Karibu Community Homes Limited	10	0	0%	0	0%
Kingston upon Hull City Council	26	0	0%	0	0%
Kirklees Metropolitan Borough Council	21	15	71%	15	71%
Lambeth and Southwark Housing Association Limited	11	0	0%	0	0%
Leeds City Council	131	0	0%	0	0%
Legal & General Affordable Homes Limited	6	0	0%	0	0%
Leicester City Council	11	0	0%	0	0%
LiveWest Homes Limited	64	7	11%	6	9%
Livv Housing Group	9	0	0%	0	0%
London & Quadrant Housing Trust	709	77	11%	55	8%
London Borough of Barking and Dagenham	32	2	6%	2	6%
London Borough of Barnet	48	7	15%	7	15%
London Borough of Brent	167	4	2%	4	2%
London Borough of Camden Council	949	12	1%	5	1%
London Borough of Croydon	67	0	0%	0	0%
London Borough of Ealing	50	2	4%	2	4%
London Borough of Enfield	67	0	0%	0	0%
London Borough of Hackney	460	75	16%	75	16%
London Borough of Hammersmith and Fulham	231	7	3%	7	3%
London Borough of Havering Council	21	0	0%	0	0%
London Borough of Hillingdon	13	0	0%	0	0%
London Borough of Hounslow	56	0	0%	0	0%
London Borough of Islington	385	2	1%	0	0%
London Borough of Lambeth	420	0	0%	0	0%
London Borough of Lewisham	137	26	19%	26	19%
London Borough of Newham	90	58	64%	49	54%
London Borough of Redbridge	19	0	0%	0	0%
London Borough of Sutton	60	1	2%	1	2%
London Borough of Tower Hamlets	326	31	10%	27	8%
London Borough of Waltham Forest	63	27	43%	24	38%
London Borough of Wandsworth	363	2	1%	2	1%
Look Ahead Care and Support Limited	10	2	20%	1	10%
Luton Borough Council	15	0	0%	0	0%
Magenta Living	11	3	27%	3	27%
Manchester City Council	51	20	39%	18	35%
Midland Heart Limited	18	1	6%	0	0%
Moat Homes Limited	23	5	22%	4	17%
New Foundations Housing Association Limited	6	0	0%	0	0%
Newark and Sherwood District Council	6	0	0%	0	0%
Newcastle City Council	55	0	0%	0	0%
Newlon Housing Trust	85	51	60%	47	55%
North London Muslim Housing Association Limited	12	9	75%	9	75%
Norwich City Council	25	2	8%	2	8%
Notting Hill Genesis	968	35	4%	0	0%
Nottingham City Council	24	0	0%	0	0%
Nottingham Community Housing Association Limited	13	0	0%	0	0%
Octavia Housing	113	30	27%	27	24%
One Manchester Limited	23	0	0%	0	0%
One Vision Housing Limited	8	2	25%	0	0%
Onward Group Limited	50	16	32%	8	16%
Orbit Group Limited	82	25	30%	21	26%
Oxford City Council	8	6	75%	6	75%
P3 Housing Limited	32	0	0%	0	0%
Paradigm Housing Group Limited	24	5	21%	0	0%
Paragon Asra Housing Limited	80	21	26%	19	24%
Peabody Trust	1209	196	16%	187	15%
Phoenix Community Housing Association (Bellingham and Downham) Limited	15	4	27%	4	27%
Pinnacle Spaces Limited	6	0	0%	0	0%
Places for People Group Limited	190	33	17%	20	11%
Platform Housing Group Limited	16	2	13%	2	13%
Plus Dane Housing Limited	11	2	18%	2	18%
Plymouth Community Homes Limited	55	4	7%	0	0%
Poplar Housing And Regeneration Community Association Limited	119	32	27%	8	7%
Portsmouth City Council	55	25	45%	14	25%
Providence Row Housing Association	11	1	9%	0	0%
Raven Housing Trust Limited	11	0	0%	0	0%
Reading Borough Council	18	3	17%	3	17%
Regenda Limited	17	4	24%	3	18%
Richmond Housing Partnership Limited	43	16	37%	16	37%
Rochdale Boroughwide Housing Limited	14	7	50%	7	50%
Rooftop Housing Group Limited	6	1	17%	1	17%
Royal Borough of Greenwich	477	1	0%	1	0%
Royal Borough of Kensington and Chelsea	145	7	5%	7	5%
Royal Borough of Kingston Upon Thames	34	0	0%	0	0%
Salix Homes Limited	20	8	40%	0	0%
Salvation Army Housing Association	15	0	0%	0	0%
Sanctuary Housing Association	424	60	14%	42	10%
Sandwell Metropolitan Borough Council	55	1	2%	1	2%
Seymour Housing Co-operative Limited	8	0	0%	0	0%
Sheffield City Council	358	0	0%	0	0%
Soho Housing Association Limited	46	0	0%	0	0%
Solihull Metropolitan Borough Council	37	16	43%	16	43%
Southampton City Council	201	103	51%	103	51%
Southend on Sea City Council	18	0	0%	0	0%
Southern Housing	543	117	22%	109	20%
Southwark Council	851	0	0%	0	0%
Southway Housing Trust (Manchester) Limited	6	0	0%	0	0%
Sovereign Housing Association Limited	309	96	31%	70	23%
Spitalfields Housing Association Limited	7	1	14%	1	14%
St Mungo Community Housing Association	20	1	5%	1	5%
Stevenage Borough Council	12	5	42%	5	42%
Stockport Homes Limited	30	0	0%	0	0%
Stoke on Trent City Council	18	10	56%	10	56%
Stonewater Limited	33	6	18%	4	12%
Swindon Borough Council	8	0	0%	0	0%
Tamworth Borough Council	7	0	0%	0	0%
Teign Housing	8	1	13%	1	13%
Thames Valley Housing Association Limited	259	110	42%	97	37%
Thanet District Council	10	5	50%	5	50%
The ExtraCare Charitable Trust	10	0	0%	0	0%
The Guinness Partnership Limited	309	25	8%	16	5%
The Housing Plus Group Limited	9	0	0%	0	0%
The Industrial Dwellings Society (1885) Limited	35	0	0%	0	0%
The Riverside Group Limited	301	91	30%	91	30%
Thirteen Housing Group Limited	15	0	0%	0	0%
Thrive Homes Limited	6	0	0%	0	0%
Thurrock Council	18	0	0%	0	0%
Together Housing Group Limited	45	12	27%	0	0%
Torus62 Limited	6	0	0%	0	0%
Tower Hamlets Community Housing	37	16	43%	15	41%
Trident Housing Association Limited	11	0	0%	0	0%
Vivid Housing Limited	54	9	17%	2	4%
Wakefield And District Housing Limited	19	4	21%	4	21%
Walsall Housing Group Limited	19	0	0%	0	0%
Wandle Housing Association Limited	39	13	33%	13	33%
Warwick District Council	16	5	31%	5	31%
Watford Community Housing Trust	9	0	0%	0	0%
Watmos Community Homes	29	0	0%	0	0%
West Hampstead Housing Co-operative Limited	11	0	0%	0	0%
West Northamptonshire Council	12	8	67%	8	67%
Wigan Council	7	0	0%	0	0%
Winchester City Council	9	0	0%	0	0%
Woking Borough Council	25	14	56%	14	56%
Wolverhampton City Council	52	9	17%	9	17%
Women's Pioneer Housing Limited	63	0	0%	0	0%
Worthing Homes Limited	6	2	33%	1	17%
Wythenshawe Community Housing Group Limited	12	7	58%	0	0%
YMCA St Paul's Group	6	1	17%	1	17%
Yorkshire Housing Limited	14	0	0%	0	0%
Your Housing Group Limited	26	12	46%	12	46%
Zebra Housing Association Limited	8	0	0%	0	0%
Other RPs	524	41	8%	28	5%

## Social_3
Provider by provider breakdown of buildings, by assessment status, England, 30 September 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each social housing provider that has submitted a building level return, as of 30 September 2024
Some cells refer to notes which can be found in the 'Notes' worksheet.
Providers with more than five buildings over 11 metres [Note 50] [Note 51]	Total number of buildings over 11 metres	Progress with assessments
		Of the total number of buildings over 11m, buildings that…
		…have had a recent works assessment [Note 52]		…have not had a recent works assessment		…have been assessed and identified as having EWS life-critical fire-safety defects at the time of their most recent works assessment [Note_35] [Note_63]
		Number	Percentage	Number	Percentage‎	Number	Percentage
Total (all providers)	17511	17379	99%	132	1%	1992	11%
A2Dominion Housing Group Limited	208	208	100%	0	0%	44	21%
Abri Group Limited	39	39	100%	0	0%	2	5%
Accent Group Limited	7	7	100%	0	0%	0	0%
Acis Group Limited	20	20	100%	0	0%	0	0%
Agudas Israel Housing Association Limited	19	19	100%	0	0%	0	0%
Anchor Hanover Group	36	36	100%	0	0%	10	28%
Ashford Borough Council	16	16	100%	0	0%	0	0%
Ashton Pioneer Homes Limited	10	10	100%	0	0%	0	0%
Aster Group Limited	43	43	100%	0	0%	4	9%
B3 Living Limited	11	11	100%	0	0%	5	45%
Beyond Housing Limited	10	10	100%	0	0%	0	0%
Birkenhead Forum Housing Association Limited	9	9	100%	0	0%	0	0%
Birmingham City Council	205	205	100%	0	0%	22	11%
Bolton at Home Limited	9	9	100%	0	0%	0	0%
Bournemouth, Christchurch and Poole Council	15	15	100%	0	0%	0	0%
bpha Limited	27	27	100%	0	0%	2	7%
Brighter Places	15	15	100%	0	0%	0	0%
Brighton and Hove City Council	81	81	100%	0	0%	0	0%
Bristol City Council	126	126	100%	0	0%	108	86%
Broadland Housing Association Limited	10	10	100%	0	0%	1	10%
Bromford Housing Group Limited	11	11	100%	0	0%	1	9%
Cambridge City Council	15	15	100%	0	0%	2	13%
Central Bedfordshire Council	9	9	100%	0	0%	1	11%
Christian Action (Enfield) Housing Association Limited	13	13	100%	0	0%	3	23%
Citizen Housing Group Limited	60	60	100%	0	0%	2	3%
City of Doncaster Council	9	9	100%	0	0%	9	100%
City of London Corporation	23	23	100%	0	0%	0	0%
City of Westminster Council	411	411	100%	0	0%	1	0%
Clarion Housing Group Limited	548	544	99%	4	1%	122	22%
Curo Group (Albion) Limited	149	149	100%	0	0%	0	0%
Dacorum Borough Council	15	15	100%	0	0%	4	27%
Dudley Metropolitan Borough Council	49	49	100%	0	0%	0	0%
East End Homes Limited	43	43	100%	0	0%	6	14%
Eastlight Community Homes Limited	16	16	100%	0	0%	0	0%
Ekaya Housing Association Limited	10	10	100%	0	0%	0	0%
Epping Forest District Council	10	10	100%	0	0%	0	0%
Estuary Housing Association Limited	94	94	100%	0	0%	1	1%
Exeter City Council	7	7	100%	0	0%	0	0%
Fairhazel Co-operative Limited	12	12	100%	0	0%	0	0%
First Choice Homes Oldham Limited	7	7	100%	0	0%	0	0%
Flagship Housing Group Limited	18	18	100%	0	0%	1	6%
ForHousing Limited	26	26	100%	0	0%	5	19%
Gateshead Metropolitan Borough Council	25	25	100%	0	0%	0	0%
Gateway Housing Association Limited	23	23	100%	0	0%	1	4%
Gentoo Group Limited	32	32	100%	0	0%	5	16%
Golding Homes Limited	8	8	100%	0	0%	3	38%
Gosport Borough Council	6	6	100%	0	0%	0	0%
Gravesham Borough Council	7	7	100%	0	0%	0	0%
Great Places Housing Group Limited	17	17	100%	0	0%	4	24%
GreenSquareAccord Limited	21	21	100%	0	0%	17	81%
Haringey London Borough Council	91	88	97%	3	3%	46	51%
Harlow District Council	18	18	100%	0	0%	2	11%
Hastoe Housing Association Limited	6	6	100%	0	0%	3	50%
Heart of Medway Housing Association Limited	8	8	100%	0	0%	0	0%
Hexagon Housing Association Limited	21	21	100%	0	0%	20	95%
HFL Homes Limited	6	6	100%	0	0%	0	0%
Hightown Housing Association Limited	20	20	100%	0	0%	2	10%
Home Group Limited	73	72	99%	1	1%	19	26%
Housing 21	19	19	100%	0	0%	0	0%
Housing For Women	20	20	100%	0	0%	0	0%
Hyde Housing Association Limited	195	195	100%	0	0%	36	18%
Incommunities Limited	32	32	100%	0	0%	11	34%
Irwell Valley Housing Association Limited	13	13	100%	0	0%	5	38%
Islington and Shoreditch Housing Association Limited	45	45	100%	0	0%	7	16%
Jigsaw Homes Group Limited	19	19	100%	0	0%	9	47%
Karbon Homes Limited	34	34	100%	0	0%	15	44%
Karibu Community Homes Limited	10	9	90%	1	10%	0	0%
Kingston upon Hull City Council	26	26	100%	0	0%	0	0%
Kirklees Metropolitan Borough Council	21	21	100%	0	0%	15	71%
Lambeth and Southwark Housing Association Limited	11	11	100%	0	0%	0	0%
Leeds City Council	131	131	100%	0	0%	0	0%
Legal & General Affordable Homes Limited	6	6	100%	0	0%	0	0%
Leicester City Council	11	11	100%	0	0%	0	0%
LiveWest Homes Limited	64	64	100%	0	0%	6	9%
Livv Housing Group	9	9	100%	0	0%	0	0%
London & Quadrant Housing Trust	709	709	100%	0	0%	55	8%
London Borough of Barking and Dagenham	32	32	100%	0	0%	2	6%
London Borough of Barnet	48	48	100%	0	0%	7	15%
London Borough of Brent	167	167	100%	0	0%	4	2%
London Borough of Camden Council	949	949	100%	0	0%	5	1%
London Borough of Croydon	67	67	100%	0	0%	0	0%
London Borough of Ealing	50	50	100%	0	0%	2	4%
London Borough of Enfield	67	67	100%	0	0%	0	0%
London Borough of Hackney	460	460	100%	0	0%	75	16%
London Borough of Hammersmith and Fulham	231	231	100%	0	0%	7	3%
London Borough of Havering Council	21	21	100%	0	0%	0	0%
London Borough of Hillingdon	13	13	100%	0	0%	0	0%
London Borough of Hounslow	56	56	100%	0	0%	0	0%
London Borough of Islington	385	376	98%	9	2%	0	0%
London Borough of Lambeth	420	420	100%	0	0%	0	0%
London Borough of Lewisham	137	137	100%	0	0%	26	19%
London Borough of Newham	90	90	100%	0	0%	49	54%
London Borough of Redbridge	19	19	100%	0	0%	0	0%
London Borough of Sutton	60	60	100%	0	0%	1	2%
London Borough of Tower Hamlets	326	326	100%	0	0%	27	8%
London Borough of Waltham Forest	63	63	100%	0	0%	24	38%
London Borough of Wandsworth	363	363	100%	0	0%	2	1%
Look Ahead Care and Support Limited	10	10	100%	0	0%	1	10%
Luton Borough Council	15	15	100%	0	0%	0	0%
Magenta Living	11	11	100%	0	0%	3	27%
Manchester City Council	51	51	100%	0	0%	18	35%
Midland Heart Limited	18	18	100%	0	0%	0	0%
Moat Homes Limited	23	22	96%	1	4%	4	17%
New Foundations Housing Association Limited	6	6	100%	0	0%	0	0%
Newark and Sherwood District Council	6	4	67%	2	33%	0	0%
Newcastle City Council	55	55	100%	0	0%	0	0%
Newlon Housing Trust	85	85	100%	0	0%	47	55%
North London Muslim Housing Association Limited	12	12	100%	0	0%	9	75%
Norwich City Council	25	25	100%	0	0%	2	8%
Notting Hill Genesis	968	968	100%	0	0%	0	0%
Nottingham City Council	24	24	100%	0	0%	0	0%
Nottingham Community Housing Association Limited	13	13	100%	0	0%	0	0%
Octavia Housing	113	113	100%	0	0%	27	24%
One Manchester Limited	23	23	100%	0	0%	0	0%
One Vision Housing Limited	8	8	100%	0	0%	0	0%
Onward Group Limited	50	50	100%	0	0%	8	16%
Orbit Group Limited	82	82	100%	0	0%	21	26%
Oxford City Council	8	8	100%	0	0%	6	75%
P3 Housing Limited	32	32	100%	0	0%	0	0%
Paradigm Housing Group Limited	24	24	100%	0	0%	0	0%
Paragon Asra Housing Limited	80	80	100%	0	0%	19	24%
Peabody Trust	1209	1209	100%	0	0%	187	15%
Phoenix Community Housing Association (Bellingham and Downham) Limited	15	15	100%	0	0%	4	27%
Pinnacle Spaces Limited	6	6	100%	0	0%	0	0%
Places for People Group Limited	190	190	100%	0	0%	20	11%
Platform Housing Group Limited	16	16	100%	0	0%	2	13%
Plus Dane Housing Limited	11	11	100%	0	0%	2	18%
Plymouth Community Homes Limited	55	55	100%	0	0%	0	0%
Poplar Housing And Regeneration Community Association Limited	119	119	100%	0	0%	8	7%
Portsmouth City Council	55	55	100%	0	0%	14	25%
Providence Row Housing Association	11	11	100%	0	0%	0	0%
Raven Housing Trust Limited	11	11	100%	0	0%	0	0%
Reading Borough Council	18	18	100%	0	0%	3	17%
Regenda Limited	17	17	100%	0	0%	3	18%
Richmond Housing Partnership Limited	43	43	100%	0	0%	16	37%
Rochdale Boroughwide Housing Limited	14	14	100%	0	0%	7	50%
Rooftop Housing Group Limited	6	6	100%	0	0%	1	17%
Royal Borough of Greenwich	477	477	100%	0	0%	1	0%
Royal Borough of Kensington and Chelsea	145	145	100%	0	0%	7	5%
Royal Borough of Kingston Upon Thames	34	34	100%	0	0%	0	0%
Salix Homes Limited	20	20	100%	0	0%	0	0%
Salvation Army Housing Association	15	15	100%	0	0%	0	0%
Sanctuary Housing Association	424	424	100%	0	0%	42	10%
Sandwell Metropolitan Borough Council	55	55	100%	0	0%	1	2%
Seymour Housing Co-operative Limited	8	8	100%	0	0%	0	0%
Sheffield City Council	358	358	100%	0	0%	0	0%
Soho Housing Association Limited	46	46	100%	0	0%	0	0%
Solihull Metropolitan Borough Council	37	37	100%	0	0%	16	43%
Southampton City Council	201	201	100%	0	0%	103	51%
Southend on Sea City Council	18	18	100%	0	0%	0	0%
Southern Housing	543	543	100%	0	0%	109	20%
Southwark Council	851	851	100%	0	0%	0	0%
Southway Housing Trust (Manchester) Limited	6	6	100%	0	0%	0	0%
Sovereign Housing Association Limited	309	308	100%	1	0%	70	23%
Spitalfields Housing Association Limited	7	7	100%	0	0%	1	14%
St Mungo Community Housing Association	20	20	100%	0	0%	1	5%
Stevenage Borough Council	12	12	100%	0	0%	5	42%
Stockport Homes Limited	30	30	100%	0	0%	0	0%
Stoke on Trent City Council	18	18	100%	0	0%	10	56%
Stonewater Limited	33	33	100%	0	0%	4	12%
Swindon Borough Council	8	8	100%	0	0%	0	0%
Tamworth Borough Council	7	7	100%	0	0%	0	0%
Teign Housing	8	8	100%	0	0%	1	13%
Thames Valley Housing Association Limited	259	150	58%	109	42%	97	37%
Thanet District Council	10	10	100%	0	0%	5	50%
The ExtraCare Charitable Trust	10	10	100%	0	0%	0	0%
The Guinness Partnership Limited	309	309	100%	0	0%	16	5%
The Housing Plus Group Limited	9	9	100%	0	0%	0	0%
The Industrial Dwellings Society (1885) Limited	35	35	100%	0	0%	0	0%
The Riverside Group Limited	301	301	100%	0	0%	91	30%
Thirteen Housing Group Limited	15	15	100%	0	0%	0	0%
Thrive Homes Limited	6	6	100%	0	0%	0	0%
Thurrock Council	18	18	100%	0	0%	0	0%
Together Housing Group Limited	45	45	100%	0	0%	0	0%
Torus62 Limited	6	6	100%	0	0%	0	0%
Tower Hamlets Community Housing	37	37	100%	0	0%	15	41%
Trident Housing Association Limited	11	11	100%	0	0%	0	0%
Vivid Housing Limited	54	54	100%	0	0%	2	4%
Wakefield And District Housing Limited	19	19	100%	0	0%	4	21%
Walsall Housing Group Limited	19	19	100%	0	0%	0	0%
Wandle Housing Association Limited	39	39	100%	0	0%	13	33%
Warwick District Council	16	16	100%	0	0%	5	31%
Watford Community Housing Trust	9	9	100%	0	0%	0	0%
Watmos Community Homes	29	29	100%	0	0%	0	0%
West Hampstead Housing Co-operative Limited	11	11	100%	0	0%	0	0%
West Northamptonshire Council	12	12	100%	0	0%	8	67%
Wigan Council	7	7	100%	0	0%	0	0%
Winchester City Council	9	9	100%	0	0%	0	0%
Woking Borough Council	25	25	100%	0	0%	14	56%
Wolverhampton City Council	52	52	100%	0	0%	9	17%
Women's Pioneer Housing Limited	63	63	100%	0	0%	0	0%
Worthing Homes Limited	6	6	100%	0	0%	1	17%
Wythenshawe Community Housing Group Limited	12	12	100%	0	0%	0	0%
YMCA St Paul's Group	6	6	100%	0	0%	1	17%
Yorkshire Housing Limited	14	14	100%	0	0%	0	0%
Your Housing Group Limited	26	26	100%	0	0%	12	46%
Zebra Housing Association Limited	8	8	100%	0	0%	0	0%
Other RPs	524	523	100%	1	0%	28	5%

## Social_4
Provider by provider breakdown of buildings, by remediation status, England, 30 September 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each social housing provieder that has submitted a building level return, as of 30 September 2024
Some cells refer to notes which can be found in the 'Notes' worksheet.
Providers with more than five buildings over 11 metres [Note 50] [Note 51]	Number of buildings with EWS life-critical fire safety defects since June 2017	Remediation Status
		Number and proportion of buildings identified as having EWS life-critical fire-safety defects [Note 35] [Note 68] since June 2017, where remediation...
		…plans are unclear from survey		…works are planned		…has started		... has completed since the most recent works assessment [Note 54]		... has completed prior to the most recent works assessment
		Number	Percentage	Number	Percentage‎	Number	Percentage	Number	Percentage‎	Number	Percentage‎
Total (all providers)	2492	572	23%	831	33%	445	18%	144	6%	500	20%
A2Dominion Housing Group Limited	44	7	16%	21	48%	2	5%	14	32%	0	0%
Abri Group Limited	6	0	0%	2	33%	0	0%	0	0%	4	67%
Accent Group Limited	2	0	0%	0	0%	0	0%	0	0%	2	100%
Acis Group Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Agudas Israel Housing Association Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Anchor Hanover Group	10	0	0%	2	20%	8	80%	0	0%	0	0%
Ashford Borough Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Ashton Pioneer Homes Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Aster Group Limited	6	0	0%	4	67%	0	0%	0	0%	2	33%
B3 Living Limited	5	5	100%	0	0%	0	0%	0	0%	0	0%
Beyond Housing Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Birkenhead Forum Housing Association Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Birmingham City Council	146	0	0%	7	5%	7	5%	8	5%	124	85%
Bolton at Home Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Bournemouth, Christchurch and Poole Council	2	0	0%	0	0%	0	0%	0	0%	2	100%
bpha Limited	5	2	40%	0	0%	0	0%	0	0%	3	60%
Brighter Places	0	0	0%	0	0%	0	0%	0	0%	0	0%
Brighton and Hove City Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Bristol City Council	108	85	79%	13	12%	10	9%	0	0%	0	0%
Broadland Housing Association Limited	2	1	50%	0	0%	0	0%	0	0%	1	50%
Bromford Housing Group Limited	1	1	100%	0	0%	0	0%	0	0%	0	0%
Cambridge City Council	2	2	100%	0	0%	0	0%	0	0%	0	0%
Central Bedfordshire Council	1	0	0%	1	100%	0	0%	0	0%	0	0%
Christian Action (Enfield) Housing Association Limited	3	3	100%	0	0%	0	0%	0	0%	0	0%
Citizen Housing Group Limited	2	0	0%	2	100%	0	0%	0	0%	0	0%
City of Doncaster Council	9	4	44%	0	0%	5	56%	0	0%	0	0%
City of London Corporation	0	0	0%	0	0%	0	0%	0	0%	0	0%
City of Westminster Council	1	0	0%	1	100%	0	0%	0	0%	0	0%
Clarion Housing Group Limited	122	0	0%	9	7%	93	76%	20	16%	0	0%
Curo Group (Albion) Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Dacorum Borough Council	4	2	50%	0	0%	2	50%	0	0%	0	0%
Dudley Metropolitan Borough Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
East End Homes Limited	7	0	0%	5	71%	0	0%	1	14%	1	14%
Eastlight Community Homes Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Ekaya Housing Association Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Epping Forest District Council	1	0	0%	0	0%	0	0%	0	0%	1	100%
Estuary Housing Association Limited	1	0	0%	1	100%	0	0%	0	0%	0	0%
Exeter City Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Fairhazel Co-operative Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
First Choice Homes Oldham Limited	2	0	0%	0	0%	0	0%	0	0%	2	100%
Flagship Housing Group Limited	1	0	0%	1	100%	0	0%	0	0%	0	0%
ForHousing Limited	11	0	0%	5	45%	0	0%	0	0%	6	55%
Gateshead Metropolitan Borough Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Gateway Housing Association Limited	1	1	100%	0	0%	0	0%	0	0%	0	0%
Gentoo Group Limited	11	4	36%	0	0%	0	0%	1	9%	6	55%
Golding Homes Limited	3	1	33%	0	0%	2	67%	0	0%	0	0%
Gosport Borough Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Gravesham Borough Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Great Places Housing Group Limited	5	0	0%	4	80%	0	0%	0	0%	1	20%
GreenSquareAccord Limited	18	3	17%	14	78%	0	0%	0	0%	1	6%
Haringey London Borough Council	46	0	0%	46	100%	0	0%	0	0%	0	0%
Harlow District Council	2	0	0%	0	0%	0	0%	2	100%	0	0%
Hastoe Housing Association Limited	3	0	0%	2	67%	1	33%	0	0%	0	0%
Heart of Medway Housing Association Limited	6	0	0%	0	0%	0	0%	0	0%	6	100%
Hexagon Housing Association Limited	20	15	75%	3	15%	1	5%	1	5%	0	0%
HFL Homes Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Hightown Housing Association Limited	2	1	50%	0	0%	1	50%	0	0%	0	0%
Home Group Limited	19	0	0%	10	53%	9	47%	0	0%	0	0%
Housing 21	0	0	0%	0	0%	0	0%	0	0%	0	0%
Housing For Women	0	0	0%	0	0%	0	0%	0	0%	0	0%
Hyde Housing Association Limited	61	0	0%	23	38%	2	3%	11	18%	25	41%
Incommunities Limited	11	7	64%	4	36%	0	0%	0	0%	0	0%
Irwell Valley Housing Association Limited	5	4	80%	1	20%	0	0%	0	0%	0	0%
Islington and Shoreditch Housing Association Limited	14	0	0%	6	43%	1	7%	0	0%	7	50%
Jigsaw Homes Group Limited	11	0	0%	2	18%	1	9%	6	55%	2	18%
Karbon Homes Limited	15	0	0%	14	93%	0	0%	1	7%	0	0%
Karibu Community Homes Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Kingston upon Hull City Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Kirklees Metropolitan Borough Council	15	0	0%	14	93%	1	7%	0	0%	0	0%
Lambeth and Southwark Housing Association Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Leeds City Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Legal & General Affordable Homes Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Leicester City Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
LiveWest Homes Limited	7	6	86%	0	0%	0	0%	0	0%	1	14%
Livv Housing Group	0	0	0%	0	0%	0	0%	0	0%	0	0%
London & Quadrant Housing Trust	77	19	25%	2	3%	12	16%	22	29%	22	29%
London Borough of Barking and Dagenham	2	0	0%	2	100%	0	0%	0	0%	0	0%
London Borough of Barnet	7	0	0%	7	100%	0	0%	0	0%	0	0%
London Borough of Brent	4	1	25%	3	75%	0	0%	0	0%	0	0%
London Borough of Camden Council	12	0	0%	5	42%	0	0%	0	0%	7	58%
London Borough of Croydon	0	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Ealing	2	2	100%	0	0%	0	0%	0	0%	0	0%
London Borough of Enfield	0	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Hackney	75	73	97%	1	1%	1	1%	0	0%	0	0%
London Borough of Hammersmith and Fulham	7	0	0%	4	57%	3	43%	0	0%	0	0%
London Borough of Havering Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Hillingdon	0	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Hounslow	0	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Islington	2	0	0%	0	0%	0	0%	0	0%	2	100%
London Borough of Lambeth	0	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Lewisham	26	0	0%	26	100%	0	0%	0	0%	0	0%
London Borough of Newham	58	44	76%	0	0%	5	9%	0	0%	9	16%
London Borough of Redbridge	0	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Sutton	1	0	0%	1	100%	0	0%	0	0%	0	0%
London Borough of Tower Hamlets	31	1	3%	24	77%	2	6%	0	0%	4	13%
London Borough of Waltham Forest	27	17	63%	0	0%	6	22%	1	4%	3	11%
London Borough of Wandsworth	2	0	0%	2	100%	0	0%	0	0%	0	0%
Look Ahead Care and Support Limited	2	0	0%	0	0%	0	0%	1	50%	1	50%
Luton Borough Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Magenta Living	3	0	0%	0	0%	3	100%	0	0%	0	0%
Manchester City Council	20	0	0%	17	85%	1	5%	0	0%	2	10%
Midland Heart Limited	1	0	0%	0	0%	0	0%	0	0%	1	100%
Moat Homes Limited	5	0	0%	2	40%	2	40%	0	0%	1	20%
New Foundations Housing Association Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Newark and Sherwood District Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Newcastle City Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Newlon Housing Trust	51	0	0%	42	82%	5	10%	0	0%	4	8%
North London Muslim Housing Association Limited	9	0	0%	9	100%	0	0%	0	0%	0	0%
Norwich City Council	2	0	0%	0	0%	2	100%	0	0%	0	0%
Notting Hill Genesis	35	0	0%	0	0%	0	0%	0	0%	35	100%
Nottingham City Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Nottingham Community Housing Association Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Octavia Housing	30	27	90%	0	0%	0	0%	0	0%	3	10%
One Manchester Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
One Vision Housing Limited	2	0	0%	0	0%	0	0%	0	0%	2	100%
Onward Group Limited	16	0	0%	4	25%	4	25%	0	0%	8	50%
Orbit Group Limited	25	11	44%	0	0%	10	40%	0	0%	4	16%
Oxford City Council	6	6	100%	0	0%	0	0%	0	0%	0	0%
P3 Housing Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Paradigm Housing Group Limited	5	0	0%	0	0%	0	0%	0	0%	5	100%
Paragon Asra Housing Limited	21	2	10%	14	67%	3	14%	0	0%	2	10%
Peabody Trust	196	76	39%	53	27%	38	19%	20	10%	9	5%
Phoenix Community Housing Association (Bellingham and Downham) Limited	4	0	0%	4	100%	0	0%	0	0%	0	0%
Pinnacle Spaces Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Places for People Group Limited	33	3	9%	15	45%	2	6%	0	0%	13	39%
Platform Housing Group Limited	2	0	0%	2	100%	0	0%	0	0%	0	0%
Plus Dane Housing Limited	2	1	50%	1	50%	0	0%	0	0%	0	0%
Plymouth Community Homes Limited	4	0	0%	0	0%	0	0%	0	0%	4	100%
Poplar Housing And Regeneration Community Association Limited	32	0	0%	6	19%	0	0%	2	6%	24	75%
Portsmouth City Council	25	10	40%	4	16%	0	0%	0	0%	11	44%
Providence Row Housing Association	1	0	0%	0	0%	0	0%	0	0%	1	100%
Raven Housing Trust Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Reading Borough Council	3	0	0%	0	0%	3	100%	0	0%	0	0%
Regenda Limited	4	0	0%	1	25%	0	0%	2	50%	1	25%
Richmond Housing Partnership Limited	16	0	0%	7	44%	9	56%	0	0%	0	0%
Rochdale Boroughwide Housing Limited	7	0	0%	0	0%	7	100%	0	0%	0	0%
Rooftop Housing Group Limited	1	1	100%	0	0%	0	0%	0	0%	0	0%
Royal Borough of Greenwich	1	1	100%	0	0%	0	0%	0	0%	0	0%
Royal Borough of Kensington and Chelsea	7	1	14%	1	14%	0	0%	5	71%	0	0%
Royal Borough of Kingston Upon Thames	0	0	0%	0	0%	0	0%	0	0%	0	0%
Salix Homes Limited	8	0	0%	0	0%	0	0%	0	0%	8	100%
Salvation Army Housing Association	0	0	0%	0	0%	0	0%	0	0%	0	0%
Sanctuary Housing Association	60	1	2%	36	60%	5	8%	0	0%	18	30%
Sandwell Metropolitan Borough Council	1	0	0%	1	100%	0	0%	0	0%	0	0%
Seymour Housing Co-operative Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Sheffield City Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Soho Housing Association Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Solihull Metropolitan Borough Council	16	0	0%	11	69%	0	0%	5	31%	0	0%
Southampton City Council	103	0	0%	24	23%	79	77%	0	0%	0	0%
Southend on Sea City Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Southern Housing	117	2	2%	94	80%	10	9%	3	3%	8	7%
Southwark Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Southway Housing Trust (Manchester) Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Sovereign Housing Association Limited	96	11	11%	37	39%	22	23%	0	0%	26	27%
Spitalfields Housing Association Limited	1	1	100%	0	0%	0	0%	0	0%	0	0%
St Mungo Community Housing Association	1	0	0%	1	100%	0	0%	0	0%	0	0%
Stevenage Borough Council	5	0	0%	5	100%	0	0%	0	0%	0	0%
Stockport Homes Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Stoke on Trent City Council	10	5	50%	3	30%	0	0%	2	20%	0	0%
Stonewater Limited	6	0	0%	3	50%	1	17%	0	0%	2	33%
Swindon Borough Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Tamworth Borough Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Teign Housing	1	0	0%	1	100%	0	0%	0	0%	0	0%
Thames Valley Housing Association Limited	110	79	72%	0	0%	18	16%	0	0%	13	12%
Thanet District Council	5	0	0%	5	100%	0	0%	0	0%	0	0%
The ExtraCare Charitable Trust	0	0	0%	0	0%	0	0%	0	0%	0	0%
The Guinness Partnership Limited	25	4	16%	7	28%	4	16%	1	4%	9	36%
The Housing Plus Group Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
The Industrial Dwellings Society (1885) Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
The Riverside Group Limited	91	0	0%	71	78%	6	7%	14	15%	0	0%
Thirteen Housing Group Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Thrive Homes Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Thurrock Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Together Housing Group Limited	12	0	0%	0	0%	0	0%	0	0%	12	100%
Torus62 Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Tower Hamlets Community Housing	16	0	0%	3	19%	12	75%	0	0%	1	6%
Trident Housing Association Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Vivid Housing Limited	9	1	11%	0	0%	1	11%	0	0%	7	78%
Wakefield And District Housing Limited	4	0	0%	3	75%	1	25%	0	0%	0	0%
Walsall Housing Group Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Wandle Housing Association Limited	13	0	0%	12	92%	1	8%	0	0%	0	0%
Warwick District Council	5	1	20%	4	80%	0	0%	0	0%	0	0%
Watford Community Housing Trust	0	0	0%	0	0%	0	0%	0	0%	0	0%
Watmos Community Homes	0	0	0%	0	0%	0	0%	0	0%	0	0%
West Hampstead Housing Co-operative Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
West Northamptonshire Council	8	0	0%	8	100%	0	0%	0	0%	0	0%
Wigan Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Winchester City Council	0	0	0%	0	0%	0	0%	0	0%	0	0%
Woking Borough Council	14	0	0%	0	0%	14	100%	0	0%	0	0%
Wolverhampton City Council	9	0	0%	9	100%	0	0%	0	0%	0	0%
Women's Pioneer Housing Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Worthing Homes Limited	2	0	0%	1	50%	0	0%	0	0%	1	50%
Wythenshawe Community Housing Group Limited	7	0	0%	0	0%	0	0%	0	0%	7	100%
YMCA St Paul's Group	1	0	0%	1	100%	0	0%	0	0%	0	0%
Yorkshire Housing Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Your Housing Group Limited	12	7	58%	5	42%	0	0%	0	0%	0	0%
Zebra Housing Association Limited	0	0	0%	0	0%	0	0%	0	0%	0	0%
Other RPs	41	10	24%	10	24%	7	17%	1	2%	13	32%

## Social_5
Remediation status of buildings with cladding defects monitored under the social housing surveys, time series, England, 30 November 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category [Note 34] [Note 35] [Note 70]	Aug-23 / Number	Aug-23 / Percentage (%)	Dec-23 / Number	Dec-23 / Percentage (%)	Mar-24 [Note 68] / Number	Mar-24 [Note 68] / Percentage (%)	Jun-24 / Number	Jun-24 / Percentage (%)	Sep-24 / Number	Sep-24 / Percentage (%)
Remediation complete [Note 37] [Note 54]	106	7%	204	10%	661	27%	703	28%	728	28%
Remediation started [Note 75]	394	25%	525	27%	544	23%	565	23%	448	18%
Remediation works planned	591	37%	658	34%	717	30%	699	28%	845	33%
Remediation plans unclear from survey	510	32%	559	29%	488	20%	540	22%	585	21%
Work is not required	7	0%	6	0%	0	0%	0	0%	0	0%
Total buildings	1608	100%	1,952	100%	2,410	100%	2,507	100%	2,606	100%

## Enforcement_1
Enforcement action taken by local authorities against 11m+ buildings under the Housing Act (2004) by remediation programme status, England, 12 December 2024
Back to Contents
This worksheet contains one table. All figures are for the number of enforcement actions by local authority and by the type of remediation programme each building is in [note_19].
Local Authority [note_2]	BSF or CSS only (non-ACM cladding only) / Number	ACM cladding only / Number	BSF or CSS (non-ACM) and ACM cladding / Number	Not in any remediation fund (non-ACM cladding only) / Number	Total / Number
Barking and Dagenham	1	0	0	2	3
Barnet	1	3	1	3	8
Birmingham	4	1	0	5	10
Bournemouth, Christchurch and Poole	2	2	0	2	6
Bradford	0	1	0	0	1
Brent	0	2	0	0	2
Brighton and Hove	0	0	0	0	0
Bristol, City of	6	1	0	3	10
Bromley	0	0	0	0	0
Calderdale	0	0	0	0	0
Camden	17	1	0	24	42
City of London	2	0	0	6	8
Croydon	3	0	1	1	5
Dacorum	0	0	0	1	1
Ealing	2	1	1	0	4
Gateshead	0	0	0	0	0
Greenwich	4	0	0	2	6
Hackney	5	3	2	5	15
Hammersmith and Fulham	9	1	2	31	43
Haringey	0	0	0	0	0
Harrow	0	0	0	0	0
Hillingdon	3	1	0	4	8
Hounslow	0	0	0	1	1
Ipswich	0	0	0	0	0
Islington	2	0	0	0	2
Kensington and Chelsea	0	0	0	0	0
Kingston upon Thames	0	0	0	0	0
Kirklees	0	0	0	0	0
Lambeth	2	2	0	0	4
Leeds	0	0	0	0	0
Leicester	0	0	0	0	0
Lewisham	0	0	0	0	0
Liverpool	4	2	3	2	11
Maidstone	0	0	0	0	0
Manchester	0	0	0	0	0
Medway	0	1	0	0	1
Merton	0	0	0	0	0
Milton Keynes	0	0	0	0	0
Newcastle upon Tyne	6	0	0	10	16
Newham	13	0	1	16	30
North Somerset	0	0	0	0	0
Norwich	0	0	0	0	0
Nottingham	3	1	0	1	5
Plymouth	2	0	0	3	5
Portsmouth	0	1	0	3	4
Reading	3	1	0	1	5
Redbridge	2	0	0	0	2
Salford	1	0	0	0	1
Sheffield	1	0	0	0	1
Slough	0	0	0	0	0
Southampton	3	0	0	0	3
Southwark	29	3	3	23	58
Sunderland	1	0	0	0	1
Sutton	0	0	1	0	1
Thanet	0	0	0	0	0
Tower Hamlets	24	7	5	29	65
Trafford	0	0	0	0	0
Waltham Forest	1	0	0	1	2
Wandsworth	1	2	1	0	4
Westminster	32	4	6	34	76
Windsor and Maidenhead	0	0	0	0	0
Others	15	0	2	19	36
Total	204	41	29	232	506

## Enforcement_2
Category rating of buildings inspected by local authorities, England, 12 December 2024
Back to Contents
This worksheet contains one table. All figures are for the number of inspections by type of rating outcome.
Local Authority [note_2]	Inspections with the building rated Category 1 [note_20] [note_69] / Number	Inspections with the building rated Category 2 [note_20] [note_69] / Number	Rating outcome to be confirmed / Number	Total / Number
Barking and Dagenham	1	2	0	3
Barnet	6	2	0	8
Birmingham	1	7	2	10
Bournemouth, Christchurch and Poole	6	0	0	6
Bradford	0	1	0	1
Brent	1	1	0	2
Brighton and Hove	0	0	0	0
Bristol, City of	0	2	8	10
Bromley	0	0	0	0
Calderdale	0	0	0	0
Camden	3	38	1	42
City of London	5	2	1	8
Croydon	1	4	0	5
Dacorum	0	1	0	1
Ealing	1	3	0	4
Gateshead	0	0	0	0
Greenwich	2	1	3	6
Hackney	8	4	3	15
Hammersmith and Fulham	1	38	4	43
Haringey	0	0	0	0
Harrow	0	0	0	0
Hillingdon	2	5	1	8
Hounslow	1	0	0	1
Ipswich	0	0	0	0
Islington	0	1	1	2
Kensington and Chelsea	0	0	0	0
Kingston upon Thames	0	0	0	0
Kirklees	0	0	0	0
Lambeth	2	2	0	4
Leeds	0	0	0	0
Leicester	0	0	0	0
Lewisham	0	0	0	0
Liverpool	3	6	2	11
Maidstone	0	0	0	0
Manchester	0	0	0	0
Medway	1	0	0	1
Merton	0	0	0	0
Milton Keynes	0	0	0	0
Newcastle upon Tyne	0	13	3	16
Newham	10	18	2	30
North Somerset	0	0	0	0
Norwich	0	0	0	0
Nottingham	0	5	0	5
Plymouth	1	4	0	5
Portsmouth	0	1	3	4
Reading	0	5	0	5
Redbridge	1	1	0	2
Salford	0	1	0	1
Sheffield	0	0	1	1
Slough	0	0	0	0
Southampton	1	0	2	3
Southwark	27	27	4	58
Sunderland	0	0	1	1
Sutton	1	0	0	1
Thanet	0	0	0	0
Tower Hamlets	7	45	13	65
Trafford	0	0	0	0
Waltham Forest	0	2	0	2
Wandsworth	1	3	0	4
Westminster	6	70	0	76
Windsor and Maidenhead	0	0	0	0
Others	12	21	3	36
Total	112	336	58	506

## Enforcement_3
Statutory notices served by local authorities under the Housing Act (2004), England, 12 December 2024
Back to Contents
This worksheet contains one table. All figures are for number of statutory notices served, broken down by type of notice, for each Local Authority.
Local Authority [note_2]	Improvement notices / Number	Hazard awareness notices / Number	Prohibition orders / Number	Total / Number
Barking and Dagenham	1	0	0	1
Barnet	8	0	0	8
Birmingham	7	0	0	7
Bournemouth, Christchurch and Poole	3	0	0	3
Bradford	1	0	0	1
Brent	0	0	0	0
Brighton and Hove	0	0	0	0
Bristol, City of	0	0	0	0
Bromley	0	0	0	0
Calderdale	0	0	0	0
Camden	14	3	0	17
City of London	2	0	0	2
Croydon	0	0	0	0
Dacorum	1	0	0	1
Ealing	2	0	0	2
Gateshead	0	0	0	0
Greenwich	3	0	0	3
Hackney	9	0	0	9
Hammersmith and Fulham	0	2	0	2
Haringey	0	0	0	0
Harrow	0	0	0	0
Hillingdon	5	1	0	6
Hounslow	1	0	0	1
Ipswich	0	0	0	0
Islington	2	0	0	2
Kensington and Chelsea	0	0	0	0
Kingston upon Thames	0	0	0	0
Kirklees	0	0	0	0
Lambeth	4	0	0	4
Leeds	0	0	0	0
Leicester	0	0	0	0
Lewisham	0	0	0	0
Liverpool	5	0	0	5
Maidstone	0	0	0	0
Manchester	0	0	0	0
Medway	1	0	0	1
Merton	0	0	0	0
Milton Keynes	0	0	0	0
Newcastle upon Tyne	2	4	0	6
Newham	26	1	0	27
North Somerset	0	0	0	0
Norwich	0	0	0	0
Nottingham	3	0	0	3
Plymouth	2	3	0	5
Portsmouth	1	0	0	1
Reading	0	0	0	0
Redbridge	0	0	0	0
Salford	0	0	0	0
Sheffield	0	0	0	0
Slough	0	0	0	0
Southampton	1	0	0	1
Southwark	25	1	0	26
Sunderland	0	0	0	0
Sutton	1	0	0	1
Thanet	0	0	0	0
Tower Hamlets	21	17	0	38
Trafford	0	0	0	0
Waltham Forest	1	0	0	1
Wandsworth	1	0	0	1
Westminster	1	19	1	21
Windsor and Maidenhead	0	0	0	0
Others	18	0	0	18
Total	172	51	1	224

## Enforcement_4
Number of inspections by local authorities supported by the Joint Inspection Team, England, 12 December 2024
Back to Contents
This worksheet contains one table. All figures are for the number of inspections supported by the Joint Inspection Team.
Local Authority [note_2]	Inspections supported by the Joint Inspection Team [note_21] / Number
Barking and Dagenham	1
Barnet	4
Birmingham	10
Bournemouth, Christchurch and Poole	2
Bradford	0
Brent	2
Brighton and Hove	0
Bristol, City of	0
Bromley	0
Calderdale	0
Camden	6
City of London	0
Croydon	5
Dacorum	0
Ealing	4
Gateshead	0
Greenwich	7
Hackney	12
Hammersmith and Fulham	3
Haringey	0
Harrow	0
Hillingdon	1
Hounslow	1
Ipswich	0
Islington	2
Kensington and Chelsea	0
Kingston upon Thames	0
Kirklees	0
Lambeth	2
Leeds	0
Leicester	0
Lewisham	0
Liverpool	9
Maidstone	0
Manchester	0
Medway	0
Merton	0
Milton Keynes	0
Newcastle upon Tyne	1
Newham	27
North Somerset	0
Norwich	0
Nottingham	3
Plymouth	1
Portsmouth	3
Reading	0
Redbridge	2
Salford	1
Sheffield	1
Slough	0
Southampton	3
Southwark	3
Sunderland	0
Sutton	1
Thanet	0
Tower Hamlets	15
Trafford	0
Waltham Forest	2
Wandsworth	4
Westminster	2
Windsor and Maidenhead	0
Others	8
Total	148

## JIT_1
Number of Joint Inspection Team training sessions attended by local authorities, England, April 2021 - 31 December 2024
Back to Contents
This worksheet contains one table. All figures are for the number of Joint Inspection Team training sessions attended by local authority officers.
Local Authority [note_22]	Intro to Fire Safety (Level 1) Number	Intermediate Fire Safety (Level 2) [note_73] Number
Barking and Dagenham	0	1
Barnet	4	6
Birmingham	10	16
Bournemouth, Christchurch and Poole	10	5
Bradford	24	5
Brent	1	4
Brighton and Hove	0	0
Bristol, City of	10	6
Bromley	3	0
Calderdale	3	1
Camden	16	17
City of London	8	5
Croydon	26	8
Dacorum	4	3
Ealing	10	6
Gateshead	6	3
Greenwich	2	10
Hackney	18	13
Hammersmith and Fulham	20	16
Haringey	4	2
Harrow	1	2
Hillingdon	3	2
Hounslow	4	4
Ipswich	0	0
Islington	11	9
Kensington and Chelsea	0	1
Kingston upon Thames	3	0
Kirklees	2	1
Lambeth	16	15
Leeds	6	2
Leicester	0	0
Lewisham	5	3
Liverpool	32	15
Maidstone	0	0
Manchester	8	7
Merton	6	4
Medway	12	5
Milton Keynes	6	7
Newcastle upon Tyne	6	5
Newham	10	7
North Somerset	8	5
Norwich	11	7
Nottingham	34	43
Plymouth	3	3
Portsmouth	2	5
Richmond and Wandsworth	8	10
Reading	15	5
Redbridge	4	3
Salford	11	7
Sheffield	0	1
Slough	5	7
Southampton	1	0
Southwark	7	1
Sunderland	3	5
Sutton	2	0
Thanet	2	2
Tower Hamlets	9	13
Trafford	7	3
Waltham Forest	6	7
Westminster	17	11
Windsor and Maidenhead	8	5
Others	414	205
Total	887	564