SLC DSA Quality Committee
25th June 2024
Welcome and thanks
The new DSA service model has been operating since 26 February 2024. SLC attended the Education Select Committee on 23 April and has since met with representatives from the three sector organisations who also gave evidence.

Members’ feedback on the service and on how they wish to see the Committee evolve is welcome. The Disabled Students’ Stakeholder Group and SLC’s DSA Customer Panel are also providing ongoing feedback, as are DSA customers and colleagues.

DSA Reforms update
Since the DSA reforms timeline was presented at the last meeting, some proposed dates have changed. The February service launch delivered the greatest share of the benefits intended in the new service. The new commercial arrangements were due to begin in June and further technical work to provide direct systems integration with the suppliers was expected to be implemented in August. Following thorough and regular assurance work, the next phase is now expected to come into effect in October or November 2024. The one-stop-shop service with Study Tech and Capita will continue, but the commercial arrangements will not begin until the autumn. This also means that full KPI reporting will not be possible until later this year, but a DSA data pack is being developed which SLC will publish quarterly on gov.uk.

Terms of reference
Members were reminded of SLC’s commitment to transparency via KPIs. Customer and members’ feedback will help to drive consistency of service across both suppliers.

Operational performance (KPIs)
Analysis of data from the new service shows an almost even split of the number of students being referred to each supplier. Referrals are trending higher than forecast, and both suppliers are proactively recruiting to accommodate this. The suppliers are performing within KPIs and showing week-on-week improvements. SLC is providing regular feedback to each supplier to ensure that improvements continue. Students are being paired with the most appropriate assessors in terms of relevant knowledge and experience of their conditions. Needs Assessment Reports are being checked in real time.

SLC has discussed with the National Association of Disability Practitioners (NADP) how practitioners can share feedback and operational insights. Practitioners’ views will complement SLC’s perspective. SLC is also scheduling on-site visits and audits with the suppliers.

Customer Experience update
Customer satisfaction data is limited at this early stage in the academic cycle, but initial feedback is encouraging. A new iteration of the Customer Satisfaction survey has been introduced with a more refined question set on customer satisfaction, making it faster and easier to complete to help increase response rates. The survey is issued when SLC receives the equipment invoice from suppliers. Additional supplementary customer research will follow, alongside feedback from SLC’s DSA Customer Panel.

SLC is continuing to monitor the convenience of travel time and provision of suitable locations for in-person assessments.

SLC contacts students if their supplier tells SLC they are leaving the market and provides SLC’s contact details should they require any further support. SLC is writing to all DSA customers to tell them about the reforms.