Annual Review/Programme Completion Review (22/23)

A. Summary Sheet
NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	African Peace Support Operations (APSO) programme
Programme ID	C-AFR-0001
Country and Region	Sub-Saharan Africa
IATI Unique ID	CSSF-03-000017
HMG Partners	MOD - British Peace Support Team (Africa)
Total Budget	ODA: £4.5m (indicative)	Non-ODA: £12m (indicative)
Budget this FY	ODA: £1.082m (actual)	Non-ODA: £4.02m (actual)
Spend this FY	ODA: £1.089m	Non-ODA: £4.037m
Time Frame	Start Date: 1 April 2021	End Date: 31 March 2025

Outputs	Individual Output Rating
OUTPUT 1: Selected partner states have increased knowledge and skills to conduct Force Preparation of military and police capabilities for UN and/or AU peace operations.	n/a*
OUTPUT 2: Selected partner states have increased knowledge on UN PSO doctrine and standards and, where applicable, IHL and PoC frameworks, gender, and conduct and discipline.	n/a*
OUTPUT 3: Personnel deploying to UN and AU missions have increased knowledge and skills on specific capabilities, as required by the UN/AU.	n/a*
OUTPUT 4: The AU Commission (PSOD) has increased knowledge on PSO doctrine, policies, and procedures.	n/a*
OUTPUT 5: The AU Commission is equipped with knowledge and skills which enable more capable PSO administrative functions, including in financial management.	n/a*
OUTPUT 6: AU PSOD and the AU’s Police Strategic Support Group (PSSG) have improved policing capacity and increased knowledge and skills to enable better performance and functionality.	n/a*
Overall Rating of Output Delivery	n/a*

* Commentary regarding activity delivered under each output has been incorporated into this review. However, as the APSO programme did not have a Results Framework with milestones or targets for this period, output-level progress cannot be scored.

Outcome 1 Assessment	Outcome statement: Select African T/PCCs are better able to deploy quality contributions to UN/AU peace operations. There is evidence that key strategic partners continue to engage seriously with BPST(A) and to engage and deploy on UN and AU PSOs of interest to the UK. It is likely that BPST(A) training and capacity development enables improved skills and capacity with select T/PCCs, although determining whether that translates into improved performance is difficult to determine. As the APSO programme did not have a current Results Framework with milestones or targets for this period, progress against this outcome must be assessed as RED, but this rating is not a comment on the quality of BPST’s delivery.
Overall Outcome Progress Rating:		RED
Overall Risk Rating:		Moderate

Outcome 2 Assessment	Outcome statement: The AU is better able to establish, manage, support, oversee, plan and generate forces for PSOs. There is evidence that the AU continues to engage constructively with BPST(A) and that support to policy development and coordination is well received. However, the AU Peace Support Operations Division remains poorly staffed and over committed to operations which hampers more effective delivery. As the APSO programme did not have a current Results Framework, progress against this outcome must be assessed as RED, but this rating is not a comment on the quality of BPST’s delivery
Overall Outcome Progress Rating:		RED
Overall Risk Rating:		Moderate

Summary of Programme Performance
Year	2020/21		2021/22		2022/23
Programme Rating	n/a	n/a	3	3	n/a	RED
Risk Rating	n/a		Amber		Amber

Note: Output / Outcome score

What Support Did the UK Provide in FY 22/23?
Total budget of £5.102m (£1.082m ODA and £4.02m non-ODA). Operating costs of £2.78m.

The APSO programme is delivered primarily by the British Peace Support Team (Africa). In 22/23 BPSTA) was comprised of approximately 16 country based staff,1 MOD civilian, 2 Deployed Civilian experts, and 22 UK Military staff.

Training facilitated by BPST(A) was primarily delivered through the deployment of UK Military Short Term Training teams; external contractors; and deployed civilian experts. Some training and other activity was delivered directly by BPST staff.

Key Results for FY 22/23:
- APSO funding BPST(A) to support delivery of 73 activities, of which 47 (64%) were to the five APSO ‘enduring partnership’ countries, and the AU. This included:
  - 9 human security-themed courses.
  - Development of Ghana’s first Explosive Ordinance Disposal (EOD) Regiment, now part of a new Ghanaian UN PSO pledge.
  - A two-week Gender in Peace Support Operations Course with the Gambia Armed Forces Training School (GAFTS) - the first of its kind at the GAFTS.
  - Pre-Deployment Training (PDT) for the Zambian battalion (ZAMBATT) deploying to the Central African Republic (MINUSCA).
  - PDT to 778 Malawian Defence Force soldiers (MALBATT) deploying to the MONUSCO Force Intervention Brigade.
  - Medical training for 50 female Zambian Defence Force medics and instructors due to deploy to MINUSCA. In collaboration with the US Global Peace Operations Initiative (GPOI), also delivered Female Engagement Team and UN CIMIC training.

Major progress towards establishment of BPST(A) Integrated Human Security Cell, combining policing/gender/IHL expertise and enabling more integrated planning for future activity (since established).

Key Lessons
Sustainability continues to be a challenging goal in the context of a three-year programme seeking to make a difference to missions and T/PCC’s with complex requirements. A gradual adjustment in BPST(A)’s approach to sustainability is evident, though more can be done to define sustainability objectives at boththe project and programme level.

The nature of PSOs in Africa is changing. To maintain relevance and maximise strategic utility, BPST(A) will likely need to increase the civilian component of its operations, particularly on the policing, gender and IHL side.

In the absence of strategic clarity, well-resourced organisations will often continue to deliver in line with perceived intent. BPST(A) has done so. This risks a lack of cohesion in delivery, impacts on overall effectiveness and drives a culture of activity-led policy making.

Tracking improvements in mission performance generated from BPST(A) supported training and capacity development remains hugely complex. A comprehensive ‘solution’ may not be realisable without disproportionate investment.

Key Recommendations for FY 22/23
- Strategy: In line with SRO commentary from last year’s Annual Review, the APSO Board should establish a process to clearly define the purpose and strategic intent of both APSO and BPST(A). This process should include consideration of BPST(A) remit, and high-level objectives related to Defence Engagement (DE), Political Access and Influence (PAI), and sustainability (which, for sustainability, had commenced, but was put on hold following a decision to extend the programme by one year).
- MEL: Following on from the above, the APSO Programme Manager should establish a process – utilising specialist support – to finalise a Theory of Change, and develop a Results Framework and MEL Plan, which should then be discussed and endorsed by the APSO Board. The ToR and RF are mandatory requirements for all CSSF-funded programmes, used to set direction, enable prioritisation and drive programme accountability, transparency and value-for-money.
- Exit: The APSO programme manager should develop an APSO exit plan (endorsed by the Board), determining the logic, process, timing and alternative funding models which would allow BPST(A) to continue, if desired by HMG, without CSSF funding.
- Management: MOD, in consultation with the FCDO and the APSO Board, should fulfil the February 2022 2* directive to employ a civilian Deputy Head of BPST(A).