Annual Review/Programme Completion Review (22/23)

A. Summary Sheet
NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	CSSF Lake Chad Basin Programme
Programme ID	C-AFR-0011
Country and Region	Nigeria, West Africa
IATI Unique ID
HMG Partners / (Lead in bold)	Ministry of Defence
Total Budget	ODA: £23.7m	Non-ODA: £24.9m
Budget this FY	ODA: £7,144,000	Non-ODA: £8,184,000
Spend this FY	ODA: £8,166,947	Non-ODA: £8,317,393
Time Frame	Start Date: 01 April 2022	End Date: 31 March 2023

Outputs	Individual Output Rating
Output 1 (Political engagement) Enhanced capacity and political will of regional governments to develop inclusive roadmap for peace.	3
Output 2 (Defence cooperation), (2.1) Improved conduct and performance of regional military forces; and (2.2) Improved Nigerian military and MNJTF operational and strategic capability.	2
Output 3 (4DR) Former low risk VEO cadres deradicalized and reintegrated.	4
Output 4 (Civ-mil coordination and accountability) Improved civ-mil coordination and human rights compliance of security forces.	3
Output 5 (Area-based stabilisation) Area-based stabilisation improves security, services and livelihood options for all civilians.	2/3
Output 6 (Sub-national governance) Improved capability of State Governors to deliver benefits for at-risk communities.	3

Overall Rating of Output Delivery	3

Outcome Assessment	The programme is on track to achieve its objectives. The LCB programme is operating in a challenging environment, on issues which are critical to the peace, development and stability of the region. That it continues to deliver in this context is a testament to the strength of the design and the capacity of the implementing partners to adapt and operate in fragile and conflict affected settings. Outcome 2, was impacted following an internal process, and the security and defence component continues to be undergoing structural reforms. This is reflected in the programme’s ability to achieve outcomes in the security sector. It remains, however, particularly relevant to the overall programme logic and should be better able to deliver in FY 23/24 and beyond, if the proposed changes are effectively implemented and the management structure better integrated.
Overall Outcome Progress Rating:		Green/Amber
Overall Risk Rating:		High

Summary of Programme Performance
Year	2020/21		2021/22		2022/23
Programme Rating	3	Amber	3	Amber	3	Amber
Risk Rating	High		High		High

Note: Output / Outcome score

What Support Did the UK Provide in FY 22/23?
- Continued to deliver against BHC Abuja’s theory of change for the Lake Chad Basin
- Received and responded to regular requests for advice and support from key stakeholders on pursuing a comprehensive political strategy.
- Completed support for the pilot on IDP resettlement ‘Durable Solutions’, implemented by IOM.
- Facilitated regular meetings between State and Federal actors and strengthened political consensus around a dialogue-centred strategy for an effective DDR process, the wider government political strategy, and transitional justice.
- Facilitated the recruitment and onboarding of a Head of the DSU, as well as Sector Experts, Data Analysts, and Drivers.
- In Cameroon, a Joint Operations Centre (JOC) was 95% built and kitted out, and phase one of JOC (DGRE and BIR) was delivered in Q4.
- Delivered training on transitional justice to 80 participants.

Key Results for FY 22/23:
- Brigade Strike Force training system (Project STINGER) was successfully handed over to UK-trained Nigerian Instructors (output 2)
- 602 clients graduated from Operation Safe Corridor, the first cohort to have benefitted from the significant improvements that have been made to the camp due to CSSF funding.
- IDPs, returned IDPs and vulnerable host community members have access to integrated services and sustainable livelihoods in the areas of return, local integration or resettlement.
- In Q1, the Borno State Government officially handed over the rebuilt Ngarannam community to the people of Ngarannam. This launch featured the completed 360 homes, with 140 more planned, a school, a marketplace with 16 lockup shops, housing for teachers and security forces, a police station, and a healthcare facility to serve 3,000 people.
- Government leadership and capacity to facilitate principled Durable Solutions processes at federal, state and local levels, and social cohesion (individual and community resilience), have been strengthened.
- Women leaders were integrated into key political discussions on political settlement, transitional justice and DDR approaches.
- 4,205 people benefitted from cash for work as income generating opportunities in JAP locations. 49,179 people benefitted from provided productive or business grants or assets.
- The inclusion of 147 female representatives, including female presidents, within Community Stabilisation Committees or similar structures across all 4 LCB countries windows [Nigeria (42) Niger (24) Cameroon (34) Chad (47)].

Key Lessons
On programme management:
- A system is needed to track the expiry of MoUs and agreements and to prompt replacements as needed. In one instance, the expiry of an MoU resulted in issues, and due to staffing changes the programme team was unsure of how long ago it had expired.
- Within fluid allocations scenarios, implementation partners could be proactively informed of expected budget reductions (as appropriate) to manage expectations.

On programme design and monitoring
- The CSSF LCB Programme results framework needs to include greater scope to measure GESI impact, including by working with the MEL team to generate more outcome level indicators.
- The programme takes an approach that strongly aligns with the principles and objectives of the funding mechanisms (CSSF).
- Overall, MEL approaches are heavily weighted towards output driven, quantitative indicators, and would benefit improved qualitative indicators that more accurately reflect the nuances and value of LCB activity and its genuine impact against desired outcomes.
- In certain areas, work is required by BHC to set the conditions that will allow for more valuable MEL data to be captured and assessed, and to bring down walls where there is reticence amongst recipients/partners to engaging in this process. Requirements for impact measurement should be negotiated as part of the UK assistance: for instance, BHC Abuja should continue to press UNDP for more thorough reporting on activities and impact. Op TURUS should also continue to engage with security and defence counterparts to stress the importance of measurement of indicators to monitor progress in our support activities.
- The defence components should continue to be better aligned with the overall management of the programme, following the conclusions of the independent study submitted the previous financial year. Steps have been taken to implement the recommendations of this study.

On activities and implementation
During Q2, the programme team identified that further consultation within the RSF was required on what agricultural inputs are necessary before procurement and delivery of these resources. Equally, further work was required on livelihoods support for women to ensure that livelihoods available are appropriate and can meet basic needs.

Key Recommendations for FY 22/23
- Reform of Defence delivery models (e.g. TURUS / BDS(WA) transition) should be closely monitored to manage the risks of any short-term drop in bandwidth and momentum, appreciating that this change will provide longer-term dividends that should address many of the issues identified in this report.
- As was noted in the previous Annual Review, the programme should reinforce its focus on human security and gender. This is particularly relevant to the lines of efforts pursued under outcome 2, but should also be reflected in the Results Framework throughout, to better capture the GESI elements of the programme and ensure they remain front and centre.
- The programme should enrol the support of a MEL adviser to ensure the Results framework reflects the qualitative elements of the work, which is overly focussed on quantitative elements at the moment.
- The programme should seek a more explicit link to the efforts of HMG under departmental baselines (in particular Nigeria, but also in other countries covered by the programme), enabling departmental spend or identifying synergies between projects: the annual review noted that this connection did exist, but it was not documented or brought forward explicitly.