Annual Review/Programme Completion Review (22/23)

A. Summary Sheet
NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	CSSF Sahel Security & Stabilisation Programme
Programme ID	C-AFR-0023
Country and Region	Mali, Niger, Burkina Faso, Mauritania
IATI Unique ID	CSSF-03-000024
HMG Partners / (Lead in bold)	FCDO, NCA
Total Budget	ODA:	Non-ODA:
Budget this FY	ODA: £5,617,000	Non-ODA: £1,351,240
Spend this FY	ODA: £5,670,707.	Non-ODA: £1,278,492
Time Frame	Start Date:04/2021	End Date:03/2024

Outputs	Individual Output Rating
STABILISATION: Increased capacity of local communities and relevant authorities in the Liptako Gourma region to identify and address sources of insecurity.	3
PROTECTION OF CIVILIANS: Enhanced capability and knowledge of security sector and humanitarian actors and local communities in tackling human security issues including human rights violations, serious organised crime and limited access to fragile areas.	3
OPEN SOCIETIES - Increased capacity of target civil society and media organisations to promote accountable and inclusive governance.	4
WOMEN PEACE AND SECURITY: Strengthened capacity of women's rights organisations to support communities to respond to GBV, promote women’s economic empowerment and engagement in relevant governance processes.	4
Overall Rating of Output Delivery	3

Outcome Assessment	Overall, delivery against the 2022/2023 outcomes was good in most areas. There were some clear and commendable successes – and some areas for improvement. / The programme’s restructuring over the 2022-23 reporting period has been positive. This was carried out partly in line with recommendations from the 2021-22 Annual Review, partly in response to external developments on the ground. The programme was simplified (from three outcomes to two) and the number of implementing partners was reduced (from 18 in 2021-22 to 12 in 2022-23). The thinking put into refining and narrowing the programme’s scope and ambition has enabled it to focus its delivery in a smaller number of areas. Difficult choices have been made and the programme is, as a whole, stronger for this. / The programme now feels broadly cohesive and integrated, pragmatically configured to deliver on the programme outcomes. Key delivery areas have been grouped (Women Peace and Security, for example). There is strong evidence of collaboration between implementing partners across different Outputs. There is also a compelling logic that runs through and underpins the programme design (evidenced in the revised Theory of Change). / While, programme outcomes have been reframed and delivery against these is more realistic, the programme remains highly ambitious. We were not convinced that the Stabilisation activity delivers strategic impact, value for money or sustainability. But we also feel that any future CSSF / ISF programme in the Sahel should retain a Stabilisation component in order to deliver against UK strategic priorities. Some thought is needed on how to reconcile these two points; there are unlikely to be easy answers and we would recommend further consultation with Stabilisation Advisers on the shape and focus of any post-2024 Stabilisation effort. / Political and security developments have forced the programme to flex. It would be an understatement to refer to the Sahel Security and Stabilisation Programme as high risk. The magnitude of the changes that have unravelled the political and security foundations on which the programme was built should be a central consideration in any appraisal of its performance. In the face of these changes the programme has adapted, spreading the risk geographically (outside Mali) but also across different delivery partners (e.g. by deepening partnerships with local Malian civil society organisations). Yet we felt that a more sturdy approach to risk management was required and that more active consideration should be given to both exit strategies and also sustainability.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		High

Summary of Programme Performance
Year	2020/21		2021/22		2022/23
Programme Rating			3	Amber	3	Amber
Risk Rating			High		High

Note: Output / Outcome score

What Support Did the UK Provide in FY 22/23?
In FY 22/23 the CSSF Sahel programme operated across 4 outputs and undertook various interventions across each:

Output 1: Stabilisation
- Gao Stabilisation Fund / ASI: The GSF is a CSSF initiative that sits at the centre of UK stabilisation efforts for MINUSMA Sector East in and around the Gao and Ménaka region. It has driven four projects over the reporting period:
  - Strategic Dialogue – supporting communal meetings and training in disinformation.
  - Community resilience – supporting more inclusive communal meetings.
  - Youth employment – identifying and creating employment for youth vulnerable to armed group recruitment.
  - Women, peace and security - supporting women farmers through supply of agricultural equipment and seeds.
- MINUSMA Trust Fund third party monitoring (Tetra-Tech): Providing expertise and knowledge to continue Third Party Monitoring solution for the Trust Fund.
- Position, Refine and Operate for Peace in Central Mali (Mercy Corps): to prevent the further spread of inter-ethnic violence in buffer zone areas of central Mali
- Support to the Government of Niger’s stabilisation Agency (HACP): targets communities at risk of radicalisation or instability, particularly along the border with Mali, for community-driven and locally-led stabilisation support.

Output 2: Protection of Civilians
- DCAF: promoting accountability of the security sector in Mali and Niger, by delivering training on human rights and gender sensitivity.
- NRC: safeguarding humanitarian access in Mali, Niger and Burkina Faso by improving humanitarian access with local authorities and increasing trust among communities and NSAGs.
- UNODC: project for Supporting gender-sensitive defence and security forces (DSF) to engage, build trust, and protect populations in cross-border and hard-to-reach areas in Mali, Mauritania and Niger is enhance the capacity of the Malian and Nigerien Gendarmerie as well as of the Mauritanian National Guard to conduct gender-sensitive counter-terrorism and transnational organized crime (CT/TOC) operations to protect civilians in cross-border and hard to reach areas.
- National Crime Agency: supporting and monitoring a Malian law enforcement unit to increase the quantity and quality of counter-trafficking operations.

Output 3: Open / Resilient Societies
- Fondation Hirondelle: Supporting local media organisations in Mali, Niger and Burkina Faso by improving access to quality information and content, especially women and marginalized groups (minors, rural populations, unemployed youth, displaced persons).
- DCAF: training civil society organisations in Mali to recognise, monitor and report on human rights violations.

Output 4: Women, Peace and Security
- Project to support the strengthening of stability in the Gao region through the promotion of female and youth leadership: “Projet Algafiat” (FEDE): Contribute to the strengthening of social ecology in the Gao region, for the active and equitable participation of women and youth in peace and reconciliation processes
- The peacemakers: no to gender-based violence (WILDAF): empowering women through creating GBV peer-support circles within WILDAF watch committees and strengthening the capacity of women and girls as peacemakers in order to prevent violence at the community level.

Key Results for FY 22/23:
- Gao Stability Fund – four projects operating in the Gao region through the GSF endured beyond the withdrawal of the UK’s LRRG contingent in MINUSMA (which the GSF was designed and established to compliment). Though delivery has been mixed, the GSF has registered impact on the Strategic Dialogue counter-disinformation project and had some localised impact in its Community Resilience efforts. The GSF team also includes research capacity to conduct regular conflict analysis to support conflict sensitivity of activities and undertake bespoke research.
- Continued development of impactful interventions on WPS – this included funding two Malian CSOs’ (FEDE and WILDAF) work on women’s’ economic empowerment, women’s’ participation in local peace discussions and managing the effects of GBV in the Gao region. This is innovative, high-impact work in a very challenging context.
- Media and counter-disinformation training – work through Fondation Hirondelle to train local language media organisations (radio and television stations) in Mali, Niger and Burkina Faso, and increase programming and audience numbers. Important and impactful work to challenge disinformation across the region.
- Disruption of narcotics and human trafficking networks, and victim protection – NCA-led counter serious organised crime activity has continued to deliver at a high level over the reporting period. Relations with NCA’s supported unit have remained strong despite wider deterioration in Western relations with the Malian authorities. This has had wider benefits.
- Wider Sahel Delivery – given the changes in the political context, the programme sought to extend its activities outside Mali. This has included support to civil society in Niger and Burkina Faso, and human rights and gender sensitivity training to security forces in Mauritania.

Key Lessons
We were struck by the apparent incompatibility between CSSF programming (that commonly looks over short time horizons) with stabilisation activity that typically requires a much longer horizon to deliver real effect. It felt sometimes like projects were ‘chasing impact’ rather than stepping back and looking at the issue strategically, and evaluating whether resource was being put in the right areas. This felt particularly the case for some of the stabilisation work. This issue is probably most acute in the project design phase and better support from JFU on navigating between ambition and delivery would be valuable.

Key Recommendations for FY 23/24
1. Reshaping stabilisation: Stabilisation work delivered by ASI was weakest. We feel it is important that the programme retain a stabilisation component both in FY 23/24 and in whatever succeeds this programme in the Sahel. Even if the focus of delivery shifts towards other, more promising areas like WPS or Open Societies, Stabilisation will likely remain the enduring UK strategic priority in the Sahel. The programme team will have a better feel for what is and is not possible, but we recommend that the team reviews the programme document and redrafts the theory of change. In broad terms, this should ensure that:
    1. stabilisation activity that has delivered the most impact is extended to close 2024;
    2. activity that is underperforming or unlikely to be viable for security or other reasons is wound up;
    3. the indirect stabilisation benefits that other IP activity delivers are made explicit in the programme document under WPS, PoC and Open Societies.
Finally, though not an actionable recommendation for FY 23/24, we feel that if the programme elects to deliver any future stabilisation activity through a commercially-tendered provider like ASI, then we would encourage a tighter set of reporting requirements and an active approach to monitoring Value for Money (e.g. through a tracker, scorecard or log).
1. Sustainability: given the acute political and security challenges the programme has faced, and will continue to face, this should be a central concern for the team’s activity over the final year. The shift towards local CSOs we see as a sound strategy (FEDE and WILDAF, particularly; also some of Fondation Hirondelle’s local media partners). We felt these would be more resilient to the political shifts washing over the region than the larger international IPs. There may be similar steps that could be taken; the programme team are best placed to identify these. We recommend that the programme team: 1) fully spell out project sustainability in proposals and the redrafted programme document; 2) review sustainability at quarterly meetings to ensure it is taking the all possible steps to safeguard the programme’s gains to date.
2. MEAL: we felt that the results framework did not always accurately capture impact of some of the work being done by partners. We recommend the results framework is redrafted to: 1) tighten the language for the milestones / performance indicators; 2) ensure that these appropriately capture project impact, particularly of the less tangible work (for example, capacity development). We also recommend quarterly challenge meetings should be brought back in to ensure that the outcomes and output indicators remain relevant.
3. Risk: given the increasing instability in the region we felt that a more sturdy risk approach could be integrated to ensure HMG’s funding is being used in a conflict-sensitive manner which does not harm beneficiaries or implementing partner staff. We felt there was further monitoring should be built into the programme for the outputs most at risk. There are two actionable aspects here:
    1. Tighter procedures on monitoring and reporting risk. This could include an updated risk register, which captures individual projects, and more regular updates to the board (either on a quarterly basis or more regularly). Risks should be escalated as and when they materialise.
    2. Enhanced planning against risks. As security and political risks grow, there should to be active planning of exit strategies for most exposed projects, with clear trigger and decision points informing these knowing when risks exceed a tolerable level. This is particularly the case for work centred on the tri-border region which, most commentators agree, is likely to become less accessible with MINUSMA’s withdrawal.