 Annual Review/Programme Completion Review (22/23)

NB: Summary Sheets Will Be Published on GOV.UK
Programme Title	CSSF Somalia Programme
Programme ID
Country and Region	Somalia
IATI Unique ID
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO), Ministry of Defence (MoD)
Total Budget	ODA: £9,336,000	Non-ODA: £15,561,000
Budget this FY	ODA: £9,336,000	Non-ODA: £15,561,000
Spend this FY	ODA: £9,548,812	Non-ODA: £14,928,765
Time Frame	Start Date: 1 April 2022	End Date: 31 March 2023

Outputs			Scale of Delivery
1. The SNA and newly identified units of the Darwish in South West State and on the Mogadishu- Baidoa MSR demonstrate improved operational capability and new approaches to address community protection are tested.			3
2. Civilian oversight structures in Federal Government of Somalia (FGS) and Federal Member State (FMS) Institutions are strengthened and demonstrate improved capacity and capability to plan for and deliver security transition.			3
3. Transition operations in targeted locations are increasingly well-coordinated between AMISOM and Somali security architecture.			2
4. FGS and select FMSs have improved capability to plan, coordinate and implement stabilisation efforts in a gender and conflict sensitive way, with the engagement of local communities.			3
5. Inclusive community and civil society-led stabilisation and security activities build social cohesion in select districts and provide greater understanding on how to engage women in these processes.			3
7. FGS have the capacity to deliver activities that support inclusive alternatives (including women and girls) for low level defection and mechanisms to support high level defection are identified.			2
Overall Scale of Output Delivery			3
Outcome Assessment However, judged against the Results Framework, outcomes were mostly not on course to be fully met by the end of the programme, but they arguably implied a type and scale of change that CSSF programme inputs could realistically produce.	Progress in FY22/23 varied. The review year saw Somali elections taking place, ending an extended period of political uncertainty and bringing in a new President and Government who adopted a more robust approach to al Shabaab. This more conducive context underlined the importance of the programme as a whole and the relevance and value of most individual elements. In some areas there was high quality work and good adaptation to take new opportunities. It was clear that much activity was highly valued by Somali stakeholders (and had a high reputation with partners). The programme also produced significant positive secondary effects for HMG in Somalia and internationally, including in the UN Security Council (UNSC). / UK civilian and military advisors influenced the reshaping and empowering the Office for National Security, to improve coordination between agencies and shape some key policy approaches eg towards the African Union Transition Mission in Somalia (ATMIS) transition. Assessing the impact of these roles remains challenging but there was good anecdotal evidence of incremental higher-level change, although this was not transformational or guaranteed to be fully sustainable. / Stabilisation/Early Recovery Initiative (ERI) came into its own. ERI undertook more genuinely early interventions in areas FGS and local clan forces had liberated. In so doing they demonstrated the value of a hyper-local approach. ERI took more opportunities to promote a structured approach to early stabilisation and had a catalytic effect in influencing other partners as stabilisation rose up the policy agenda. Pilot Gender Equality and Social Inclusion (GESI) activity to improve women’s representation in local decision-making made a modest contribution but will require significant progress to have an impact on higher level change. / The programme completed its commitment to train infantry units in South West State (SWS) and transitioned to a new training model that promised more operational value-added. Op Tangham’s advisory contributions showed good returns although their effect was not all easily captured in existing criteria. / Counter al Shabaab (CaS) work did not deliver significant practical returns. Some new work did not materialise and there was limited effect Low Level Defections, although progress on transitioning to a new approach. Starting other new CaS work was an important step forward with real potential and demonstrated the high level of trust with the new FGS. But this was still in the inception phase at year end. / However, judged against the Results Framework, some outcomes were not on course to be fully met by the end of the programme – with one year to go. The outcomes arguably implied a type and scale of change that CSSF programme inputs could not realistically produce. The challenges for the future will include ensuring resources are sharply focused on areas of greatest added value suitable for the CSSF and less reliant on the local context.
Overall Outcome Progress Rating:		AMBER
Overall Risk Rating:		HIGH

Summary of Programme Performance / The programme began in FY21/22.
Year		2020/21a		2021/22		2022/23
Programme Rating					3	AMBER
Risk Rating				High		High
Programme changes during this period		The main building blocks of the programme remained the same but there was change at project and activity level. The Op Tangham training model changed; a new High Level Defectors project began and the current model of support on Low Level Defections ended.
Note: a scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 22/23?
CSSF Programme		Allocation (£m)
		Non-ODA	ODA	Total
Security Governance, Early Recovery, Transition	Security Governance (MOD)	14,891,000	-	14,891,000
	Security Governance	-	2,054,000	2,054,000
	Early Recovery, Transition	-	2,992,000	2,992,000
	Women, Peace & Security	-	1,300,000	1,300,000
Counter al-Shabaab	Counter al-Shabaab	350,000	2,771,000	3,121,000
Staffing		320,000	219,000	539,000
Total		15,561,000	9,336,000	24,897,000

Key Results for FY 22/23:
- Early Recovery stabilisation work responded well to the new political and security context and delivered more interventions and had more influence on local and international partners approaches.
- OpTangham completed its commitment to infantry training in South West State (SWS) and transitioned to a new training model; its advisors continued to play an effective role in shaping and coordinating Somali and international security responses.
- UK civilian advisors shaped changes in the Somali security architecture and policy agendas.

Key Lessons
- Not a new lesson but a further reinforcement of the crucial importance of the Somalia political context in determining the scale and speed of delivery and results and the need to respond agilely – leaning in to new opportunities as quickly as possible and ending/reducing activity where potential benefits are less likely.
- The benefits of increased integration and interaction between mature activities in different programme strands – eg military and ERI; civilian and military advisory work – and the important role played in this by internal communication and relationships. More broadly a recognition that the programme generates a wide range of information and insights that should be captured and harnessed in a more structured way.
- In this context of integrated delivery across programme streams, regularly reviewing programme tools to ensure outputs and indicators sufficiently capture multiple contributions.
- Recognition that the programme’s mostly top down, FGS and Institutional focus, while essential, will only go so far in the Somalia context and that despite the major political, security and practical challenges, more focus will need to be paid in future on how to have effect at the Federal Member State level to underpin sustainable change.
- While drawing on the benefits of highly integrated working, ensuring the programme/team has the space to operate to ensure delivery meets CSSF principles.

Key Recommendations for FY 22/23
Review staffing structures to ensure the CSSF lead and team have clear lines of accountability and operational autonomy to better demonstrate the Fund’s operating principles.

Narrow the breadth of the future programme and better define results. Quickly stand up a programme Board or working group to take operational level decisions and provide a formal link to the Senior Responsible Owner (SRO).

Transition to a new UK military support implementation model which has more local ownership, scope for agility and lower fixed and administrative costs and increase alignment with other relevant UK resource.

Reassess with Counter Terrorism Network (CTEN) the fit of CT work within the programme and the most efficient oversight, staffing and delivery model, and end support to Low Level Defection work.

Ensure team staffing capacity and capability is right for the new programme, including through a senior lead with space for strategic engagement, an empowered ‘executive’ role to ensure smooth operational running and dedicated conflict advisory resource.