Annual Review/Programme Completion Review (22/23)

A. Summary Sheet
NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Combatting Illicit Economies Programme (CIEP)
Programme ID	C-AMS-0003
Country and Region	Latin America: Colombia, Peru, Panama, Ecuador, Brazil and Venezuela
IATI Unique ID	CSSF-04-000004
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO)
Total Budget	ODA:	Non-ODA:
Budget this FY	ODA:	Non-ODA:
Spend this FY	ODA:	Non-ODA:
Time Frame	Start Date: April 2020	End Date: March 2025

Outputs* / *Due to the cumulative total number of outcomes and outputs that the programme has generated as well as the scope of the AR across 3 countries, the Review Team only validated results at outcome level. In doing so however, the Team is confident that the outputs claimed are valid and substantiated.	Individual Output Rating
# of outputs harvested showing increased civil society capacity to demand and influence State action on illicit economies	4
# of outputs harvested showing increased domestic collaboration and adoption of more effective practices based upon evidence across institutions engaged in tackling illicit economies	4
# of outputs harvested showing increased regional / international collaboration and adoption of more effective practices based upon evidence across institutions engaged in tackling illicit economies	3
Overall Rating of Output Delivery	4

Outcome Assessment	The CIEP delivered 17 outcomes out of 19, which is a significant result, particularly given some of the challenges with evidencing outcomes relating to illicit finance investigations due to their highly confidential nature. / At its mid-point, the programme is on track against, or exceeding, its outcome targets in two areas. There as a downtick this year in delivery against outcome 1.3 which relates to supporting regional cooperation. This is understandable given that this outcome is considerably more challenging that the other two and further consideration should be given to whether ambition is set correctly across all outcomes. / The programme is also delivering a range of additional benefits via a regional approach across six countries in a region that impacts UK security interests. In the year for this review it piloted innovative environmental crime programming, filling a gap in regional programming in this area.
Overall Outcome Progress Rating:		4
Overall Risk Rating:		Medium

Summary of Programme Performance
Year	2020/21		2021/22		2022/23
Programme Rating	2	Amber	4	Amber / Green	4	Green
Risk Rating	Medium		Medium		Medium
Note: Output / Outcome score

What Support Did the UK Provide in FY 22/23?
The Combatting Illicit Economies Programme (CIEP) seeks to tackle global illicit financial flows (IFFs) and money laundering dynamics, as they impact Latin America and generate instability, organized crime and corruption risks that threaten UK interests. The programme works regionally but with a particular focus on Colombia, Peru, Panama, Venezuela, Brazil and Ecuador. The programme engages in a mixed delivery model, which encompasses work with Non-Governmental Organisations (NGOs), multilateral organisations, commercial implementers and through deployed HMG advisors working with regional counterparts to build institutional capacity.

In financial year 22/23, the programme engaged in the following activity:

- Support to regional investigative journalism.
- Tackling the role of corporate structures in sustaining organized crime dynamics.
- Promoting design of improved criminal justice policies against organised and financial crime and
     corruption.
- Tackling anti-corruption dynamics sustaining drug trafficking.
- Strengthening civil society capacity to tackle corruption, illicit economies and serious organized
crime.
- Enhancing capacity to reduce environmental crime in the Amazon.
- Enhancing capacity to interrogate and share digital evidence in complex cases.
- Developing capacity to tackle trade-based money laundering.
- Technical support to develop IFFs analytical capacity and allied processes.
- Strengthening beneficial ownership systems and capacities.
- Capacity building support to regulatory authorities across the region in tackling IFFs.

Key Results for FY 22/23:
The 2022/23 CIEP outcome measures the effect the programme has had on improving organisational effectiveness to identify, tackle and suppress illicit economies generated by Latin America. At an aggregate level the programme has demonstrated strong results against the outcome measurements across six countries.  The overall outcome is broken down into three key indicators which assess results using CIEP’s outcome harvesting methodology as follows:

Outcome indicator 1: outcomes harvested showing improved, evidence-based processes being adopted by organizations engaged in tackling illicit economies regionally. Against an envisioned target of 7 results, the CIEP is assessed as achieving 11 outcomes in 22/23.

Outcome indicator 2: outcomes harvested showing improved, evidence-based domestic coordination between organizations engaged in tackling illicit economies regionally. Against an envisioned target of 7 results, the CIEP is assessed as achieving 5 outcomes in 22/23.

Outcome indicator 3: outcomes harvested showing improved, evidence based cross-border coordination between organizations engaged in tackling illicit economies regionally, and improved compliance with international standards. Against an envisioned target of 5 results, the CIEP is assessed as achieving 1 outcome in 22/23.

Key Lessons
- The CIEP is delivering significant results and has developed a robust and impressive outcome harvesting methodology to capture the same. Nevertheless, focusing on outcome harvesting has meant that in some instances either the results are not fully captured, or it is difficult to appreciate the full extent of how the programme is supporting the relevant HMG strategies (though based on meetings with implementers and stakeholders, the Review Team has no doubt that CIEP is delivering towards them). This means that successes and value for money are more difficult to understand and assess.
- The work of the embedded FCDO technical advisors is a good model to use to influence systemic change but it is challenging to capture the full range of activity and benefits of the model without also specifically measuring political access and influencing.
- A regional programme across six countries with different delivery models and complex thematics requires significant amounts of programme management, in terms of expertise and resource. This is not only important from the perspective of ensuring that projects run smoothly but is also important from a risk management perspective and to ensure that HOMs are updated on progress. This also has cost implications.
- ODA cuts/reprogramming and financial system changes place significant burden on the programming team.
- Successful programme interventions can have significant positive impacts for the wider bilateral relationship and the positive examples from CIEP, in particular from Panama and Ecuador, could serve as useful learning tools for the wider FCDO working on illicit finance and more broadly on SOC.

Key Recommendations for FY 22/23
It is recommended that the MEL system be further upgraded to enable the CIEP team to fully show success and have an easier way of tracking progress, including through the addition of fully worked up change stories rather than only outcome statements. This will also enable a better value for money assessment of the advisors and facilitate the case to be made for future funding of such a model. As part of this review CIEP should also review under/over achievability of
its outcome targets.
- Linked to the above recommendation, the Review Team recommend the programme starts to plan for building a rigorous external evaluation (ideally using experimental or quasi-experimental methods to test causality alongside process evaluation questions to build evidence on how and why outcomes have been achieved) into the next phase of the programme. Starting with a baseline assessment, this evaluation would help any future iteration of CIEP to more rigorously learn from successes, build evidence for wider HMG on how and why change happens on illicit finance, and understand where improvements can be made. The JFU will need to support the Programme to enable this to happen.
- JFU MEL advisory support and wider Global SOC Portfolio should engage with CIEP team to design collective Impact Indicators across the CIEP/SOC programming in region, alongside support from the JFU economist to improve VFM indicators.
- Also, linked to the above recommendations, it is worth capturing the work and achievements of the advisors in a more systematic way to learn lessons from this delivery model (which is different to the embedded advisor model used in other parts of HMG), and to show full value of the work of the advisors as part of the wider updates to the MEL system.
- It is recommended that the Review Teamwork with policy leads in the IFAC team, SOCnet, IF leads and wider SOC teams to feed lessons into the wider IF/SOC system that the policy leads can then feed into wider strategic approaches. It is recommended the JFU helps feed lessons into wider CSSF programming on SOC and illicit finance.
- The CIEP has a significant compendium of lessons that should be captured that can be shared with the wider network to support role out of similar activity as delivered in this programme – it would be useful to seek an external evaluation team to undertake research deep dives into high achieving outcomes in order to build evidence on the factors and conditions that support success e.g. SSNF functional review and how that informed organisational reform and behaviour change within industry.
- Succession planning for the technical advisors is challenging given the reliance on Spanish speaking technical advisors, this is further complicated by FCDO recruitment timelines and therefore needs to be planned carefully. JFU might want to assess whether the recruitment challenges faced by CIEP are similar across other CSSF programmes on the FCDO baseline and whether there is anything further that can be done to support recruitment for programmes on the FCDO baseline that facilitates the kind of agile programming that CSSF aims to deliver.
- A recommendation from the last AR was that the CIEP explore potential funding options from within the transnational threat portfolios given overlap with the work of this programme. It is recommended that this should still be explored in the remaining 18 months for this programme and may free up funding to cover other catalytic activity.