Annual Review Summary (2022 - 2023)

A. Summary Sheet
NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Enablers Incubator Strategic Drivers (EISD) Programme
Programme ID	C-CTP-0005
Country and Region	Multi-Region
IATI Unique ID	CSSF-01-000014
HMG Partners / (Lead in bold)	CONTEST Unit (CU) - inc. Overseas and Risk and Performance teams; CTEN, including Officers and Hub Heads; Joint Intelligence Operations, Joint Terrorism Analysis Centre, Defence Intelligence, Defence Sciences and Technology Laboratory, National Security Research Group (NSRG), Extremism Analysis Unit (EAU) Foreign Commonwealth and Development Office (FCDO), Home Office (HO).
Time Frame	Start Date: 1 April 2022	End Date: 31 March 2023
Outputs			Individual Output Rating
A1 (i). Increased engagement between HMG and priority host government Counter Terrorism (CT) contacts in cooperative activity			4
B1 (i). Improvements to HMG data sets made in key areas of UK exposure and partner capability			4
B2 (i). Programme level Results Frameworks utilised effectively by programme staff			3
B2 (ii). Staff capacity increased to use MEL tools, incorporate best practice approaches to Gender, Human Rights and Conflict Sensitivity and to improve programming on the basis of lessons learned			4
C1 (i). Research, pilot project design and engagement that informs / enables HMG CT activity			3
Overall Rating of Output Delivery			4

Outcome Assessment	The Enabler’s Programme continues to take steps to improve. The Theory of Change provides greater clarity and better aligns to the Results Framework and is a highly effective tool for building access and influence and informing future programming.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Medium

Summary of Programme Performance
Year	2020/21		2021/22		2022/23
Programme Rating	3 (Ba)	Amber (Ba)	4	Green	4	Green
Risk Rating	Medium		Medium		Medium

Note: Output / Outcome score

What Support Did the UK Provide in FY 22/23?
In 2022/23 the Enablers programme supported a wide range of activity, across all four Pillars (4 Ps) of the Contest Strategy aimed at maintaining and expanding human-rights compliant political access, engagement and influence (PAI) amongst host nations, multilaterals and counter terrorism (CT) partners (Enabler A); helping the HMG CT community better understand the risk posed by current and future international terrorism, the most effective tools and critically, the impact of HMG actions on risks (Enabler B); and ensuring that HMG’s systems support the international CT effort (Enabler C).
Enablers projects maintained or strengthened political access and influence in 17 countries across 5 regions, greater understanding led to future programming in 8 countries and 239 CTPF project officers received training.

Key Results for FY 22/23:
- Strengthened CT relationships with hard-to-reach CT partners. Opened the door for enhanced cooperation.
- Improved HMG's understanding of deficiencies in the Financial Action Task Force (FATF) methodologies
- Maintaining critical CT partnerships and building access and influence
- Strengthening Host Partners juvenile CT criminal justice system
- Supported a biometric exchange workshop that provided actionable insights on potential future data exchange and data management safeguards
- Funding the Design of CT Financing Strategies
- Theory of Change and Results Framework was simplified & strengthened.
- 239 project officers received CT Programme Fund (CTPF) Programme training.

Key Lessons
- Research and lessons aren’t benefiting other programmes outside of the country of focus. A learning repository would help build synergies across programmes and regions.
- Building access and influence takes time but can pay dividends. CTPf could benefit from multi-year programming and taking a long-term approach to PAI, paving the way for delivery of projects across all 4 Ps.
- There needs to be a more strategic approach. Currently the programme is demand led with good project proposals being approved.
- Though the ToC and RFW have been reviewed there is limited linkages between outputs and outcomes to show how better understanding leads to better programming and a reduction in threat of terrorism to the UK or UK interests overseas.

Key Recommendations for FY 22/23
- The Enablers Fund should act as an incubator for wider CTPf. Plans should be formulated starting with Enablers funded research to inform pilot projects leading to larger programmes where research and evidence from pilots indicates these would be worthwhile.
- Project funding should be allocated on a multi-year basis to maximise the benefits of investing in building political access and influence recognising the time and financial investment required to do this properly and protecting from changing priorities.
- To manage changing priority countries of focus, Enablers Fund should hold a flexible fund.
- Build greater linkages to other funding streams including SOC and development funding particularly sharing lessons from research projects and pilots to inform programming from other funding streams and ensure greater strategic alignment.
- Establish clearer criteria for Enablers projects in order to demonstrate what differentiates an Enablers project from other programme projects.