Annual Review (22/23)

A. Summary Sheet
NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	CSSF Sri Lanka
Programme ID	C-SAA-0010
Country and Region	Sri Lanka, IIOD
IATI Unique ID	CSSF-09-000003
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO) and Ministry of Defence (MOD)
Total Budget	ODA: £10,567,500	Non-ODA: £450,000
Budget this FY	ODA: £3,522,500	Non-ODA: £129,000
Spend this FY	ODA: £3,545,486	Non-ODA: £77,842
Time Frame	Start Date: 1 April 2022	End Date: 31 March 2023

Outputs	Rating
Mine and explosive remnants of war affected land released; Vocational training, education and psychosocial support for demining operatives.	4
Resettled communities are supported, protected and engaged in durable livelihood activities	3
Committees capacitated and mechanisms establish to carry out more effective oversight of public finance and increase engagement with marginalised people (WFD)	3
Civil society capacitated to work safely, remote network established, government policies strengthened to improve civil society management (UNOPS)	3
Military capacitated to promote democratic values, human rights and modern military standards (MoD)	2
Innovative pilots developed to address climate-driven conflict co-designed and implemented based on mapping, results and lessons documented and shared (IMWI, CEPA, Chysalis)	3
Government, civil society and users capacitated to prevent and respond to Cyber Sexual and Gender-Based Violence and trends in CSGBV monitored (SFCG, #Generation)	4
Number of evidence products or analytical pieces developed	3
Overall Rating of Output Delivery	3

Outcome Assessment	The programme is likely to meet its outcome targets, but there is some uncertainty due to the compressed timescale caused by delays during the first year, and the uncertain political and economic context. These factors put the results at moderate risk and will require close monitoring over the remaining 20 months. / The mine clearance project is the best established, having started with a platform already in place – it exceeded its targets for the number of direct beneficiaries, despite having had to pause operations for two months due to lack of fuel for transport. Over 12,000 people will directly benefit from the cleared land, against a target of 11,000. The other projects are not yet mature enough for outcome goals to have been reached. / The delays to the start of project implementation were outside of the programme team’s and the implementing partners’ control: Sri Lanka’s political and financial crisis, a lack of fuel for transport, procurement delays, a global UK pause on ODA spending and internal FCDO problems with the transition to the new finance system. The delays, and some of their underlying causes, put immense pressure on the programme team, both inside and outside work, and their resilience and dedication throughout the period were commendable.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		Medium

Summary of Programme Performance
Year	2020/21		2021/22		2022/23
Programme Rating	3	Amber	3	Amber	3	Amber
Risk Rating	M		M		M

Note: Output / Outcome score

What Support Did the UK Provide in FY 22/23?

Pillar 1: Conflict drivers
- Landmine Clearance. To enable protracted refugees and IDPs to resettle, improve livelihoods and encourage a return to stability in conflict-affected areas. Partners: The HALO Trust and Mines Advisory Group. Budget £2,800,000 ODA.
- Reintegration and sustainable settlement. To support for durable resettlement and reintegration for conflict-displaced refugees and internally displaced people. Partner: United Nations Development Programme (UNDP) and International Organization for Migration (IOM). Budget £1,500,000 ODA
Pillar 2: Reducing democratic fragility
- Parliamentary strengthening. To build institutional trust in parliament by strengthening financial oversight and promoting inclusive processes in areas relevant to the prevailing political and economic crisis. Partner: Westminster Foundation for Democracy (WFD). Budget: £520,000 ODA
- CSO strengthening. To preserve civic spaces by investing in civil society protection, performance, skills development and coping mechanisms, to enable CSO self-reliance and self-care. Partner: United Nations Office for Project Services (UNOPS) and United nations Office on Drugs and Crime (UNODC). Budget: £1,500,000 ODA
- Defence Engagement. Build military capacity to deliver against the role expected of a modern military to keep communication channels open on sensitive topics, including raising human rights issues and concerns where appropriate. Partner: UK Ministry of Defence. Budget: £520,000 non-ODA.
Pillar 3: Reducing future inter-community tensions due to climate change
Climate/conflict. Pilot to improve water resource management while addressing local conflict issues leading to more equitable benefits to community members. Partners: International Water Management Institute (IWMI), Centre for Policy Analysis (CPA) and Chrysalis. £1,183,185 ODA.
Pillar 4: Tackling gender-based violence in society and barriers to women’s inclusion.:
Caught in the Web. To advance effective responses to Gendered Online Hate Speech (GOHS) and Cyber Sexual and Gender Based Violence (CSGBV) in Sri Lanka. Partners: Search for Common Ground (SFCG), Centre For Equality and Justice (CEJ) and Hashtag Generation. £549,334 ODA

Key Results for FY 22/23

The activities which could be delivered during the year were curtailed by external delivery challenges. Despite these, the following results were achieved:
- HALO and MAP cleared over 360,000m2 of land of mines and other explosive remnants of war and another 62,000m2 of suspected contaminated land was found to be safe for release. Over 12,200 people in communities neighbouring the cleared land will benefit directly, and another 36,700 living near the land who will benefit indirectly. Agricultural training of mine clearance workers for post-project employment began, with 309 staff completing an orientation and referral programme.
- UNDP and IOM completed needs assessments and baseline surveys of sites for resettlement and selected local implementing partners.
- WFD provided support to the Committee on Public Finance; Committee on Public Enterprises; and Committee on Public Accounts, including a visit to the parliaments of Holyrood and Westminster. It established the Economic Inclusion Working Group of five MPs, five political party affiliates, seven members of civil society organisations and two media professionals: they were trained in action research methods and concluded eight community research activities with marginalised communities. They also delivered a campaign aiming to increase local election compliance with a new law on campaign financing.
- A CSO project work plan has been agreed with UNOPS. The project builds on the networking ‘platform’ created by UNOPS with previous funding under the brand of Vriddhi.
- Defence engagement saw four senior Sri Lankan Armed Forces officers attending training in the UK. Three courses were delivered in Sri Lanka on maritime explosive ordnance disposal, counter-IED and operational law. A total of 27 officers were engaged by the project.
- IMWI carried out the initial research phase of the project and selected locations for project implementation in the North and North-west of Sri Lanka.
- The SFCG-led consortium established a research service to identify key trends, current topics, and escalations related to GOHS and CSGBV. They formed a National Advisory Committee and developed a training module on CSGBV, GOHS, laws and the response mechanism and advocated for it to be used by stakeholders, including the police, in their own institutional training and learning mechanisms. Capacity building was delivered for members of the Bar association, police, the tech sector, social and mainstream media, civil society members and legislators.

Key Lessons

- Risk management must consider and prepare for scenarios that prevent activities from taking place. Recent years have shown how varied and surprising these can be: a global pandemic, HMT ODA pauses or cuts, lack of fuel, and inability of FCDO accounting systems to transfer funds. The reasons may be hard to predict, but many of the consequences are the same. The programme team was able to continue work in some cases because of the trust it had built with partners.
- The importance of agreeing with partners from the outset to be flexible and adaptive in their approach. In the case of the Westminster Foundation for Democracy, challenges it encountered included the prorogation of Parliament, the changes of the chairs of the parliamentary committees they were working with and the sudden announcement (and later deferment) of local elections. In each case, alternative approaches were identified and implemented, ensuring the project remained on track to meet its goals.
- Efficiencies can be made by ensuring that partners only report the information needed by the programme team. Without clear direction, partners tend to over-report, wasting the project’s resources and making it harder to read and use the reports. By creating a new streamlined reporting template the programme team increased efficiency for the partner and for the programme team.

Key Recommendations for FY 23/24

1. More clearly articulate the contribution the programme makes to achieving political access and influence for the wider mission in support of HMG country business plan goals.
2. Strengthen the monitoring and evaluation system and the evidence base for reporting and learning.
3. Build learning from context, delivery and results monitoring data more systematically into the team calendar.
4. Boost advisory support available to the programme team.
5. Increase assurance of partners’ processes for safeguarding against sexual exploitation and abuse within projects working with vulnerable beneficiaries.
6. Monitor the costs and benefits of working through the UN Peace Window (a multi-partner trust fund) over the coming year to assess its value for money, and then review its use in April 2024.