Annual Review (22/23)

A. Summary Sheet
NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Egypt Programme
Programme ID	C-MNA-0004
Country and Region	Egypt, Middle East and North Africa
IATI Unique ID	CSSF-06-000002
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO)
Total Budget	ODA: £4m	Non-ODA: £0
Budget this FY	ODA: £4m	Non-ODA: £0
Spend this FY	ODA: £0.86m	Non-ODA: £0
Time Frame	Start Date: April 2022	End Date: March 2025

Due to the focus on design rather than delivery during the reporting period, CSSF Egypt and Middle East and North Africa (MENA) Strategic Programmes Team (MSPT) have agreed with Joint Fund Unit (JFU) that the 22/23 Annual Review (AR) will be conducted in a proportionate manner focussing on reviewing the process of the redesign as opposed to delivery.

Summary of Programme Performance
Year	2020/21		2021/22		2022/23
Programme Rating	4	Green	3	Amber	N/A	N/A
Risk Rating	Medium-High		Medium		Medium

Note: N/A due to redesign

What Support Did the UK Provide in FY 22/23?
- By May 2022 all programmes from the previous FY had been closed, except for one contract with United National Development Programme (UNDP). All suggested programmes in the FY22/23 programme document (PD) were new, and although the PD had been approved, there were questions over effectiveness. A gap in Head of Programme from May to August meant no programming agreed in the FY22/23 PD had begun. Given the ODA “pause” in place in August 2022, the UK then made the decision to halt planned programming in FY22/23 to enable a full redesign to ensure a better strategic fit to both policy and changing context.
- The UK continued to give support to the UNDP in FY 22/23, however, considering the redesign and underperformance, the decision was made to cease funding in March 2023.
- The UK commenced support to the United Nations Office in Drugs and Crime (UNODC) towards the end of the FY and deliverables will be evident from FY 23/24

Key Results for FY 22/23:
A full redesign of programming that reflects better policy, context, and deliverability.

Key Recommendations for FY 22/23
- Consider staffing uplift, and specifically increased UKB footprint - due to the sensitive nature of Post and Security Clearence limitations with Country Based Staff.
- Continue with capacity building approach for Implementing Partners.
- Complete a renewed Joint Analysis of Conflict and Stability (JACS)
- Undertake an environmental impact assessment in FY23/24 to ensure that their projects are nature proofed.