Annual Review (22/23)

A. Summary Sheet

Programme Title	Eastern Route (Turkey) Programme
Programme ID	C-MIG-0005
Country and Region	Turkey
IATI Unique ID	CSSF-01-000006
HMG Partners / (Lead in bold)	Foreign, Commonwealth & Development Office Home Office
Total Budget	ODA: £15,029,449	Non-ODA: £132,937
Budget this FY	ODA: £2,150,000.00	Non-ODA: £0
Spend this FY	ODA: £2,623,798.50	Non-ODA: £0
Time Frame	Start Date: 1 April 2017	End Date: 31 March 2023

Outputs – Assessed	Individual Output Rating
Output 1.1 - Ankara Municipality staff acquire knowledge - and develop guidelines - on service provision and employability skills for women and young refugees	3
Output 1.2 - Service providers (Ankara Municipality) assess and assist refugee women, girls and young refugees in a human-rights, conflict sensitive and gender compliant manner	3
Output 1.3 - Presidency of Migration Management (PMM’s) overall capacity and manner of work in the areas of legal migration developing additional policies/strategies, improved data analysis and operational work are further strengthened	3
Output 1.4 - Enhanced capacities to observe and assess the regional and global developments that may have implications over Turkey’s legal migration policies	3
Output 2.3 - Women from refugee and vulnerable host communities in Kayseri have improved social cohesion through access to labour market and increased awareness on sexual and gender-based violence	3
Output 2.4 - Empowering Afghans by enabling their access to asylum right and basic services in coordination with the migration agencies including law enforcement	4
Output 3.1 - PMM proactively responds irregular migration through strengthened operational and coordination capacity to maintain cooperation with the primary CoO and with the strategical partners at national, regional and international levels	3
Overall Rating of Output Delivery	3

Outcome Assessment	Overall outcome score: Green. On track to meet outcome targets. / The CSSF programme made good progress with delivering the desired changes at the outcome level overall. Beneficiaries, including Turkish government officials, refugees, migrants and Turkish host communities, provided positive feedback about the changes the programme is making. They welcomed the UK government’s support and encouraged its continuation.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Low/Medium

Summary of Programme Performance
Year	2019/20		2020/21		2021/22		2022/23
Programme Rating	A	A	Green	3	Green	3	Green	3
Risk Rating	Low/Medium		Low/Medium		Low/Medium		Low/Medium

What Support Did the UK Provide in FY 22/23?
The Turkey Migration Programme is part of a multi-year programme delivered through nine projects during the financial year 2022/23. The programme is aligned to the NSC Irregular Migration Strategy with Turkey as a priority country. It supports the National Security Council (NSC) Strategy on Turkey, which has migration as a central pillar; as well as being integrated into the Turkey Country Business Plan. This programme aligns to HMG’s new Integrated Review, particularly around the themes of Resilience, UK National Security, and Open Societies/Force for Good. The IR recognises that “migration will remain a permanent feature of the global landscape…with Europe the destination for mass migration from the Middle East and Africa in particular”. A key element of the programme is to deliver HMG’s efforts to work with Turkey to “manage the movement of people within Europe’s wider neighbourhood, including towards the UK”. This is done through a whole-of-route approach; building upstream capacity; and continuing to meet the legitimate needs of refugees and asylum seekers, in accordance with UK & Turkey’s international obligations. Together with €465.5m multilateral funding deployed through the EU Facility for Refugees in Turkey (FRIT (II) - and the deployment of HMG experts and political levers - this programme is the mechanism by which HMG meets migration-related objectives.

The nine projects are:
1. Strengthening Cooperation with Countries of Origin and Fostering Cooperation with Strategic Partners to prevent Irregular Migration (COMPLEMENT) (Delivered by International Centre for Migration Policy Development (ICMPD), beneficiary PMM)
2. Enhancing Analysis and Operational Capacity on Improvement of Legal Migration Policy and Pathways (ANAPOL) (Delivered by ICMPD, beneficiary PMM)
3. Improving employability and social inclusion of most vulnerable refugee women and youth (with Ankara Metropolitan Municipality) (Delivered by United Nations Population Fund (UNFPA), beneficiary refugee women and youth)
4. Facilitating Legal Pathways for the Migrant Labour Force in Turkey (Delivered by International Organisation on Migration (IOM), beneficiary Ministry of Labour and Social Security)
5. Multi-sectoral Approach for Fostering Resilience among non-Syrian Refugee and Vulnerable Host Communities (Delivered by RET, beneficiary refugees and migrants, Kayseri and Aksaray Municipalities and local authorities)
6. Social cohesion training programme for refugees in Turkey (Delivered by ASAM)
7. Fostering International Protection (Asylum) for the Most Vulnerable Refugees (Afghans) in Turkey (Delivered by ASAM, beneficiary refugees and migrants, PMM and law enforcement agencies)
8. Enforcing Turkish Coast Guard Efforts to Mainstream Human Rights Based and Gender Sensitive Response to Irregular Migration (ESSENCE) (Delivered by ICMPD, beneficiary Turkish Coast Guard (TCG))
9. Earthquake Response Project to renovate Nizip Camp for Syrians (Delivered by ASAM, beneficiary PMM and refugees and migrants)
Five projects have been covered during 22/23 Annual Review:
1. ICMPD - Strengthening Cooperation with Countries of Origin and Fostering Cooperation with Strategic Partners to prevent Irregular Migration (COMPLEMENT)
2. ICMPD - Enhancing Analysis and Operational Capacity on Improvement of Legal Migration Policy and Pathways (ANAPOL)
3. RETInt - Multi-sectoral Approach for Fostering Resilience among non-Syrian Refugee and Vulnerable Host Communities
4. ASAM -  Fostering International Protection (Asylum) for the Most Vulnerable Refugees (Afghans) in Turkey
5. UNFPA - Improving employability and social inclusion of the most vulnerable refugee women and youth

Key Results for FY 22/23

- Under the Irregular Migration Project (COMPLEMENT), returns cooperation with Pakistan was established and the document sharing database decreased the duration of return processing from 6 months to 2 days. A Pakistani Delegation was hosted in Turkey, between 27 July-7 August 2022. Technical meetings between the Delegation and PMM were held in Ankara and in Istanbul, and Field visit to Çankırı, Erzurum and Malatya Removal Centres (RCs) were conducted, where 4,006 irregular migrants with Pakistan nationals were interviewed and returned back to Pakistan. PMM refers to this as best practice and continues to use the established relationships for returns to Pakistan.
- Under the Regular Migration Project (ANAPOL), as a result of residence permit/visa training to PMM staff in provinces, staff awareness and knowledge increased on identifying the types of permits/visas. As a result issuance of work permits increased by 52%, student residence permits by 22%, humanitarian residence permits by 27%, family residence permits by 16%, investor residence permits by 26% and property residence permits by 25%. This project also enabled PMM to improve standardisation of provincial directorates. PMM has stated that the ANAPOL project has contributed to regularisation of irregular migrants through capacity building of PMM staff on visas and residence permits, which was not covered before. The unintended effect of this project is the support given to the Statistics Department of PMM through the procurement of software programme and trainings conducted to the personnel. By the help of this support PMM will be producing analysis from the data gathered under the programme and use the analysis to determine the profiles (i.e. migrants arriving legally to Turkey becoming irregular) and support the policy making decisions of PMM. The overall support provided under this project is the first of its kind in the field as most of the donors mostly focus on irregular migration.
- Under the UNFPA project, a centre for Women and Young Refugees was established within Ankara Metropolitan Municipality to provide refugees skills for employment, social cohesion training and reproductive health services. The centre is still functional and continues to provide most of the services by Municipality`s own means, including language courses and sports activities. The review team met a number of beneficiaries who were delighted that the service provision was continuing after project completion, emphasising that the centre had become a “lifeline” for them and their families. The project has also contributed to the Municipality`s capacity to deal with refugees - the model has also been shared with other municipalities as best-practice. Izmir, Sanliurfa and Adana municipalities have been interested and are looking to replicate the same model of service delivery to the most vulnerable migrants in those regions.
- The earthquake response project, a costed extension (with additional funding of £600,000) to the ASAM Social Cohesion Project (SUYE) has allowed the renovation of old accommodation ‘containers’ (small demountable cabins) in Nizip II Temporary Accommodation Centre (TAC), a previously disused Government of Turkey reception site for (mainly Syrian) refugees which provided shelter for refugee families who lost their homes in the earthquake. The project renovated 510 containers. A small element of the budget was also available to provide hygiene kits to refugees. Renovation was completed in less than 2 months including contracting and tendering. This was a rapid emergency response by a strong partner on the ground. PMM continues to use the same construction company for renovating containers with their own resources.

Key Lessons

- The CSSF programme takes a coherent and well-structured approach with its focus on interrelated aspects of migration in Turkey. There is good alignment with other HMG activities and programmes.
- Turkey is an important country for the UK in relation to migration, as well as in many other areas. The support provided to the Turkish government by the programme has improved British Embassy Ankara’s access and influence on officials involved with migration. The UK is described by the Turkish government officials as a ‘partner of choice’ in this area.
- The programme team has good relationships with the programme’s implementing partners, who appreciate the team’s flexibility and good communications. This has enabled the programme to respond to the evolving needs of beneficiaries and changes to the context.
- The programme demonstrated agility in responding to the major earthquake that struck southern and central Turkey in February 2023.
- End beneficiaries – including refugees, migrants and Turkish host communities – greatly value the support being provided by the UK government.
- Sustainability is well-considered and evidence suggests that the programme’s support to various parts of the Turkish government system is having a positive and sustained impact on the management of migrants and refugees.

Key Recommendations for FY22/23

1. Results management: some progress has been made with improving results management since the previous annual review, but further work is needed on the project and programme level results frameworks, which are essential for monitoring the delivery of the programme’s outcomes and outputs. The frameworks could be better presented to make it clearer which outcomes and indicators are delivered by which partners and through which projects. The outcomes included in the results frameworks should correspond to those used in the theory of change. Indicators could be made clearer and more consistently presented across milestones and targets. Outcomes and outputs should be more consistently applied across programme and project level results frameworks. Disaggregated data should be included in the results frameworks. It is recommended that a specialist evaluation advisor be involved with improving the project and programme level results frameworks.
2. Alignment with other programming: there is currently good alignment with other HMG activities and programmes. This will be increasingly important with the launch of the much larger new UK bilateral humanitarian programme in 2024. The two programmes have quite different purposes and promise to complement each other well, but this hinges on close cooperation between the two teams as the new bilateral programme takes shape and is launched. The joint programme board chaired by HMA is an important mechanism for ensuring the complementarity of HMG programmes in Turkey. The CSSF programme team’s role as the board’s secretariat is useful in ensuring coherence with wider programming.
3. Value for money: further work is needed to integrate value for money considerations into the programme. Implementing partners have improved their data collation and reporting on value for money during this review period, but there is still room for improvements to ensure more consistent and systematic reporting. A standardised approach to value for money across the programme would help with this.
4. Cross cutting themes: conflict sensitivity, gender and human rights are important to this programme. Although good consideration has been given to these issues previously, it is necessary for these analyses to be regularly updated. It is recommended that new consideration be given to conflict sensitivity and gender, where previous reviews were carried out four and three years ago respectively. Human rights concerns should continue to be monitored regularly via the programme’s new risk management mechanisms.
5. Communications: the programme is successfully delivering its outcomes and is having a positive impact, but successes could be better communicated internally within HMG and externally. It is recommended that feedback on existing internal communications products (monthly migration updates and quarterly reports) be invited from existing readers with a view to improving them. Consideration should be given to the distribution of these products to ensure that they are reaching the key audiences. It is also recommended that consideration be given to external communications, taking into account the government of Turkey’s sensitivities and beneficiary confidentiality. There is scope for well-designed external communications to support the programme’s goal and impact by highlighting its successes.