Programme Completion Review (22/23)

A. Summary Sheet
NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Anguilla Programme (AP)
Programme ID
Country and Region	Anguilla, Caribbean
IATI Unique ID
HMG Partners / (Lead in bold)	Foreign, Commonwealth, and Development Office (FCDO)
Total Budget	ODA:	Non-ODA: £83m
Budget this FY	ODA:	Non-ODA: £4.79m
Spend this FY	ODA:	Non-ODA: £5.40
Time Frame	Start Date: 1 April 2018	End Date: 31 March 2023

Outputs	Individual Output Rating
Previously reviewed:
Education infrastructure restored to pre-Irma levels and built back better	4
Health facilities restored to pre-Irma levels of functionality but with greater hurricane resilience	4
The majority of Government officials are located in appropriate, safe and hurricane-resilient accommodation, realising financial savings by co-locating and reducing of amount of rented accommodation	4
Prioritised elements of National Infrastructure returned to full functionality but built back stronger	4
Revenue strengthening reforms required under the Medium Term Economic and Fiscal Plan (MTEFP) implemented	4
Currently reviewed:
Albena Lake Hodge Comprehensive School (Package 2)	3
Road Bay Jetty	2
Princess Alexandra Hospital (dialysis and isolation wards)	4
Blowing Point Ferry Terminal	4
Education infrastructure (provisions for solar panels)	4
Overall Rating of Output Delivery	4

Outcome Assessment	Agreed prioritised infrastructure restored to pre-hurricane levels, enhanced to improve resilience. / Significant final progress has been made as the secondary school, the new ferry terminal, and the remaining packages of health-related activity were completed. / Noting that this is a Programme Completion Review (PCR), these results are mentioned in addition to the outputs achieved in previous years of the programme, which include health clinics and a hospital, completion of the House of Assembly, initial construction of the Road Bay Jetty, airport runway resurfacing, and revenue strengthening. / Moreover, while this review includes activities from the past financial year (22/23), given the unique nature of the programme, specifically the multiyear nature of a number of its components, commentary within this review extends across the lifetime of the Programme. / Construction of the final project, Blowing Point Ferry Terminal, began in August 2021 with completion achieved in late 2022. This project was completely managed by the Ministry of Infrastructure using project experience developed from their involvement in earlier Anguilla Programme (AP) projects, applied with great success. / The handover of the Albena Lake Hodge Comprehensive School to the Department of Education was delayed, but had opened at the time of the review with an almost full timetable in operation. Crucially, this means that the much-maligned ‘split shift’ system could finally be removed, a system which had been in place since the Irma and Maria hurricanes that prevented school grades from attending classes simultaneously. This represents a significant uplift in educational outcomes and staff wellbeing. / Although programme delivery has continued to be hampered by the disruption caused by geopolitical flashpoints on material supply chains and international shipping, delays were mitigated where possible, with the ferry terminal demonstrating agility in procurement and construction timetabling. / Contracts were generally well managed via clear Project Managers Instructions and the issue of Extensions of Time without costs agreed between contracting parties. There is ample evidence of regular governance meetings, decision-making and recordkeeping by the Governor’s Office, and a strong grip by the Programme Manager (PM), the Governor’s Office and a consistent focus on delivery objectives, governance requirements and value for money in the programme’s final year. / The full operation of the New Road Bay Jetty remains delayed. This is due to a package of onshore works being requested by the Port Operator. The Memorandum of Understanding between the Governor’s Office and the Port Authority will indicate what was to be included in the envelope provided for the Jetty. Further works must be considered additional to the Anguilla Programme. It is these remaining issues which impact the Output rating above, not concerns about the new infrastructure itself.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Low

Summary of Programme Performance
Year	2020/21		2021/22		2022/23
Programme Rating	B	B	B	B	A	A
Risk Rating	Medium-low		Medium-low		Low

What Support Did the UK Provide in FY 22/23

- Support to bring the Albena Lake Hodge Comprehensive School to completion.
- Support to complete the Blowing Point Ferry Terminal (Phase 2).

Key Results for FY 22/23:

- Secondary School completed and operational.
- New Ferry Port, Blowing Point, complete and fully operational.

Key Lessons

- Despite some small ongoing issues in a limited number of areas – the Anguilla Programme has been a success, despite the unique nature of the programme, the risk inherent in the mode of delivery and having to overcome quite sustained capability and capacity issues. The CSSF or successor should continue to consider novel or atypical programmes where they can strongly contribute to
- Maintenance budgets and effective maintenance plans have not been developed and put into place.
- Ongoing snagging issues around the Road Bay Jetty demonstrate the importance of consensus when designing infrastructure projects which can potentially span different elected administrations.
- The importance of clearly communicated decision-making when decisions are made with regards scope reductions.
- Feedback from a range of stakeholders has been consistent that bringing in external engineering expertise was beneficial not just for the Anguilla Programme, but in building wider capability in the construction and project management sectors. See ‘Wider Unintended Benefits’ section below for more detail.
- The CSSF’s flexibility to issue prepayments where needed was highlighted as important for using on-island contractors.
- HMG should consider the lessons learned from this programme for future similar programmes, particularly where action is required to deliver directly in a geography which either has insufficient expertise or capability. The experience of the Anguilla programme should be formally noted for reference in the CSSF and beyond.

Key Recommendations

- A number of pieces of scope were removed for sensible reasons – predominantly a lack of funding. HMG should consider looking to fund those packages where they would further improve the sustainability of its investment and reinforce the wider fiscal position of the Government of Anguilla (GoA) – namely through the provision of solar panels where passive provision is in place.
- HMG should continue to lobby the GoA to put in place effective maintenance plans, backed by adequate Operating expenditure budgets and technical support for maintenance planning, where feasible.
- Recommend a targeted narrative lessons learned experience based on key areas across the life of the programme (e.g. development, prioritisation, implementation, delivery and evaluation).