Annual Review (22/23)
A. Summary Sheet
Programme Title	Border Security in the UKs Overseas Territories
Programme ID	OTD Border Security Programme
Country and Region	Overseas Territories
IATI Unique ID	CSSF-07-000013
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO), Home Office (HO), Ministry of Defence (MOD)
Total Budget	ODA: £688,000 (Mains)	Non-ODA: £2,600,000 (Mains)
Budget this FY	ODA: £277,000 (Reduce at mid)	Non-ODA: £2,446,000 (Post-Supps)
Spend this FY	ODA: £263,131	Non-ODA: £1,860,721
Time Frame	Start Date: April 2022	End Date: March 2023

Outputs	Individual Output Rating
Output 1: Multi-Territory Secondment, Twinning and Exchange Programme, including cross-Overseas Territories (OT) conference	3
Output 2: Multi-Territory Threat and Operational Needs Assessments	4
Output 3: Modern Slavery and Human Trafficking Awareness/Training	3
Output 4: Multi-Territory Border Transformation, Upskilling and Capacity Building	2
Output 5: Creation of OT cyber community	3
Output 6: Undertaking National Cyber Risk Assessments (NCRA) in OTs, identification of critical national infrastructure and skill development	3
Output 7: St Helena secondment to support implementation of recommendations from NCRA	3
Output 8: Identification of current maritime capability and required development in Caribbean OTs	2
Output 9: Provision of technical expertise/training to OT Coastguards and Marine Police Units	1
Output 10: Additional support to British Virgin Islands (BVI) marine police unit	3
Output 11: Additional support to Turks and Caicos Islands (TCI) Borders	4
Overall Rating of Output Delivery	3

Outcome Assessment	As with the AR for last year, there has been significant progress against several outputs, which has led to concomitant progress against the outcomes. Overall, the programme is largely achieving its aims, although the cohesion of the successes is less than optimal in the absence of an overall HMG strategy for the OTs. The Review Team understands that this is in progress and the programme will benefit from this. The Results Framework has been implemented, as recommended in last year’s AR, which has improved tracking; the introduction of shorter-term milestones will add to this.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		Medium-Low

Summary of Programme Performance
Year	2020/21		2021/22		2022/23
Programme Rating	2	Red	3	Amber	3	Amber
Risk Rating	Medium-Low		Medium-High		Medium-Low

What Support Did the UK Provide in FY 22/23?
- Ongoing secondment of Home Office personnel in TCI and additional short-term targeted secondment to TCI in October 2022, Cyber secondee in St Helena, short-term
  - Recruitment for replacement customs and immigration secondee in Cayman Islands re-advertised.
- Conducted first customs and immigration conference for OT delegates.
- Threat and Operational Needs assessment completed in TCI, Anguilla, Montserrat and St Helena
  - TA conducted in Falklands and Port Security assessment completed in Cayman.
- Modern Slavery and Human Trafficking Awareness/Training delivered to eight services and Customs training provided to Anguilla and TCI, Vessel Search training delivered in several OTs, Maritime training to RYA Level 2 delivered to Marine Police unit in BVI and maritime accident investigation training delivered in UK.
- Agency to assist TCI Government (TCIG) to develop a Border Management system identified and terms of reference produced.
- Second annual cybersecurity conference in Miami, Monthly intra-OT cyber meetings, Formation of the OTs Cyber Community Coordination Group (CSCCG), NCRAs completed for all OTs and recommendations implemented.
- Delivery of four vessels to BVI Marine unit
- Deployment of Cayman Islands helicopter to assist TCI and Provision of accommodation to support US agency air crew deployment (US Customs and Border Protection)

Key Results for FY 22/23:
1. Increase in intra-OT cyber cooperation and interaction.
2. Preparation for TCI Border Force, expected to go live in FY 23/24
3. Secondees gaining traction with OT, particularly within TCI.
4. Increase in capacity and capability of marine unit in BVI.
5. Training largely intelligence-led now and developed following TNAs, particularly in BVI and TCI
6. Cooperation with US entities increased, including with Coast Guard and DEA
  1. At least partly due to increased professionalism of Caribbean OTs, which was achieved with CSSF funding.

Key Lessons
1. COVID-19 impacts from the previous FY continued into the reporting period - Lack of resources, including limited connectivity, reduced or obviated opportunities for mitigations such as remote working.
  1. As highlighted in previous reviews, the lack of an updated cross-HMG OT strategic vision for the OTs has hampered a coordinated response; The 2012 White Paper is still extant, but most parties agree that it would benefit from an update. The Review Team understands the FCDO has commenced work to update this, (strategy document and declaration) which is to be welcomed; The withdrawal of HOIO support for the next financial year will negatively impact the progress made in the customs and immigration areas.
2. CSSF funding in the OTs has been most impactful when there is a local champion to drive this, which in the cases examined is either a secondee or a UK employee, such as a police commissioner. The agile nature of CSSF has allowed the OTs to adapt to changing needs, such as focussed training which has, for example, facilitated an increase in fines and seizures as well as an improvement in the responses to irregular migration in TCI .
3. All interviewees acknowledged the sterling efforts of the Border Security Programme Manager, who has driven all aspects of the programme well. As with the previous point, the right person can make significant differences.
4. CSSF funding has had a multiplier effect in many areas, for example:
  1. the TCIG has agreed to fund a digital border programme, including biometrics, following CSSF funding to undertake an initial review in the area.
  2. US cooperation has increased as mentioned above, due at least in part to an increase in border security professionalism in the OTs enabled CSSF-funded programmes.

Key Recommendations for FY 22/23
1. Completion and implementation of the HMG OTs new Strategy document
2. Refinement of the Results Framework to include more tangible benchmarks.
3. Consider an increase in targeted secondments to assist the OTs, particularly in customs and immigration.
4. To assist in governance, consider communicating the details of the Programme Boards to key interlocutors in the OTs.
5. The Theory of Change framework is good, but there is little evidence of knowledge of it with interlocutors. It could be communicated more effectively.