Annual Review/Programme Completion Review (22/23)

A. Summary Sheet
NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Environmental Sustainability and Climate Change (ESCC) Programme
Programme ID	CSSF-07-000011
Country and Region	UK Overseas Territories (OTs)
IATI Unique ID	41010
HMG Partners / (Lead in bold)	Department of Environment, Farming and Rural Affairs (Defra) / Ministry of Defence (MoD) / Business Energy Innovation Science (BEIS)
Total Budget	ODA: £1,689,000	Non-ODA: £2,071,000
Budget this FY	ODA: £1,689,000	Non-ODA: £2,071,000
Spend this FY	ODA: £1,881,582	Non-ODA: £2,086,224
Time Frame	Start Date: April 2022	End Date: March 2023

Outputs	Individual Output Rating
Output 1: Seabed mapping datasets collected in areas of high priority to update the navigational charts and provide the foundation information layer for environmental and climate change research and policy decision making	4
Output 2: Increasing resilience through capacity building and technical assistance	4
Output 3: An improved understanding of pressures facing coral reefs in UK OTs and priority mitigation options developed to manage these pressures and improve reef health and resilience.	3
Output 4: Increased awareness and understanding of coral reefs throughout society in each OT, with local stakeholders at all levels understanding the role and value that coral reefs play in coastal protection, well-being and food security.	3
Output 5: Contribute to providing an effective response to mitigate the effects of Stony Coral Tissue Loss Disease (SCTLD) in the region, ensuring the latest disease treatments and management strategies inform the response.	4
Output 6: Embed project capacity with OT partners to deliver the coral reef action plans, and work towards building buy-in for the longer-term implementation of effective coral reef management beyond project funding. Capacity building also for the nature based solutions outputs.	3
Output 7: Increased awareness and understanding of the role and value of the environment in providing resilience to natural hazards throughout society in each OT	3
Output 8: Reviewed, developed and refined Disaster Resilience tool(s) in each OT	3
Output 9: Improved understanding of the role of nature-based solutions, and value of natural capital in enhancing resilience to natural hazards.	2
Output 10 (/11): Enhanced data management capacity in each OT	2
Output 12: St Helena Cloud Forest (SHCF): Increased cloud forest habitat, connectivity and quality to benefit biodiversity and water resources on St Helena: Increase plant production and plants used in habitat and gene bank planting by 25% year on year and increase area of habitat restoration by **% (target TBC)	3
Output 13: SHCF: St Helena's water resources more clearly understood, and data collected to inform the development of the water resources management plan. (Project data shared with St Helena Government (SHG) and ‘Connect Saint Helena’ on a regular basis to support the development of an island-wide water resource management plan. Note: the development of a Water Resource Management Plan is a joint venture between SHG and ‘Connect Saint Helena’, due for completion by 2024.)	4
Output 14: SHCF: Increased capacity of in-Territory agencies to effectively manage the Peaks National Park and to improve public awareness/engagement	3
Output 15: SHCF: Programme management, linkage with strategic and management plan and communications	3
Overall Rating of Output Delivery	3

Outcome Assessment	Overall outcome performance is Amber, due in part to some weak outcomes from one delivery partner and lack of evidence of impact and continuation of work. Additionally, many of the outcomes require continued work in the OTs, either as business-as-usual (BAU) or through additionally funded outputs, meaning that the outcomes cannot yet be fully realised and with less evidence of long-term change. Feedback from OTs, however, did indicate that even though outcomes cannot yet be fully met, the funding has given opportunities and been a catalyst for further beneficial work.
Overall Outcome Progress Rating:		3
Overall Risk Rating:		Medium-High

Summary of Programme Performance
Year	2020/21		2021/22		2022/23
Programme Rating	3	3	4	Green	3	Amber
Risk Rating	n/a		Medium-High		Medium-High
Note: Output / Outcome score

What Support Did the UK Provide in FY 22/23?
- A final year of continued support for compliance with hydrographic governance and the ability to make OT waters safer.
- A final year of continued support for efficient environmental management and raised awareness of OT importance of OTs’ natural environments, including disaster resilience and coral conservation.
- A second year of funding for St Helena’s Cloud Forest project, providing the tools and resources for restoration of cloud forest habitat and improved water security.
- Funding for climate change related projects led by Governors’ Offices in four OTs.

Key Results for FY 22/23:
- Completion of the Seabed Mapping, Coral and Disaster Resilience projects funded from the ESCC Programme.
- On-going Cloud Forest project continues to grow and starts to produce results used for water security management.
- Successful Post-led projects impact policy decisions in the OTs.

Key Lessons
- Early and ongoing engagement and communications with OT governments and Governors Offices.
- Different OT strategic priorities and lack of adequate resources lead to weaknesses within the OTs for project sustainability and long-term legacy.
- Strong delivery partner project management and OT relationships result in projects with better sustainability and higher value for money.

Key Recommendations for FY 22/23
- Improved communication to delivery partners (current and future) of programme requirements and expectations.
- Ensure that OT governments and Governors’ Offices are engaged before programme activities are agreed, to ensure that strategic needs of the OT, resourcing, sustainable/post-project funding and legacy are considered.
- Further support and guidance to delivery partners to aid the financial reporting, gender and climate requirements of programming.
- Review, differentiation and inclusion of more risks and issues in the Risk Register.
- Guidance on OT engagement to ensure adequate communication of activities.