Annual Review/Programme Completion Review (22/23)

A. Summary Sheet
NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	OVERSEAS TERRITORIES JUSTICE PROGRAMME
Programme ID	CSSF-07-000009
Country and Region	The British Overseas Territories
IATI Unique ID
HMG Partners / (Lead in bold)	FCDO, Ministry of Justice (MoJ), Home Office (IPAS)
Total Budget	ODA: £917,000	Non-ODA: £3,545,000
Budget this FY	ODA: £917,000	Non-ODA: £3,545,000
Spend this FY	ODA: £853,847	Non-ODA: £3,015,969
Time Frame	Start Date: 1 April 22	End Date: 31 March 23

Outputs	Individual Output Rating
Support OT Police Force reviews and actions	2
Embed common minimum standards across operational policing	2
Support the establishment of ‘Women in Policing’ networks in the OTs	3
Establish agile new capabilities to support policing across OTs	2
Embed prison standards framework and training support	3
Deliver training, deployment and infrastructure projects across OT justice systems	3
Implement legislative reform support based on need assessment	2
Strengthen child safeguarding systems and family court procedures	3

Overall Rating of Output Delivery	2

Outcome Assessment	The overall assessment reflects the ongoing challenges of delivering the scope of this programme across the Overseas Territories (OTs). There are political, strategic, and operational challenges of working on policing, prisons, and safeguarding, set against a background of underinvestment and a relatively small CSSF budget supporting an ambitious delivery plan. There is an opportunity to reaffirm and shape strategic objectives, programme design and operational delivery against a risk focused baseline by developing a Strategic Threat and Risk Assessment (STRA) as well as better monitoring, evaluation and learning.
Overall Outcome Progress Rating:		Amber/Red
Overall Risk Rating:		Medium-high

Summary of Programme Performance
Year	2020/21		2021/22		2022/23
Programme Rating	3	Amber	3	Amber	2	Amber/Red
Risk Rating	Medium		Medium-Low		Medium-High

Note: / Output Score = 2: Planned results at high risk. / Outcome score = Amber/Red: Planned results at high risk.

What Support Did the UK Provide in FY 22/23?
- law enforcement support sought to build capability within the OTs, agree standards informed by international good practice and provide technical expertise. This included: training operational police; improving standards of investigation and operational performance; establishing trained and accredited financial investigators to improve the quality of finance-related investigations.
- The support to HM’s prisons in the OTs and further support to the justice systems included: the development of bespoke training packages, building capacity of parole boards and working to develop policy on prisoner rehabilitation.
- capacity-building support to safeguarding systems that protect vulnerable children and assistance in reviewing and designing regulations that enhance human rights.

Key Results for FY 22/23:
- The pilot of detention standards framework in the OTs was introduced. This is a key milestone in embedding an inspection process that encourages human rights compliant places of detention.
- British Virgin Islands (BVI) prison superintendent deployment has significantly improved the safety and security of the prison by increasing staffing levels and focuses on developing senior managers locally. This builds resilience and local capability ensuring that change can be long term.
- On law enforcement, the commercially procured investigation team in Turks & Caicos Islands (TCI) assisted in arrests and development of casework for recent murder crimes and started cold case reviews of all unsolved murders from the last three years. The work directly improved evidential submissions for charging decisions and contributed significant actionable intelligence to the national crime intelligence bureau.
- Policewomen across five OTs were supported with their professional development and two dedicated women in policing networks established in Gibraltar and TCI.
- specialist investigators deployed to Montserrat facilitated the arrest of six high profile individuals involved in fraudulent activity and the investigation team in BVI improved local capacity and capability by mentoring, training and upskilling local officers.
- the litigation guardianship project developed new child centred reporting templates and guidance in Bermuda providing the court with better recommendations.

Key Lessons
- Law Enforcement: the implementation of recommendations from audits and inspections requires commitment and leadership within individual OTs to deliver sustainable results.
- Prisons: The ongoing development of European Convention on Human Rights (ECHR) compliant process and procedures across the OT prison estate requires visible leadership and consistency of approach.
- Child Safeguarding: UK local authorities need to ensure that local context and capacity is factored into project planning and that there is good communication between the parties.

Key Recommendations for FY 22/23
A programme level Strategic Threat and Risk Assessment (STRA) be undertaken to strengthen the alignment between UK government and OTs, and documentation be produced that clearly demonstrates how the programme is aligned to HMG strategies. It is recommended that together with risk-based programme design decisions, FCDO activity seeks to incorporate sustainability considerations into each individual delivery plan. Where that is not possible, it is recommended that this be explained to support future programming and budgetary decisions.

Results frameworks should be utilised with greater effectiveness to monitor and evaluate delivery implementation throughout the year. The quality of programme level quarterly reports could be further improved by including evidence and commentary concerning any challenges or failures to deliver specific aspects of the programme, to ensure that learning may be identified and shared.

Operational capabilities within Caribbean OTs should be used to lever regional expertise, benefit from economies of scale, and encourage closer inter-territory cooperation and sharing of best practices. It is also recommended that observance of VfM be strengthened going forwards to ensure efficiency, effectiveness, economy, and equality factors are each actively monitored against performance in programme design and operational delivery. The development of a suitable monitoring tool would be beneficial.