Annual Review 22/23

A. Summary Sheet
Programme Title	China Capability Programme
Programme ID	Asia Pacific
Country and Region	UK
IATI Unique ID	CSSF-15-000002
HMG Partners / (Lead in bold)	Cabinet Office (CO), FCDO, DSIT, DCMS, BEIS, DEFRA, MOD
Total Budget	ODA: £0	Non-ODA: £2.5m
Budget this FY	ODA: £0	Non-ODA: £1.6m
Spend this FY	ODA: £0	Non-ODA: £840,229
Time Frame	Start Date: April 2022	End Date: March 2023

Outputs	Output Rating
Output group 1 – knowledge and expertise (weighting: 80%)	3
Output group 2 – future China capability (weighting: 10%)	2
Output group 3 – people and enablers (weighting: 10%)	2
Overall Rating of Output Delivery	3

Outcome Assessment	The programme is likely to have made a reasonable contribution towards delivery of the desired changes at the outcome level. However, the Results Framework against which the programme is measured was incomplete and the evidence available to support this judgement was moderate.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		Low

Summary of Programme Performance
Year	2020/21		2021/22		2022/23
Programme Rating	n/a	n/a	n/a	n/a	3	Amber
Risk Rating	n/a		n/a		Low

Note: Output / Outcome score

What Support Did the UK Provide in FY 22/23?
- Total budget of £1.6m budget (all non-ODA) made available to all Whitehall departments, of which £840,229 was spent.
- Delivery and support of key activities across three ‘HMG China capability’ output groups: knowledge and expertise, people and enablers, future China capability.
Key Results for FY 22/23:
- Knowledge and expertise: the programme enabled expert panels, research reports and training sessions across government to enable officials to develop their understanding of China and the issues they are working on. This included a flagship training programme with some of the UK’s leading China experts, an externally produced report providing up-to-date knowledge on business practices and sectors within China and; a China Risk Indicators Analysis and Toolkit for how businesses can respond when contemplating deals with/in China.
- People and enablers: cross-HMG awareness on ways to improve China capability was improved, with departments deepening their understanding of their role in delivering the Integrated Review and the HMG China Strategy. This included a two day China Tech Training with 120 participants from departments including DSIT, CO, DBT, FCDO, HO, HMT, MOD and NCSC.

Future China capability: progress was made on building the foundations to scale up pilot projects to build long-term China capability. This included creation of a long list of China experts across government and related workshops with experts to identify future workstreams.
Key Lessons
CO has performed an essential cross-Whitehall/convening role with this programme, however CO is not resourced, or structured, to deliver active management of programmes with complex project-management requirements. This should be closely considered in the design of future programmes.

- China can, at times, be viewed as a homogeneous monolith within HMG. China-focussed teams have to work hard to ensure colleagues across government recognise and understand the nuances. This is likely to be an ongoing issue, the significance of which can be reduced if additional China expertise in the National Security and Economic Security communities is developed.
- Given the sensitivity regarding certain aspects of China-focussed work, communicating HMG interests and requirements to external suppliers can be challenging. It is important to build in sufficient time to manage such issues when procuring work from external parties.
Key Recommendations for FY 22/23
Management - merge the separate CO-led and FCDO-led China Capability programmes into a single programme, managed by the FCDO China Capability and Resilience team.

- Governance – strengthen and establish a regular meeting schedule of the cross-Whitehall China Capabilities Working Group, ensuring CO have a central role within this structure.
- Strategy – review and agree programme objectives, including clear articulation of long-term strategic intent.

Programme management – review the programme-level Theory of Change and develop new Results Framework and Risk Register.

Monitoring, Evaluation and Learning – engage external support to assist with development of the ‘strategy’ and ‘programme management’ points above, and a fit-for-purpose approach to measuring and reporting results at the programme level.