Annual Review/Programme Completion Review (22/23)

A. Summary Sheet
NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Philippines Conflict, Stability and Security Fund (CSSF)
Programme ID	CSSF-09-000007
Country and Region	Philippines, South East Asia and Pacific
IATI Unique ID	CSSF-09-000007
HMG Partners / (Lead in bold)	FCDO, MoD
Total Budget	ODA: £ 12.5 m	Non-ODA: £ 0
Budget this FY	ODA: £ 2.5 m	Non-ODA: £ 0
Spend this FY	ODA: £ 2,549,186.48	Non-ODA: £ 0
Time Frame	Start Date: 1st April 2022	End Date: 31 March 2023

Outputs	Individual Output Rating
Bangsamoro Parliament acquire skills and knowledge to enact quality and inclusive legislation and perform effective oversight.	4
Bangsamoro women acquire skills and opportunities to politically engage at all levels across the region.	4
Bangsamoro Citizens understand the new parliamentary system, and their democratic functions and rights.	4
Overall Rating of Output Delivery	4

Outcome Assessment / Statement: Locally owned institutions and processes that are increasingly accountable, inclusive, and pluralistic, with tangible benefits delivered to citizens, working together to make progress on the Bangsamoro Organic Law (BOL) and peace process.	The programme is supporting the delivery of this outcome, with good progress being made on all three intermediate outcomes and all outputs. The programme retains good strategic clarity in a complex and fragile environment.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Medium

Summary of Programme Performance
Year	2020/21		2021/22		2022/23
Programme Rating	4	AMBER GREEN	4	GREEN	4	Green
Risk Rating	Medium-High		Medium-High		Medium

Note: Output / Outcome score

What Support Did the UK Provide in FY 22/23?

FY21/22 was the third year of this programme. Interventions primarily focussed on three strands to support the ‘political/governance track’ of the Bangsamoro Peace Process, which established the Bangsamoro Autonomous Region of Muslim Mindanao (BARMM). These three strands were:
1. increasing the capacity and governing capability of officials in the Bangsamoro Transition Authority (BTA)
2. strengthening women’s political participation and promotion of women, peace and security;
3. promoting civic engagement.

There was also some support provided to tackle the Climate-Security nexus in the region to address the growing risks brought by climate emergencies.

The CSSF Philippines programme funded eight projects in 22/23:

Project Code	Project End Date	Project Name	Project Partner	Overall Total

PAP CSSF 000110	31-Mar-23	Promote Voting Rights	ChildFund	£ 286,515.14
PAP CSSF 000111	31-Mar-23	Supporting / Democratic Stability in the Bangsamoro III	Westminster Foundation for Democracy	£ 750,604.97
PAP CSSF 000123	28-Feb-23	Peace Mediation Support II	CR	£ 19,720.38
PAP CSSF 000121	20-Mar-23	BARMM Citizen Engagement II	TAF	£ 375,921.23
PAP CSSF 000116	15-Mar-23	Women, Peace and / Security II	UN Development Programme	£ 350,000.00
PAP CSSF 000122	25-Mar-23	Women Political Empowerment II	Catholic / Relief / Services	£ 253,793.73
PAP CSSF 000124	31-Mar-23	Strengthening / Resilience of / Climate-Related / Security Risks in / BARMM	International Organisation for Migration	£ 250,000.00
PAP CSSF 000134	31-Mar-23	Comparative Learning Visit	CR	£ 169,783.89
PAP CSSF 000033	30-Apr-23	Philippines - Staff costs	Grades (Country Based) C4 & / B3	£ 90,585.14
PAP CSSF 000035	30-Apr-23	Philippines - Platform costs		£ 2,262.00
				£ 2,549,186.48

Key Results for FY 22/23:

- Passing of the Bangsamoro Electoral Code into law - including a stipulation for 30% of party nominations to be represented by women.
- The First Minster of the BARMM Parliament participating in a visit to London and Scotland, and a cross party and CSO trip to Northern Ireland, which saw learning and cross- party dialogue.
- Mobilising and strengthening the capacity of female leaders and women’s associations to enable them to develop greater awareness of their rights and increase their participation in the development of a new autonomous region.
- Developing stronger formal and informal relationships between CSO organisations and the BARMM MPs and Officials. For example, CSOs were fully involved in scrutinising the budgets for economic and social development plans.

Key Lessons
Political neutrality can be achieved but it requires careful scoping to identify trust issues and to set out clearly defined working relationships. This is crucial in inherently political contexts where peace is fragile and perceived support to some can be provocative to others.

Agility; The presidential election led to a change in the nominated BARM MPs, which put the Parliament in temporary hiatus. Those working with MPs used this wisely by focussing their activities on parliamentary staff more.

Getting together decision makers and ‘change makers’ together in new settings for a sustained period can enable deeper conversations and connections (although the learning trip obviously gives this a strong focus).

Training for CSOs and others can be particularly useful if they have a practical focus. For example, ‘write shops’, which are usually skills-based training around a particular issue; where participants may be asked to develop ideas and basic products, such as advocacy messages and brief position papers.

Programmes will do best when the projects are well coordinated and have the opportunity to work together, as opposed to only focussing on their own objectives, however complementary.

Key Recommendations for FY 22/23

There is need for stronger coordination and collaboration of implementing partners activities, so they work in synergy and avoid duplicating efforts. The current MEL sessions could be extended and used for stakeholder mapping across the group to identify who is working with which groups and for work planning and identifying where there is opportunity for collaboration, coordination and/or introduction.

Efforts to re-establish and re-energise the ICG should be prioritised. It is important that it is used to strengthen pressure to make progress on the normalisation tract; given its likely contribution to the continued success of the peace process. It is also crucial that such a group is functioning and useful when elections are held, should it be needed as an additional route for negotiation. The British Embassy should also consider any other avenues it can use to reaffirm the importance for progress to be made on the normalisation tract.

Providing support past the 2025 elections and through the transfer of power is crucial. The UK, like others, has invested in this (both financially and reputationally) and this investment needs to continue during the early days of a democratically elected Parliament. The CSSF appears to be the most relevant source of funding but the Embassy needs to ensure the programme continues to evolve with the context and with the UK’s National Security needs and hence consider future sources of funding, as it is important the UK remains involved in materially supporting the process.

The programme already has links with the UK work focussed on terrorism in the Philippines, but this should be developed further, as well as exploring ties with CSSF/ISF work around maritime security, illicit finance and/or Serious and Organised Crime, given the relevance to the Southern Philippines (but recognising there may not be direct relation to current programmes).

ISF and the Philippines Embassy could use scenario planning to consider how funding that covers the 2025 elections retains a flexible/responsive element which can be used in the response to the outcome of the elections to support the peace process, as seems appropriate at the time. The forthcoming JACS process will consider the UK’s support further and should be used to consider future support more thoroughly. The Embassy will need to consider both form, function and sources of funding post 2025 very shortly.

The Embassy should assess the ‘Political Access and Influencing’ role of the programme. The importance of the programme in this domain has been well articulated to the review team, but further assessment and documentation of this could prove useful in consideration on how the programme evolves. This should not become a bureaucratic exercise, but more a strategic approach to how the Embassy ensures the opportunities presented by the programme are maximised and how this can then be evidenced. This may play an important role in considering the importance to UK National Security versus the other diplomatic benefits and can be used in evidence for future funding.

Partners could share their lessons on training and dialogue sessions and the MEL partner could also provide lessons from the literature from other relevant contexts. A number of the implementing partners are delivering awareness raising, training and dialogue sessions. Whilst these have different aims, there is an opportunity to improve learning around the delivery and assessment of these sessions. A future group MEL session should focus on this.

MEL providers should work with programme implementors and the Embassy to ensure all indicators are realistic, but stretching and simply and clearly constructed. The programme has scored highly because it is a good programme. However, some of its indicators and targets are not ambitious enough. In addition, whilst the outcomes are outcomes rather than outputs; the programme should ensure the indicators are mainly outcome indicators as there are some that are close to output indicators.

Once the new project officer is in place, further triangulation of activities through in person visits should take place.