Annual Review (22/23)

A. Summary Sheet
NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Counter Smuggling/Illicit Commodities (COSIC) Programme
Programme ID	C-SOC-0008
Country and Region	Global / Africa: Ghana; Guinea; Guinea-Bissau; Kenya; Morocco; Nigeria; Senegal; Tanzania; / Americas: Brazil; Columbia; Dominican Republic; Ecuador; Peru; Panama / Eurasia: Azerbaijan; Pakistan; Turkey; Afghanistan / Europe: Bulgaria; Greece; Hungary; Poland; Romania; Slovakia
IATI Unique ID	CSSF-12-000006
HMG Partners (Lead in bold)	Home Office, FCDO, National Crime Agency Joint Narcotics Analysis Centre
Total Budget	ODA:	Non-ODA:
Budget this FY	ODA: £4,700,000	Non-ODA: £2,300,000
Spend this FY	ODA: £2,145,833	Non-ODA: £2,654,901
Time Frame	Start Date: 1.4.2021	End Date: 31.3.2025

Outputs	Individual / Output / Rating
1. Countering trafficking of Illicit Commodities from Eurasia	4
2. Countering smuggling of Class A drugs and cash from Africa to UK	4
3. Border Security Project - Home Office International Operations - Americas	4
4. Reduction of Firearms Threat from Turkey to the UK	4
5. Combatting Serious and Organised Crime from Afghanistan: A 4P Approach	-
6. Community Resilience Building against Illicit Economies in West Africa Borderlands	3
7. Countering the flow of illicit cash	4
8. Crystal Methamphetamine Analysis Project	4
Overall Rating of Output Delivery	4

Outcome Assessment	The COSIC Programme strengthened the capacities of partner countries to tackle serious and organised crime related to smuggling and trafficking of illicit commodities. The programme is on track although the very positive achievements towards outcomes were not captured by the 2022/23 results’ framework. A revised framework has been adopted for 2023/24.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Medium

Summary of Programme Performance
Year	2020/21			2021/22			2022/23
Programme Rating	Output	Outcome	Output		Outcome	Output		Outcome
	B	B	No score assigned		Green	4		Green
Risk Rating	M		M			M

What Support Did the UK Provide in FY 22/23?

- Training of customs personnel and law enforcement personnel in Africa, the Americas and Asia to detect drugs and other illicit commodities at airports, land crossings and seaports.
- Equipment including handheld x-ray equipment to locate drugs and other illegal commodities supplied to the Dominican Republic, Ecuador, and Panama.
- Border security enhancements including on Tukey’s border with Iran and Syria.

# Key Results for FY 22/23

- Cooperation on legislation led to Turkish authorities seizing and destroying 450K blank firing weapons and a significant reduction in their use in crimes in the UK.
- Ninety (90) tonnes of cocaine seized in Central America in FY22/23 because of COSIC and other UK funded capacity building initiatives.
- Bulgaria forms inter-ministerial group to address legislative gaps and increase coordination to counter cash smuggling.

# Key Lessons

- Partner capacity needs to be taken into consideration when setting realistic timescales for the construction of infrastructure to reduce the risks of projects not completing on schedule.
- Project onboarding needs to be fully completed, outcome and output indicators defined, and reporting processes understood by delivery partners.

# Key Recommendations for FY 22/23

- Strengthen COSIC programme governance by enhancing Programme Board’s oversight of crosscutting issues including gender, finance, results, and risks and enable the Senior Responsible Owner (SRO) to hold output leads to account for delivery of outcomes and outputs.
- Improve reporting and monitoring of outcome and output level results and risks by fully completing the project onboarding process and instituting regular engagement of programme team with outputs.
- Strengthen gender mainstreaming processes by integrating gender perspectives comprehensively in all relevant dimensions of the programme (including theory of change, risk assessment, results, activities and Monitoring, Evaluation and Learning (MEL)) ensuring clear guidance is provided to project partners and Gender Equality and Social Inclusion (GESI) markers assigned to each project.