CSSF Annual Review (23/24)
# A. Summary Sheet
Programme Title	Africa Peace Support Operations (APSO)
Country and Region	Sub-Saharan Africa (continental)
Programme ID	C-AFR-001	IATI Unique ID	CSSF-03-000017
Start date	1 April 2021	End date	31 March 2025
HMG Partners / (Lead department in bold)	Ministry of Defence (MOD) and Foreign, Commonwealth & Development Office (FCDO)
	Total overall Programme Allocation over 4 years (including SUPPS).	Allocation FY2023/24	Spend FY 2023/24
ODA	£5,301,000	£1,250,000	£1,145,620
Non-ODA	£16,722,000	£3,916,000 / Revised to £4,116,000 at SUPPS	£3,725,296
Total	£22,023,000	£5,166,000 / Revised to £5,366,000 at SUPPs	£4,870,916

## Outputs
Output statements	Individual Output Rating
(No. and statement)
Selected partner states have increased knowledge and skills to conduct Force Preparation of military and police capabilities for deployment on Peace Support Operations (PSO).	3
Selected partner states have increased knowledge on United Nations (UN) PSO doctrine and standards and, where applicable, International Humanitarian Law (IHL) and Protection of Civilians (PoC) frameworks, gender, and conduct and discipline.	3
Personnel deploying to UN and African Union (AU) missions have increased knowledge and skills on specific capabilities, as required by the UN and AU	3
The AU Commission (PSOD) has increased knowledge on PSO doctrine, policies and procedures.	3
The AU Commission is equipped with knowledge and skills which enable more capable PSO administrative functions, including in financial management.	2
AU PSOD and the AU’s Police Strategic Support Group (PSSG) have improved policing capacity and increased knowledge and skills to enable better performance and functionality.	3
Overall Rating of Output Delivery	3

## Outcomes
Outcome statement(s)
UK-partnered African Troop and Police Contributing Countries (T/PCCs) are better able to deploy and sustain quality contributions to PSO’s in Africa – either UN, AU, or those delivered by regional African bodies.
The AU is better able to establish, manage, support, oversee, plan, and generate forces for PSO’s
Outcome Assessment	There is sufficient evidence of progress against programme outputs and outcomes that the programme can be considered as broadly on track. But it is unlikely that all targets will be fully achieved within the current programme lifespan – largely due to external factors outside programme (or HMG) ability to control, most notably partner capacity. Broadly, APSO, through the British Peace Support Team (Africa) (BPST(A)), is almost certainly providing some of the right support, in some of the right ways, to most of the right partners, and achieving most of the desired effects, and key T/PCC are better able to deploy and sustain PSO contributions. / There is evidence that African partners, and other international actors continue to engage seriously and constructively with BPST(A), and that BPST(A) support is well-received and generating some sustainable effect, although in most cases ensuring the long-term sustainability of those impacts will take longer than the three (now four) year lifespan of the current programme (a lesson from the UK Armed Forces’ own capability development). British Peace Support Team (Africa) (BPST(A)) support is almost certainly helping to improve the capacity and capability of African troop and police contributing countries to prepare and train personnel for deployment on PSO. But determining the extent to which that translates into improved mission performance remains difficult to determine (an issue common to developing measurement of effect for military operations).
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		Amber

## Summary of Programme Performance
Year	2021/22		2022/23		2023/24
	Output	Outcome	Output	Outcome	Output	Outcome
Programme Rating	3	3	n/a	Red	3	Amber
Risk Rating	Amber	Amber	Amber	Amber	Amber	Amber
Notes: Output/Outcome score

## What Support Did the UK Provide in FY 23/24?

The APSO programme aims to enhance the ability of African countries and institutions to make effective contributions to UN or African Union (AU) peace support operations (PSO), working both “bottom up” with African countries deploying or preparing to deploy to missions and “top down” to build the capability of the AU to manage PSO. It does this through the following means:

Personnel: APSO is delivered primarily by the British Peace Support Team (Africa) (BPST(A)). Headquartered in Nairobi, BPST(A) comprises of 18 UK military staff, one MOD civilian, two UK-based deployed civilian experts, three civilian advisers appointed in country, and 13 country-based support staff.

Funding: Final spend was £4,845,244 (£1,145,619 ODA, and £3,699,635 non-ODA) against an original budget of £5,166,000. Of this, £2,833,346 was spent on activity, and £2,011,898 on operating costs, allowances, real life support, and other staff costs (e.g. country-based staff).

Activity: BPST(A) delivered or enabled 94 training events and courses in 23/24, to some 2637 African military, police, and civilian personnel. Training was delivered by UK military Short Term Training teams (STTT), external contractors, African training institutions, and deployed civilian experts (DCEs), as well by BPST(A) staff themselves.

## Key Results for FY 23/24

UK support assisted the Ghanaian army in developing a new counter-explosive ordnance (C-EO) capability - 851 Explosive Ordnance Disposal (EOD) Regiment. The Regiment has reached a sufficient standard that Ghana was able to pledge a company deployment to future UN PSO at the December 2023 UN peacekeeping ministerial conference. Only two other African nations can match this capability, and once deployed it will help service a critical UN shortfall. Creation of the Regiment has also enabled Ghana to strengthen responses to terrorist threats on its northern border and spillover of violent instability from the Sahel – thereby indirectly contributing to the outcomes of the ISF West Africa Stability Programme (WASP).

BPST(A) continued to strengthen collaboration with the UN. It has now received UN recognition to deliver the UN Military Peacekeeping Intelligence (MPKI) course in Africa, the culmination of two years’ work with the UN Integrated Training Services (ITS). BPST(A) also helped UN ITS to pilot a new Force Protection (FP) course, covering the fundamentals of FP, including countering improvised explosive devices, and base design. With BPST(A) support, the Humanitarian Peace Support School (HPSS) in Nairobi has secured UN ITS accreditation for several of its courses. The UN has also asked BPST(A) to co-sponsor the first UN Senior Mission Leader Course to be held in sub-Saharan Africa for 17 years.

FY23/24 saw a further strengthening of collaboration with the AU Peace Support Operations Division (PSOD), and an increase in PSOD requests for UK help to develop PSO-specific policies and processes. Outputs include:

  - A draft policy on gender mainstreaming in PSO (which provides a framework for the systematic integration of gender perspectives in current and future AU-led PSO).

  - An AU policy on countering improvised explosive devices (C-IED - since adopted by the AU’s Stabilized Technical Committee on Defence, Safety and Security) which provides a benchmark for development of common African approaches to countering IED threats.

  - Policies on the Protection of Civilians in PSO, the Selection and Screening of Personnel for deployment on PSO, and a Strategic Framework for Compliance and Accountability of PSO, all of which were agreed adopted at the 37th AU Summit in February 2024.

  - Development of an AU train-the-trainer course intended to promote use of an AU-endorsed standardised pre-deployment training package, and pilot delivery to an audience drawn from the Southern African Development Community (SADC) and its member states.

FY23/24 saw BPST(A) coalesce its civilian expertise into a combined ‘Human Security Team’, which led to the development of a more integrated approach to training, with activity that hitherto had been offered in isolation (specifically international humanitarian law and international human rights law, protection of civilians, gender, women peace and security, and civil-military cooperation) consolidated to create a more integrated ‘human security in PSO’ training package. This concept was piloted in Malawi (July 23) and Ghana (September 23). Ghana’s Army Peace Operations Training School subsequently requested that a Human Security in PSO course be formally integrated as a recurring fixture of its training syllabus.

BPST(A) continued to help African partners deliver pre-deployment training (PDT) and specialist training to contingents deploying on UN and AU missions This included Uganda (ATMIS), Malawi (MONUSCO), Zambia, (MINUSCA), Kenya (ATMIS), and Liberia (MINUSMA).

Having received BPST(A) help to develop the capability to teach officers how to investigate sexual and gender-based violence (SGBV) whilst deployed on PSO, the Zambian police service took the BPST(A) material and developed its own national SGBV investigation manual. During the reporting year, BPST(A) worked with the Zambian police adapt its training material to the Zambian context, and using previously trained trainers, helped train an additional cadre of instructors for a national programme. With funding from Canada and support from the UN Development Programme, the Zambian police has since delivered SGBV investigation training to over 700 police officers nationally.

FY23/24 also saw collaboration with Interpol, which is seeking BPST(A) help to develop its own courses to address sexual and gender-based violence (SGBV) and sexual exploitation and abuse (SEA).

## Key Lessons:

The assumptions underpinning the programme remain sound and BPST(A) has made progress in delivering against programme outcomes. But fully achieving those outcomes is dependent on external factors and contextual developments outside programme (or HMG) ability to control. Successor programme design, whilst striving to be ambitious, should be realistic about what APSO can expect to achieve – in isolation and with wider HMG and other donors – ensuring that it is measuring performance against outcomes and targets which are within programme (or wider HMG) capacity to influence.

BPST(A) is a recognised and respected brand – in Africa, within the UN, and amongst Western partners. There is good evidence of coordination and deconfliction with other donors (the US and UN especially), with pockets of close collaboration. Given the scale of Africa’s peacekeeping needs, future programming should be more collaborative by design. Programme documentation should aim to better situate UK efforts within a wider international context to provide a clearer indication of synergies and dependencies. There is significant opportunity for HMG to both provide niche, catalytic contributions to support other delivery partners, and to leverage the resources and activities of others in support of common objectives.

Sustainability remains a challenge (especially in the context of a three-year programme). There is clear evidence that BPST(A) continues to adopt a pragmatic approach towards sustainability, adapting its delivery (e.g. with a continuing evolution from training delivery to the mentoring of previously trained trainers and institutional support) whilst doing so at a pace that reflects partner nation capacity. But there remains a need to more clearly define sustainability objectives at both the project and programme level and ensure that they objectives are realistic - reflecting both the reality of what the programme is resourced to deliver, and lessons that UK Defence has learnt from its own capability development.

There is also a tension between the intent to enable African partners to be self-sustaining, and the benefits to HMG access and influence of preserving a role for BPST(A) / Defence in providing continued support to African troop and police contributing countries. Most African partners will continue to seek and accept offers of external support. Reductions / removal of UK support will create a vacuum that others – both allies and strategic competitors – would seek to fill at HMG expense. Development of a successor programme should seek to explicitly address this tension and explore options and timelines for a future transition of funding - where appropriate - from ISF to departmental baselines to enable an ISF exit strategy that does not harm wider HMG equities.

As noted in last year’s annual review, the nature of PSOs in Africa is changing; to maintain relevance and maximise strategic utility BPST(A) will need to increase its civilian component (policing/International Humanitarian Law/gender). There is evidence of a plan to do so and strengthen the ‘human security’ offer. Implementation will require APSO Board level direction on priorities, trade-offs and compensatory reductions elsewhere in the programme unless additional resource can be secured to fund it.

APSO/BPST(A) creates significant opportunities for HMG by way of access and influence, which are almost certainly not being fully exploited. It is assumed that APSO/BPST(A) activity is integrated within Defence Section country plans, and MOD regional strategies. But there remains a need to improve wider awareness of the programme to maximise the benefits to HMG and strengthen policy/programming cohesion – a recurring theme in APSO annual reviews.

## Key Recommendations for FY 23/24:

Integration: There remains both requirement and scope to improve integration with wider HMG stakeholders to maximise and leverage the political access and influence that APSO generates. In order to aid understanding of how this might be achieved, the APSO Programme Manager should undertake a review of APSO stakeholders and develop an engagement plan that articulates their interest, how the programme will interact with them, for what purpose, and through what means.

Monitoring, Evaluation and Learning (MEL): The APSO Programme Manager should introduce a process to review regularly both the Theory of Change and Results Framework to ensure they remain relevant, up-to-date, and reflect lessons. Design of a successor programme should (utilising specialist support as appropriate) review and develop the metrics and indicators by which success is measured and incorporate them into a refreshed Results Framework and MEL plan, which should be endorsed by the programme board prior to programme delivery commencing.

Risk: The APSO Programme Manager should develop a programme risk register, and formalise processes to track, manage and escalate programme risks.

Sustainability: There remains a requirement to develop a more coherent and realistic understanding of what is meant by sustainable. Design of an APSO successor programme should a) include clear articulation of what is meant by commonly used terms, b) through a refreshed Results Framework provide clear metrics at the programme level of what sustainable outcomes look like, and c) at the project level better articulate the specific end-state that APSO is seeking to achieve with each partner, and how it will be sustained.