Annual Review (23/24)
# A. Summary Sheet
Programme Title	CSSF East Africa Borderlands Programme
Country and Region	Kenya, Somalia, Ethiopia, Mozambique, Tanzania
Programme ID	C-AFR-0042	IATI Unique ID	CSSF-03-000042
Start date	April 2022	End date	March 2026
HMG Partners	Foreign, Commonwealth & Development Office (FCDO), Ministry of Defence (MoD)
	Total overall Programme Allocation	Allocation FY 2023/24	Spend FY 2023/2
ODA	£23.25m	£4,935,000	£4,936,142
Non-ODA	£2.25m	£557,000	£639,273
Total	£25.50m	£5,492,000	£5,575,415

## Outputs
Output statements	Individual Output Rating
Locally informed and gender sensitive understanding of the context, conflict dynamics, drivers of instability and violence in borderland areas promoted to relevant actors/stakeholders.	3
Targeted formal and informal peace and security structures and actors have the tools and capabilities jointly identified as needed to make them more effective, trusted, inclusive, and able to deliver long-term stability and advance gender equality.	4
Locally designed, piloted, and scaled grant initiatives in vulnerable target areas aimed at boosting social cohesion and promoting gender equality to mitigate drivers of conflict, instability, and violent extremism.	3
Overall Rating of Output Delivery	3

## Outcomes
Outcome statement(s)
Key stakeholders adopt more effective, evidence-driven policies and practices supporting peace, stability, gender equality and social inclusion, underpinned by locally informed understanding of conflict, gender, diversity, and social inclusion dynamics in target areas.
Formal and informal peace and security structures and actors operating in the borderland communities are (more) inclusive, cooperative, effective, and trusted, to deliver long-term stability and advance gender equality.
Target communities, households, and individuals more resilient to Violent Extremism (VE) influence (through gender-equitable, and socially inclusive, local approaches to strengthen social cohesion and build resilience).
Outcome Assessment	The programme is broadly on track to achieve its outcomes but there is some uncertainty that all targets will be met. Most progress across all three Outcomes was being made by the Deris Wanaag project, with evidence of stakeholders being influenced by the project’s research and evidence, and grantees taking onboard evidence and lessons relating to Gender Equality and Social Inclusion (GESI). The Daraja La Amani / Pontes de Paz has made relatively less progress towards the Outcomes, largely owing to the delay getting project approval from Tanzanian authorities, but also because of a weak granting process and poor quality of some of the grants. There was more success under Outcome 2, but this strand of activity was affected by the issues in other components.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		High

## Summary of Programme Performance
Year	2021/22		2022/23		2023/24
	Output	Outcome	Output	Outcome	Output	Outcome
Programme Rating	3	3	3	N/A	3	Amber
Risk Rating	Medium	Medium	High	N/A		High

## What Support Did the UK Provide in FY 23/24?
- Deris Wanaag, Kenya-Somalia-Ethiopia (KSE) Borderlands Project.
- Daraja La Amani / Pontes de Paz, Mozambique-Tanzania (MT) Borderlands Project.
- Collective Resilience Against Extremism (CREATE) Project which sought to reduce drivers, enablers and narratives of Violent Extremism (VE) by providing mentorship, referrals and psychosocial support to understand and assist individuals at risk of radicalisation or recruitment, and building the capacity of non-state actors, and state actors on PVE (Preventing Violent Extremism).
- Counter al-Shabaab Strat-Comms Advisor (MOD).
- Stabilisation Advisor to the CITSO (Counter Insurgency, Counter Terrorism, Stabilisation Operations Centre).
## Key Results for FY 23/24
- Establishment of the Deris Wanaag Spotlight analysis series as a valued source of information and insight into a range of conflict, security and development dynamics in the KSE borderlands for a wide range of programme stakeholders.
- A series of events during 2023 and early 2024 bringing together senior representatives (politicians and officials) from Kenya, Somalia and Ethiopia to discuss security in the borderlands, including the establishment of a Borderlands Advisory Group to facilitate quarterly KSE engagement and oversight of the programme (three meetings of the BAG happened during the period under review).
- Two cross-border security coordination meetings at Khorof-Harar and Diif in November and December 2023 involving 30 security officials from Kenya and Somalia, leading to the identification of capacity building requirements for security personnel, suggestions for community engagement modalities, and a review of information sharing mechanisms and practices.
- In response to devastating floods in the border areas, the Deris Wanaag project supported more than 22,000 of the most vulnerable and marginalised cross-border communities through Rural Agency for Community Development and Assistance (RACIDA).
- The signing of a Memorandum of Understanding (MoU) with the Government of Tanzania Ministry of Home Affairs was a major success given that other donors/agencies have not succeeded in doing this.

## Key Lessons:
- Links between the strands of activity under each outcome could be improved. For example, under Outcome 3, Mozambique grantee Helpcode identified harmful state practices interviewing survivors of conflict-related sexual violence to ensure they are not combatants following their release from captivity. This insight could be used to improve the practices of state security actors, under Outcome 2, but during the period under review the link had not been made.
- Coordination meetings between grantees and Deris Wanaag implementing partners during the period under review were valued by grantees as an opportunity to learn lessons from working on a complex, fragile region.
- Training, particularly on specialist functions like financial reporting, is essential for grantees to be able to meet reporting requirements adequately.

## Key Recommendations for FY 24/25:
There is room to streamline and improve grantee coordination in reporting and training. Several grantees of the Deris Wanaag project described the reporting process as duplicative and this is impacting the quality of their reporting.

Management of granting under the Daraja La Amani / Pontes de Paz project needs to be improved: it is too inefficient and burdensome to be effective, grants need to be longer to demonstrate effects that the programme can learn from, and initial progress needs to be capitalised on, not abandoned (as was the case with one grant), otherwise there is a risk of doing harm to beneficiaries.

Stronger linkages are needed between granting activities under Outcome 3 and research activities under Outcome 1. Research and analysis should be playing a greater role shaping grant making and new areas of activity, and the Community Resilience Index (launched in February 2024) should be used to help measure the effect of grants and generate evidence to feed into research and analysis.

Significant momentum on cross border activities through the Daraja La Amani / Pontes de Paz project is required for FY24/25, now that the project has permission to operate in Tanzania. A cross-border platform was in the process of being established during the review period, but at end Q1 FY24/5 there was limited evidence of the focus and momentum required by the project to make significant progress in this regard.

A re-set of project management culture and processes is needed to improve efficiency, communications and trust between the programme team and Implementing Partners (IPs), especially on the Daraja La Amani / Pontes de Paz project. This is already being considered by the programme team. The roles of the programme team and the Deris Wanaag project team could be clarified through a ‘ways of working’ ToR to avoid duplication of effort.

The Programme results framework and the associated IP reporting process needs to be comprehensively reviewed and revised to make the RF more fit for purpose as a tool the team can use to monitor progress, with an efficient reporting process that keeps the RF up to date. As part of this, the theory of change should be revised to ensure it reflects a realistic approach to the borderlands challenges in KSE and M-T borders.