CSSF Annual Review/Programme Completion Review (23/24)

A. Summary Sheet
NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	West Africa Stability Programme
Programme ID	C-AFR-0040
Country and Region	Ghana, Burkina Faso
IATI Unique ID	CSSF-03-000045
HMG Partners / (Lead in bold)	FCDO
Total Budget	ODA: £7, 500, 000 (indicative)	Non-ODA: £2,500,000 (indicative)
Budget this FY	ODA: £ 755,000.00	Non-ODA: £ 466,000.00
Spend this FY	ODA: £839,422	Non-ODA: £203,683
Time Frame	Start Date: September 2023	End Date: 31 March 2024

Outputs	Individual Output Rating
Increased cohesion in local communities and development of initiatives to sustainably address local drivers of conflict	3
Multi-stakeholder consultation and decision-making spaces at the local and cross-border levels are established.	4
Enhanced coordination among state and non-state actors to address insecurity, including ahead of the 2024 Presidential election	3
Reinforcing regionally led security initiatives	1
Overall Rating of Output Delivery	3

Outcome Assessment	WASP did not have a complete results framework in place by the time of the review, so this assessment is based on general direction of the programme against its overarching aims and its contributions to overarching UK and ISF objectives. The Annual Review team deduced programme outputs, indicators and milestones from an objective analysis of the ambition implied in the programme document, programme activities and overarching ISF objectives.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		Medium

Summary of Programme Performance
Year	2020/21	2021/22	2022/23
Programme Rating
Risk Rating	-	-

Note: This was the first year of the Programme having emerged from the Upstream Threats Programme in Q1. The Programme remained relevant in its respective policy contexts and in relation to the problems it aimed to address.

A1. UK Support Offered in FY 2023/24

WASP built on the UK’s existing work in the region – including through the former Upstream Programme – focusing on the following areas, which contributed to needs identified by UK Ministers:

- Reinforcing African-led Initiatives: support to partner-country security and crisis management, and financial and technical advice to the Accra Initiative[1] and the International Counter Terrorism Academy (AILCT).[2]
  [1] Coalition of West African member states and Sahelian observers. Primarily an intelligence sharing forum to build security capacity, tackle the expansion of extremist activities, address transnational organised crime and violent extremism in member states’ border areas.
  [2] International CT Academy - a Franco-Ivorian Academy strengthening capabilities of Regional States in the fight against terrorism.
- Enhancing coordination: reinforcing UK leadership in the region through bilateral projects and regional mechanisms such as Coastal States Stability Mechanism (CSSM)[3] and possibly the Atlantic Corridor[4] when conditions of UK involvement are met.
  [3] Coastal States Stability Mechanism, developed jointly by the US and German Governments and implemented by IOM, aims to strengthen state presence in areas most at risk of VEO attacks and enhance relations with communities.
  [4] German and Danish funded programme delivered by UNDP. Focussed on preventing the spread of violent extremism in the border regions of five countries through strengthening national PVE capacities and coordination mechanisms, and developing national PVE strategies.
- Leveraging regional influence: providing a programmatic tool for diplomatic and defence engagement with West African peace and security architecture e.g. Economic Community of West African States (ECOWAS).
- Addressing causes of conflict: continuing community-based peacebuilding programmes in Ghana and flexing programming to gaps as they are identified elsewhere.

The programme continued the following activity in 2023/24 that was previously funded under the Upstream Threats programme:

The cross-border ‘Supporting Agro-pastoralism to reinforce Social Cohesion’ (SAPSOC) programme implemented by Acting for Life. This programme facilitates dialogue in the agro-pastoral sector to reinforce social cohesion in the cross-border territories of Ghana and Burkina Faso, focussing on minorities who are targeted for recruitment by Violent Extremist Organisations (VEO)s.

STAR Ghana, a multi-donor programme that supports community-driven initiatives for peace and security including community-police engagement; working with government and non-government stakeholders to implement the Roadmap for Peace and Security in Northern Ghana; and working with excluded groups to facilitate engagement in peacebuilding processes.

Support to the Accra Initiative (AI): This includes a technical adviser for the AI; a potential international conference to convene support to the AI; work with Multinational Joint Task Force (MNJTF) HQ to support Ghana’s Armed Forces; a joint operational planning course; Geo intelligence capability; and a research project.[5]
[5] Coalition of West African member states and Sahelian observers. Primarily an intelligence sharing forum to build security capacity, tackle the expansion of extremist activities, address transnational organised crime and violent extremism in member states’ border areas.

A2. Key Results

- There were encouraging signs from community dialogue forums (informed debates) held in Northern Ghana to improve relations between livestock herders and refugees crossing the border from Burkina Faso into Ghana amid rising insecurity across the Sahel.
- Establishing Community Watch Relays (CWRs) to identify tensions quickly allowed partners to intervene and successfully reduced recourse to conflict in at least 49 situations, demonstrating the potential for realtime monitoring at the local level, recorded and communicated to the appropriate actors, allows measures to be taken before conflict occurs.
- UK support to the AI created foundations on which to build further by bringing together a network of donors and other actors working in the stabilisation and peace space.
- Dialogues of State and Non-State actors on Security Coordination in Northern Ghana were held. These have significantly improved relationships between key actors in the bid to promote peace and conflict resolution in northern Ghana.
- Significant progress has been made in the development of a Northern Ghana Peace Index. The Index will greatly enhance continuous monitoring of the peace and security situation in northern Ghana and stakeholders’ access to such information, incentivise community actions to promote peace and security in their areas and provide a one-stop shop for information on peace and security in northern Ghana.

A3. Key Lessons

1. WASP requires better systems for recording and storing information to provide greater clarity on activity and ensure greater accountability. This will assist with risk management and better monitoring of programme activity.
2. It is essential that outputs and a results framework are created as soon as possible so that the programme can shape and compliment the activities of each implementing partner.
3. Improved internal coordination is essential to the success and the delivery of the programme. To facilitate this, clear roles and responsibilities must be established throughout the full phase of the programme cycle.
4. Where there is limited programme management experience at Post, increased advice and support from the portfolio team is required, otherwise we risk increasing pressure across the system, which implementing partners feel the effects of in terms of delivery.
5. Locally owned and locally driven processes and dialogues in northern Ghana have ensured buy in from key state and non-state stakeholders.
6. A conflict sensitive approach that recognises grievances and structural factors driving insecurity is proving effective. Activities that involve building community engagement and collectively discussing drivers of insecurity have led to initiatives, such as the Community Watch Relay and Fulbe Manual, that build cohesion and address some of the local drivers of conflict and structural instability, rather than utilising an securitised response to a VEO threat. WASP should seek to amplify this preventative approach to stabilisation.
7. Access to opportunities for communities provides a practical approach and alternative options to addressing issues of economic empowerment. Vulnerable communities in northern Ghana - particulary youth - are often drawn into VEOs due lack of opportunities or access to livelihoods. Activities such as the provision of fenced gardens to 40 young people in the Bole districts supported them to exit illegal small-scale mining under very precarious conditions that predispose them to radicalisation and violent extremism.
8. Quick reactive responses to large, complex issues may offer some short-term fixes, however this approach will inevitably diminish the programme’s success and ability to bring about genuine catalytic change in the long-term. This then becomes a compound problem with over each new year of the programme.
9. Engagement with the Accra Initiative highlights that working in complex environments and challenging political situations requires immense investment of time and energy in building relationships and trust. Programmes therefore need to factor this into planning alongside being realistic about what can be achieved within a short timeframe considering the lengthy investment needed to unlock progress.

A4. Key Recommendations

1. Clearer delineation of roles and responsibilities across the programme, across both British High Commission (BHC) Accra and London.
2. Develop a clear results framework for WASP, and review outcomes and outputs suggested by the Annual Review team.
3. Clearer communication with implementing partners about WASP (its aims, scope and objectives) and CSSF/ISF to improve understanding, and regular evaluation to ensure value for money.
4. Greater focus on vulnerable groups (women and youth). Continue programme activity that supports women’s economic empowerment and involvement in sustaining peace. Youth inclusion in the community and employment should also be an important consideration to avoid VEO recruitment. This supports FCDO analysis that was conducted on conflict sensitivity and stability in the region (Ghana Stability Audit).
5. Update GESI analysis and scoring of all projects (as is mandatory for ISF programming).
6. Increase engagement with other FCDO programme teams (and conducting joint engagements) will help to identify areas of complementarity and synergy and enable a more cumulative impact of programmes in the region.
7. Increase coordination with multilaterals to enhance impact of capability-building and avoid overlaps, particularly for programmes on border management or VEO spillover in the Northern regions of the coastal States.
8. Capture lessons learnt, and possible ways to reflect (and capture) wider and unintended effects from the year’s activities.