CSSF Annual Review/Programme Completion Review (23/24)
# A. Summary Sheet
Programme Title	Colombia Peace and Stabilisation Programme (CPSP)
Country and Region	Colombia, Americas
Programme ID	C - AMS - 0002	IATI Unique ID	CSSF-04-000002
Start date	1 April 2022	End date	31 March 2025
HMG Partners / (Lead department in bold)	Foreign, Commonwealth and Development Office (FCDO) / Ministry of Defence
	Total overall Programme Allocation (e.g. 3 years) / From FY 2015/16 until FY 2023/24	Allocation FY2023/24	Spend FY 2023/24
ODA	£77,600,000	£3,600,000	£3,590,235
Non-ODA	0	0	0
Total	£77,600,000	£3,600,000	£3,590,235

## Outputs
Output statements	Individual Output Rating
Support the full and inclusive implementation of the peace agreement, ensuring its success and sustainability	4
Build the capacity and capability of the Colombian State, civil society and communities to tackle threats to peace, security, environment and human rights.	4
Overall Rating of Output Delivery	4

## Outcomes
Outcome statement(s)
The Colombian state is committed, and better able, to implement the peace agreement, strengthen its presence and service delivery in conflict-affected areas and tackle threats and spoilers to long-term peace and security, with active participation from civil society and communities.
Outcome Assessment	Since the 2016 Peace Agreement and the inception of ISF/CSSF programming on peace in Colombia, the programme has clearly contributed to the development and the strengthening of Colombian state architecture, institutions, and tools to implement the peace agreement, strengthen its presence, and deliver services to conflict-affected areas. This is evident in the presence of: / The development and operationalisation of the JEP (the Special Jurisdiction for Peace) and a transitional justice system that is fair and contributing to long-term understanding and burden-sharing. / The development of UNIPEP, the Colombian Police’s Peacebuilding Unit. / Institutions that further increase the population’s access to truth including the UBPD (the Unit for the Search for Persons Deemed as Missing). / The Office of the High Commissioner for Peace. / In 2023/24, the programme has continued to build the capacity of these institutions to improve their ability to implement the peace agreement, improve its presence and service delivery, and tackler threats and long-term spoilers to peace. / In 2023/24, there has been evidence to suggest a worsening in several important indicators of conflict dynamics in Colombia and the region. For example: / The number of kidnappings, massacres, forced recruitment and hostages has continued to climb since 2016 with a peak in 2023 (ACAPS). According to National Police data, there was a significant increase in both reported kidnappings (56%) and extortions (111%) across the country in 2023 which rose to levels not seen since before the 2016 peace agreement. / Violence levels have stayed fairly consistent in geographical hotspots, but they have increased in the Amazon regions showing a geographical spread in the presence, or at least the impacts, of armed groups. / This trend is reflected in worsening public perception of security, compared to previous years: 63% of respondents stated they felt unsafe in their municipality in 2023, compared to 58% in 2022. Experts point to the increase in clashes between armed groups as a primary reason for humanitarian risks to civilians. / Regarding the programme’s outcome milestones and indicators, there are clear specific examples of where the state is more committed, more able, and is delivering a level of services in some conflict affected areas. The development of operational state architecture clearly demonstrates an increase in capacity and willingness for implementation. However, considering some worrying bigger picture trends: We assess the outcome progress at a Green/Amber level, for reasons that are outside of the direct control of this programme.
Overall Outcome Progress Rating:		Green/Amber
Overall Risk Rating:		Medium

## Summary of Programme Performance
Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c		2021/22		2022/23		2023/24
Programme Rating	A	A	A	A	A+	A	A	4	Green	4	Green	4	Green	4	Green/ / Ambar
Risk Rating	Medium	Medium		Medium		Medium		Medium-Low		Medium-Low		Medium-Low		Medium
Note: Output/Outcome score

## What Support Did the UK Provide in FY 23/24?

The ISF Colombia Peace and Stabilisation Programme (CPSP) supports Colombia's efforts to achieve long-term peace by implementing the peace agreement with the Revolutionary Armed Forces of Colombia (FARC-EP) and tackling the underlying causes of conflict and instability. Over the past financial year, the programme provided:

Targeted, catalytic support to Colombian institutions tasked with implementing the peace agreement. Including:

Support to the Ministry of Defence to open pathways for state forces to participate in the Special Jurisdiction for Peace (JEP) and therefore the truth and transitional justice process (UNDP).

Innovations through the Colombian Police’s Peacebuilding Unit (UNIPEP), to improve state presence in contested areas, build community-state relations and direct training on ‘Peace Pedagogy and Destigmatisation’ (UNDP, IOM).

Support to the Interior Ministry on human rights, protection of civilians and “safety guarantee tables” (UNDP).

Support to the strategic planning and milestone development for the delivery of the recommendations to the government from the Truth Commission (IOM).

Contributions and technical expertise to the UN Multi-Partner Trust Fund (MPTF) for Colombia to fund FARC reintegration, support to victims, and rural development for stabilisation.

Strengthening gender mainstreaming across implementation of the peace accords, and support to the Colombian Government to develop their first ever National Action Plan on Women, Peace and Security (CIASE).

Strategic negotiations support to the Office of the High Commission for Peace, including a strategy retreat (InterMediate).

Enhancing the role, and the understanding, of congresspeople in the peace process at the local level (Fundación Ideas para la Paz).

Support to the UN High Commissioner for Human Rights to (UNOHCHR) to enhance victim’s access to truth, justice and reparation through transitional justice systems and monitoring the human rights situation in Colombia.

Support to the Organisation of the American States Monitoring Mission (OAS-MAPP) to monitor conflict dynamics, supporting local authorities, and providing recommendations to the Colombia Government in the regions most affected by the conflict.

Environmental focused work in conflict affected areas including contributing to the UK’s Sustainable Forest Territories programme (TEFOS) and support to entrepreneurships focussed on peacebuilding in the Amazon (COMPAZ).

Delivery of a refreshed Joint Analysis on Conflict and Stability (JACS) to inform the UK’s approach to peace in Colombia from strategic, policy and programming perspective (UK Office of Conflict, Stabilisation and Mediation).

Construction of diagnostic documents that would feed into National Government policies on social investment, public policies, and territorial transformation in areas of interest for peace (INDEPAZ – Instituto de Estudios para el Desarrollo y la Paz).

## Key Results for FY 23/24

Through targeted, catalytic projects, the programme played a key role in:

The continued implementation of and monitoring of the 2016 peace agreement with the FARC, notably i) the development of the government's new National Development Plan, which sets budgets and legal frameworks on peace and is more actively incorporating milestones and recommendations from the Truth Commission in their planning; ii) creating spaces for reconciliation through dialogue and recognition of responsibilities between victims and perpetrators, and iii) increased role and understanding of congresspeople in the implementation of the peace agreement at a local level.

Ensuring that there was increased state (or multilateral) presence in conflict-affected territories through support to the Colombia Police’s Peacebuilding Unit and both UN and OAS presence and monitoring.

High-level Government institutions and their teams were better prepared (strategically and tactically) for peace negotiations. UK projects supported the government to design and communicate the framework for a peace process that included ten distinct and diverse armed groups. The programme also supported the Colombian Government to formulate a territorial transformation policy as a component of the peace negotiations with the EMC-FARC-EP for the first time.

The Special Jurisdiction for the Peace (JEP)’s work to achieve transitional justice, including i) the opening of ‘Case 11’ on sexual and gender-based violence and to advance the resolution phase of ‘Case 02’ on the environmental impact of the conflict on indigenous communities. These emblematic cases will ensure victim’s participation and access to justice. In the process, 47,952 female victims received support, including psychological and emotional recovery. The programme also built trust and guarantees for 366 public force defendants to participate in the JEP, alongside specific work on disappearances and legal defence.

After 13 years, the Government of Colombia committed to developing their first National Action Plan for UN Resolution 1325 on Women, Peace and Security. UK support ensured the mobilisation and inclusion of more than 100 indigenous women in the process, through input gathering, consultative sessions and review of documents.

Strengthening Human Rights architecture including i) developing the Ministry of Interior’s public policies on human rights and their ‘mesas de garantias’ and ii) the monitoring and reporting of threats, violations and assassinations of Human Rights Defenders.

The development of Colombian legal frameworks on tackling deforestation that launched investigations that lead towards the cancellation of land titles in the Amazon for failure to comply with environmental and forest protection regulations. This is the first such process in 30 years.

## Key Lessons:

The region has interconnected conflict and crime dynamics. Highly securitised responses in one country can create a ‘balloon effect’ whereby activities are push into neighbouring countries (Ecuador, Peru, Venezuela) generating regional instability.

Armed groups’ have become increasingly driven by criminal interests, which has shaped the patterns of violence. Armed groups are no longer seeking to overthrow the state and exercise control at national level. Criminal interests have increasingly pervaded armed groups’ modus operandi which has changed typologies of violence at subnational levels.

The geographic hotspots of violence have remained consistent. However, violence has spread into Amazon regions, worsening environmental degradation.

Reputationally, as penholder for Colombia on the UN Security Council, there is a need for the UK to have a clear vision for programmatic support to the peace process that is sustained and consistent. This could continue through the Integrated Security Fund or be transitioned onto departmental (FCDO) baselines.

The Colombian conflict context should continue to generate lessons for our work in conflict zones across the world. For example, Colombia hosted the first forum on transitional justice that included the environment as a victim of armed crime, setting a benchmark for transitional justice systems across the world.

## Key Recommendations for FY 24/25:

Strategic Review: Using the refreshed Joint Analysis on Conflict and Stability (JACS), a strategic review of programme priorities and focus should be undertaken. Ensuring that work is proportionate, aligns with ISF values, and focuses on the UK’s comparative advantages in Colombia. This should also consider if some specific thematic focuses would be better placed on departmental baselines (e.g. negotiations and multilateral contributions).

Regional dynamics: Given worsening conflict dynamics in the region, the programme / portfolio should consider a wider, more regional view of the conflict dynamics, and mitigate the risks of displacing instability problems into neighbouring countries (the balloon effect).

Human and Climate Security: The JACS highlights climate security (including illicit economies) and human security as entry points to focus UK thinking and intervention. Working with other programming levers (CIEP, TEFOS, new environmental security work), the UK should consider how it focuses on these identified themes.

Recalibrate milestones and targets: Given that the programme had already surpassed several of its 2025 targets in 2023 and 2024. Within this programme year, the programme team should revisit the Results Framework to set a series of ambitious goals for the final year of programming. For a successor programme, the output level indicators could be reconsidered.

Outcome Harvesting: Given the programme is in its final year, it would be valuable if implementing partners could undertake a process to consider multi-year outcomes and big picture contextual changes which could be attributable for the programme. The programme team should encourage this through their end of year reporting processes. There are still some knowledge gaps from implementing partners on how to report outcomes usefully, they should receive further guidance on outcome harvesting as a mechanism of reporting.

Programme management: The programme’s model of delivering smaller, catalytic projects comes with an administrative and capacity burden for teams. To continue the important grassroots work, the programme could consider adapting the contracting mechanism to ensure continued support to local partners whilst reducing the administrative burden. E.g. by developing an umbrella mechanism, where work is subcontracted to local partners by a single, lead implementing partner.

Exit planning: Given a year-on-year reduction in programme budget, the programme team and wider Embassy should prepare for a possibility of closure of certain projects. Exit planning should be undertook to i) understand and report the risks contextually and reputationally of closing projects, ii) scope options for other UK funding options in the region to transition or baseline projects, and iii) be honest and open with implementers, partners and beneficiaries, if risks to funding emerge.