CSSF Annual Review (23/24)
# A. Summary Sheet
Programme Title	CSSF Protective Security and Attack Response Programme (PSARP)
Country and Region	Global
Programme ID	C-CTP-0009	IATI Unique ID	CSSF-01-000015
Start Date	1 April 2022	End date	31 March 2025
HMG Partners / (Lead department in bold)	Home Office (HO)/Foreign, Commonwealth and Development Office (FCDO) [both HO and FCDO were joint Senior Responsible Owners of the CSSF PSARP]; Counter Terrorism Policing Head Quarters (CTPHQ) – primarily the International Protect and Prepare (IPP) team and its Joint Overseas Protect and Prepare (JOPP) team, but also SO15 through CTPLOs; Counter Terrorism Network (CTeN); Joint Emergency Service Interoperability Principles team (JESIP); MoD
	Total Overall Programme Allocation (over 3 years)	Allocation FY2023/24	Spend FY 2023/24
ODA	£6,756,792	£2,171,000	£2,287,646
Non-ODA	£764,517	£393,000	£321,749
Total	£7,521,309	£2,564,000	£2,609,395

## Outputs
Output Statements	Individual Output Rating
1.i. ACROSS EUROPE (PORTUGAL): Improved Portuguese police and gendarmerie ability to adapt and use assessment tools on risks around publicly accessible locations and vulnerable sites.	4
2.i. TANZANIA: Extent of protective security/awareness training delivered.	4
2.ii. INDONESIA: Indonesians better equipped to carry out more proactive security assessments of tourist locations.	3
2.iii. TUNISIA: Tunisians better equipped to maintain a consistent and effective approach to emergency response.	4
2.iv. PHILIPPINES: capabilities of first responders in Boracay and Palawan to respond to a terrorist attack improved.	3
2.v. KENYA: Kenyans better equipped to plan and run effective training and exercising of interoperability capabilities.	3
2.vi. MALDIVES: Maldives National Disaster Management Authority (NDMA) better equipped to develop multi-agency crisis response doctrine.	3
3.i. GENDER: All PSARP country activity is planned and delivered in ways which meaningfully reflect an understanding of the different needs and perspectives of women and men.	3
Overall Rating of Output Delivery	3

## Outcomes
Outcome Statements
Vulnerability to terrorist attacks reduced or mitigated in key locations.
Improved response to terrorist attacks, minimising loss of tourist life.
Outcome Assessment	The PSARP delivered a significant amount of national-level outcome advancement around protective security (including standards setting in law, standardised vulnerability assessment approaches, general awareness-raising etc.) and in attack response (including interoperability doctrine and training/exercises, first aid / first responder capabilities etc.). Nonetheless, both outcomes individually rated amber in FY 23/24. They were on track, but there were some doubts and evidence regarding whether outcome milestones/targets would be met by the end of the three-year programme. Most of these doubts related to events/situations beyond the UK’s control, including the economic means, staffing etc. of third country partners, and impact of external events (elections, national disasters etc.). Nonetheless, continued monitoring is recommended so that moderate risks to results in the third year of the three-year programme are managed.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		Moderate

## Summary of Programme Performance
Year	2021/22		2022/23		2023/24
	Output	Outcome	Output	Outcome	Output	Outcome
Programme Rating	Amber	Amber	3	Amber	3	Amber
Risk Rating	High	High	Moderate	Moderate	Moderate	Moderate
Notes: Both output and outcome scores for the PSARP were similar the first year of the three-year programme, the year before.

## What Support Did the UK Provide in FY 23/24?
- In Asia:
  - In Indonesia, prepared for the national Counter Terrorism (CT) protective security adviser cadre to increase in size so they can do more assessments in response to/as needed by the tourism industry. Delivered a workshop on security assessments with 10 Bali police. Trained over eight hundred Bali police officers in trauma first aid through trained trainers. Added Action Counters Terrorism (ACT) awareness training to private security guard training, for which the Bali police will be the accrediting authority. There were examples of Bali training being put into practice.
  - In the Philippines, many thousands of participants benefited from online training. Department of Health trainers started a trauma care first aid training across Palawan. Delivered Palawan first aid train-the-trainers course. Delivered an interoperability/immediate first aid training/workshop. Completed the final phase of ‘Trauma Care First Aid’ training in Palawan. With 44% of students female, supported the building of a cadre of sixteen trauma care first aid trainers capable of delivering better than basic-life-support (BLS) training to, among others, emergency responders and tourism sector frontliners in Palawan.
  - In Sri Lanka, provided CT security advice and guidance leading to the Tourism Development Authority signing off standards of minimum security in guest houses. Delivered CT awareness training to seventy-six hoteliers from Kandy and Negombo hotel associations.
  - In Thailand, a senior delegation from the National Institute of Emergency Medicine (NIEM) visited the UK and exchanged expertise and best practice on medical response to incidents, including exploring creation of Thailand’s own Hazardous Area Response Team (HART) capability. Delivered a ‘Protection of Tourism and Historical sites’ course. Delivered a multi-national ‘Crisis Response Conference’ aimed at developing understanding and encouraging discussion on Thailand’s response to major incidents, attended by representatives from over 40 Thai organisations and departments, as well as representatives from over twenty-five international diplomatic missions. Helped a multi-agency senior workshop on JESIP on the back of the conference.
  - In India, delivered a joint workshop with the CSSF CT Portfolio Maritime Security Strategic Engagement & Training (MSSET) programme.
- In Africa:
  - In Morocco, facilitated re-establishment of the twinning engagement between London Fire Brigade and Moroccan Civil Protection (CP) after a long gap, with the visit of Assistant Commissioner Pat Goulbourne. Delivered a joint workshop with the with the CSSF CT Portfolio MSSET programme.
  - In Tanzania, delivered JESIP and crisis communications management courses. Delivered a showcasing workshop with 31 Tanzanian Police Force (TPF) seniors. Delivered a familiarisation session on ACT awareness and Terrorist Incident First Response (TIFR) with twenty-one senior Tanzanian police force delegates (including five women) and a train-the-trainer course.
  - In the Maldives, supported an inward visit to the UK, after which the National Disaster Management Agency (NDMA) committed to develop multi-agency crisis response doctrine. Trained the NDMA with first responding agencies in Manchester and London. Supported women in security and policing. Increased CT awareness amongst frontline service providers through delivery of ACT awareness training to over two hundred members from the Maldives Transport and Contracting Company and Trans Maldivian Airways, the world’s largest seaplane operator who fly most tourists to resorts on their fleet.
  - In Tunisia, supported an inward visit leading to their decision to create a crisis management centre based on the UK’s Cabinet Office Briefing Rooms (COBR), with UK support on doctrine and formal structures. Delivered a three-week Counter Terrorism Protective Security Assessment (CTPSA) train-the-trainer package to a cadre of 12 Ministry of Interior (MoI) protective security specialists in Tunis. Scoped a tourist excursion ‘visa’ platform which should help Ministry of Tourism/MoI’s coordination and communication of tourist numbers and movements.
  - In Kenya, supported the Kenyan National Disaster Management Unit assuming responsibility for testing and exercising for organisational learning. Supported the National Counter Terrorism Centre (NCTC) in their delivery of ACT awareness training to 202 staff from eleven hotels in the Watamu and Malindi area of the North Coast, through four ACT awareness deliveries and two ACT operational deliveries. Distributed 70,000 Terrorist Incident First Response (TIFR) aide memoirs to the Kenyan Police Service (KPS) to use at Regional Training Centres (RTC) for use in their onward delivery of first response training. Facilitated delivery of JESIP, TIFR, and Terrorist Incident Command Response (TICR) training to 106 people, to support the expansion of the National Emergency and Disaster Network. Delivered the inaugural Training & Exercising Foundation Course (a new course developed by the IPP team) to twenty-one people representing a variety of departments involved in national exercising in Kenya. Delivered an interoperability/immediate first aid training workshop. Following the findings of the capability survey conducted at King Fahd Hospital, Lamu Island, delivered Basic Life Support and First Aid training jointly with US government counterparts to hospital staff and community health volunteers, totalling 120 people (of which sixty-nine were female).
  - In South Africa, delivered a ‘Show and Tell’ workshop to nineteen senior personnel from a variety of organisations in Western Cape. Delivered an interoperability/immediate first aid training workshop. Delivered the initial stage of interoperability train-the-trainer course to nineteen representatives (15 male and four female) from various emergency services.
- In Europe:
  - In Cyprus, delivered ACT awareness training and a train-the-trainer course.
  - In Greece, delivered an interoperability/immediate first aid training workshop. 106 individuals attended the workshop where the Hellenic Police and others presented their plans for managing an incident at an airport, with a split of eighty-five males and twenty-one females. Delivered a two-day JESIP training workshop, and a table-top exercise that allowed participants to practice what they had learned and discuss how this might be applicable in Greece. Delivered ACT awareness train-the-trainer course to thirty-one people from across the tourism industry in two locations. Attendees included hotels, water parks, restaurants, Sovereign Base Area police, British High Commission and Cyprus Civil Defence.
  - In Ireland, presented to approximately 25 Irish officials from the An Garda Siochana (AGS), Airport Police and Department of Justice.
  - In Portugal, trained the police and gendarmerie, plus mentors, in standardised risk assessment criteria, and worked on adapting these to their needs. Ministerial talks took place with a view to getting authorisation for a working group. Facilitated the fifth and final module, and the accompanying mentoring module, of the Counter Terrorism Protective Security Assessment (CTPSA) course to a cohort from the Portuguese Security Police (PSP) and the Guarda Nacional Republicana. Delivered four sessions of ACT awareness training to 143 members of the Association of Shopping Malls in Lisbon and Porto. Ministers, police and gendarmeries considered national roll-out, including across the Algarve where British nationals (BN) live and visit.
  - In Spain, joined up with travel industry contacts to deliver a CT awareness and staff vigilance session to approximately seventy attendees at the Jet2 roadshow in Tenerife.
  - In Turkey, delivered Counter Terrorism Protective Security Assessment (CTPSA) training and training of trainers. Delivered week two of the CTPSA course in Turkey to twelve students and five observers from the Turkish police.
- In the Middle East:
  - In the UAE, delivered ACT awareness training and train-the-trainer course and a refresher to nineteen people (including two women).
## Key Results for FY 23/24:
In the above locations, thanks to the above investments, third countries had:
  - better protective security capability (more skills) and/or capacity (greater numbers and ranges of staff, facilities, equipment etc.) in both the public and private sectors that can reduce risks faced by BN tourists in some tourist locations/facilities where terrorist threats might include attacks; and
  - better attack response capability (more skills) and/or capacity (greater numbers and ranges of staff, facilities, equipment etc.) in both the public and private sectors that can respond to terrorist attacks in locations/facilities where BN tourists go, reducing the risk of injury and/or loss of life.
The UK government gained the ability to get both quick access to the right people and quick and appropriate responses to UK government requests, should it need, at times of terrorist attack impacting on the UK homeland and UK interests, including BN tourists, overseas.
## Key Lessons:
- Greece used capabilities built by this programme to respond to wildfires, and there were other examples of the use of CT crisis response capabilities built by this programme to respond to non-CT disasters (e.g. road traffic accidents, earthquakes etc.). There is potential for CT attack response, or at least the crisis management part of it, to move away from CT and be delivered through broader development programming overseas.
- Qualitative updates, less bound by quantitative performance metrics that all too often count participants, can provide meaningful analysis (often more so than statistics) of how well or badly protective security and attack response investments overseas are reducing risk from terrorist threats faced by BN tourists overseas.
## Key Recommendations for FY 24/25:
- Maintain the use of the JOPP team’s scorecard for tracking capability and capacity development around protective security and attack response overseas. Remove duplication in the CSSF results framework (RFW) in such a way that liberates the RFW to re-focus on purely value for money and risk management of public funding allocated. In this way, operational management can return to the tried and tested means used institutionally by the IPP and JOPP teams worldwide, and the good governance of public funds, via the RFW, will be less time-consuming and more effective.
- Mainstream attack response investments into broader development programming overseas, only retaining those parts of attack response that are unique to terrorist attacks in the CSSF CT Portfolio. As disaster management and crisis response is already covered by non-CT support from the UK overseas (covering a wide range of incidents where loss of life or limb can occur, from road traffic accidents to health crises to natural disasters etc.), work on interoperability, crisis management etc. which is not threat-specific, is better served by those longer-term larger budgets that also tackle things like institutional reforms. This would liberate CT money to focus on protective security that specifically relates to vulnerability to terrorist attack, terrorist incident first response etc., weighted in favour of protective security rather than attack response (because attack response would be covered by other UK support that is not part of CT).
- Consider different approaches in countries where the PSARP struggled, attempting to unblock progress, without withdrawing.