CSSF Annual Review/Programme Completion Review (23/24)
# A. Summary Sheet
Programme Title	Africa Cyber Programme: Phase 1 (Financial Year: 2023-2024)
Country and Region	Africa
Programme ID	C-CYB-0006	IATI Unique ID	CSSF-14-000005
Start date	April 2023	End date	March 2026
HMG Partners / (Lead department in bold)	FCDO
	Total overall Programme Allocation (e.g. 3 years)	Allocation FY2023/24	Spend FY 2023/24
ODA	1 year	£4.5m	£4.5m
Non-ODA	-	-	-
Total	1 year (ACP I was the successor to the Digital Access Programme in Kenya, South Africa & Nigeria)	£4.5m	£4.5m

## Outputs
Output statements	Individual Output Rating
Cyber hygiene benchmarking research on businesses for the Government of Nigeria.	4
Critical National Infrastructure (CNI) protection workshops, training and the development of a sectoral framework to the Government of Nigeria.	4
Digital forensics and evidence handling training for Judges, Prosecutors and Specialist Law Enforcement Officers for the Government of Nigeria.	4
A Cyber Support Package of Cyber Diplomacy Training to the African Union.	4
The Africa Joint Operations Against Cybercrime (AFJOC) project.	4
Digital Forensics and International Protocols training for the South African Police Service (SAPS).	4
Cybercrime training for South African Police Service recruits, including Train the Trainer sessions.	4
Cyber training for underprivileged school leavers in South Africa.	4
Incident response training to the Government of Kenya.	4
Digital forensics and evidence handling training for judiciary and state prosecution of the Government of Kenya.	4
Educating Kenyan citizens on how to protect themselves against cyber harms.	4
Overall Rating of Output Delivery	4

## Outcomes
Outcome statement(s)
Increased cyber maturity and threat awareness of partner countries better protects national and UK CNI. Increasing likeminded on cyber security internationally.
Better co-ordinated national-level and international responses to cyber threats in Africa. Improved cyber skills for more inclusive digital development in Africa.
Outcome Assessment	The Africa Cyber Programme aimed to improve national-level and international awareness of and responses to cyber threats across Africa. It sought to achieve this this through three main avenues: / Building law enforcement awareness of digital forensics, cyber-crime legislation and encouraging operational best practices in cyber-crime investigations, including through supporting Interpol led operations to identify cyber criminals and compromise criminal technical infrastructure. / Building national cyber resilience in Kenya, Nigeria and South Africa whilst delivering support across the continent through Interpol and the African Union. This has included CNI protection, benchmarking industry maturity and supporting national cyber hygiene. / Delivering cyber diplomacy training to the African Union, through promotion of UN frameworks and the UK’s vision of responsible state behaviour in cyberspace, encouraging regional multi-lateral cooperation on international cyber governance.
Overall Outcome Progress Rating:		On Track (Amber)
Overall Risk Rating:		Amber (Medium)

## Summary of Programme Performance
Year	2021/22		2022/23		2023/24
	Output	Outcome	Output	Outcome	Output	Outcome
Programme Rating			3	Amber	4	Amber
Risk Rating			Medium		Medium
Notes: Output/Outcome score

## What Support Did the UK Provide in FY 23/24?
- Capability development within law enforcement and judicial systems, to counter cyber-enabled and cyber-dependant criminal activity in the region delivered across Kenya, Nigeria, and South Africa. This involved 5 separate training projects focusing on digital evidence handling and application of cyber crime legislation.
- The Africa Joint Operations Against Cybercrime (AFJOC) project and the African Union Cyber Support Package. AFJOC delivered cross-jurisdictional operations, cyber working groups and tabletop exercises which have involved law enforcement entities from over 40 African countries.
- Critical National Infrastructure (CNI) support within Kenya and Nigeria through the development of CNI sector cyber security guidance in Nigeria and the use of incident response training and Table-top exercises.
- Cyber hygiene and skills development projects in Kenya, Nigeria and South Africa to improve cyber security awareness, baseline cyber maturity within Small to Medium enterprises and provide access to cyber security skills and qualifications to underprivileged students.

## Key Results for FY 23/24
- The programme achieved almost all of its outputs and initiated Monitoring, Evaluation and Learning through an independent third-party.
- The programme moved successfully from the Digital Access Programme under the Conflict, Stability and Security Fund, realigning its strategic outcomes successfully.
## Key Lessons:
- To continue to deliver on its outcomes, the programme may look to increase its focus on hardening Critical National Infrastructure and wider Public Sector resilience through technical-led capacity building.
- Amendments should be made to the current Monitoring, Evaluation, Reporting and Learning (MERL) process to set clear, uniform programme-level outcomes across all projects and to centrally maintain and monitor the delivery of these throughout the programme cycle.
- There are opportunities to drive value-for-money efficiencies through adaptions to the programme design that places more emphasis on local commissioning and project management.
- OSJAs are required to be in place for all projects prior to delivery starting.

## Key Recommendations for FY 23/24:
- Continue to monitor outcomes from this phase of delivery throughout its next iteration and up until March 2026 as a minimum timeline to ensure a more comprehensive assessment of its impact.
- Ensure that programme outputs and outcomes are all defined with clear indicators, and when adaptions are made there is a record outlining the reason and date.
- Involve wider technical expertise in the programme on project design and programme governance.
- Consider directly procuring local suppliers where appropriate to improve efficiency and Value for Money.
- Ensure a tactical pot of programme funds is used to fund agile projects and cannot be used to cover wider programme spend.
- Consider reviewing programme governance to ensure clear roles and responsibilities between the FCDO, implementing partners and associated subcontractors are defined.
- Broaden the types of risks being monitored, to include human rights, conflict dynamics and fiscal risks.
- Utilise a financial forecasting and spends incurred spreadsheet to capture all information in one dashboard, so that there is an up-to-date record of all finances.