CSSF Annual Review/Programme Completion Review (23/24)
# A. Summary Sheet
Programme Title	Georgia Cyber Programme
Country and Region	Georgia, EECAD
Programme ID	C-CYB-0007	IATI Unique ID	CSSF-14-000006
Start date	February 2022	End date	March 2025
HMG Partners / (Lead department in bold)	FCDO
	Total overall Programme Allocation (e.g. 3 years)	Allocation FY2023/24	Spend FY 2023/24
ODA	£0	£0	£0
Non-ODA	£4.2m	£2m	£1,825,009
Total	£4.2m	£2m	£1,825,009

## Outputs
Output statements	Individual Output Rating
(No. and statement)
Enhanced Information and Cyber Department (ICD) capacity to perform core functions.	3
1.2 ICD capable of using National Cyber Security Strategy (NCSS) project progress tracker.	1
1.3 Office for National Security Council (ONSC) hosted International donor coordination meetings.	4
2.1 Georgian Cyber Public-Private sector forum.	4
2.2 Process for awareness campaign’s apps, games and software that pose a threat to user community safety is agreed by Digital Governance Agency (DGA) and other actors.	4
2.3 Mechanisms for cybersecurity information sharing within Georgian policy and law. Guidance provided to pass secondary legislation in support of ISF.	4
2.4 Information exchange platform between core stakeholders and selected secondary stakeholders.	3
2.5 National Malware Information Sharing Platform (MISP) network accessed by key stakeholders.	3
2.6 Cyber Security Information Sharing Policy produced to enable communication with international partners.	3
3.1 Content that drives awareness of cyber threats and encourages good cyber hygiene is created.	4
3.2 Community events that support the development of / the campaign strategy.	4
3.3 Promotion of cyber threats / impacts and hygiene practices.	4
4.1 Women working in professions related to cyber supported through events, networks and training.​	4
4.2 Cyber career awareness and support events conducted to school and university students.	4
4.3 Women-specific cyber awareness content produced and disseminated.​	4
Overall Rating of Output Delivery	4

## Outcomes
Outcome statement(s)
National Cyber Security Strategy (NCSS) is implemented in line with the schedule and performance measures set out in the NCSS Logframe.
Core agencies* are more aware of cyber incidents affecting other agencies/government departments and better able and motivated to spot national scale incidents. Cyber security communication between private sector, government and the public, and public awareness of cybersecurity issues is raised.
Georgian public, including journalists, CSOs and vulnerable groups (Women and Children) can better protect themselves against cyber threats.
Georgia has a stronger and more diverse cybersecurity workforce.
Outcome Assessment	The second year of the Georgia Cyber Programme has been productive, with many of the previous Annual Review Recommendations having been put in place with tangible benefits seen as a result. / Solid progress towards outcomes has been clearly evidenced during the review, however, there is still work to be done on refining outcomes so that they are more reflective of work being done considering the shifting, changing and challenging context.
Overall Outcome Progress Rating:		Amber/Green
Overall Risk Rating:		Medium-Low

## Summary of Programme Performance
Year	2022/23		2023/24		2024/25
	Output	Outcome	Output	Outcome	Output	Outcome
Programme Rating	3	Amber	4	Amber/Green
Risk Rating	Amber		Medium-Low

## What Support Did the UK Provide in FY 23/24?
- Building Capability for implementation of Georgian National Cyber Security Strategy
- Development of an Incident Management Framework and Information Sharing Strategy
- Continued assistance in raising public cyber awareness
- Support to women working (and those wishing to work) in professions related to cyber

## Key Results for FY 23/24
- Public Campaign for raising awareness of cyber-crime and the need for cyber hygiene
- Regional tours delivered to engage young people to consider careers in cyber
- Legislation drafted to allow the use of the information sharing framework
- Effective cross HMG collaboration to deliver events such as Defence Cyber Marvel (DCM3) and Cyber UK
- Georgian Cyber Public Private Partnership (GCPPP) forums held

## Key Lessons:
- The Programme team have utilised the local Implementing Partner to greatest extent possible, using their links to the beneficiary authorities (helping to avoid misunderstanding and head off implementation problems)
- There has been clear engagement between beneficiaries and implementing partners with early and frequent face to face contacts to help understand local culture and working practices

## Key Recommendations for FY 23/24:

- The Results Framework was redesigned in FY23/24 and, while the resulting document is comprehensive and detailed, there is still a need for milestones/targets to accurately map to outputs and for better Gender Equality and Social Inclusion (GESI) reporting. For greater confidence and Value for Money (VfM) in Y3, there needs to be increased evidence of the implementer using the new RF consistently, adaptively, and as a base to collate relevant evidence using data gathered from across the consortium.
- When considering the future sustainability and deliverability of Women in Cyber (WiC) activity in the context of the Foreign Agents Law (FAL), the review team suggest that the programme team consider the full range of options available in pursuit of the overall workstream outcomes and intended impact, from winding down UKGCP involvement in delivery of WiC and pivoting funding elsewhere, to using Skillwill’s involvement to scale back funding of internships and refocus activities on outreach to new audiences and network building.
- Consider further opportunities for 'integrated' delivery, for example opportunities presented through existing work under the Global Cyber Programme (World Bank Cybersecurity Multi-donor Trust Fund, Shadowserver, MOD Defence Cyber Marvel), wider Cyber Policy Department opportunities and regional join up (VfM).
- The review team recommend that the Programme Team strongly consider if the Prime/Sub Prime model is the best way to approach this type of programming when considering next steps beyond Year 3.
- Feed into the Activity Based Budget (ABB) template design process led by Integrated Security Fund Unit (ISFU) Commercial Working Group.
- Carry out a Joint Assessment of Conflict Sensitivity (JACS) process to consider Conflict Sensitivity in relation to cyber activities.
- Carry out a Climate Assessment of the programme in relation to cyber activities.
- Commission the contracted mid-point evaluation from TAG, adjusting the scope/question as required.