CSSF Annual Review (23/24)
# A. Summary Sheet
Programme Title	Global Cyber Programme (GCP)
Country and Region	Global: Latin America and Caribbean; Middle East; Commonwealth
Programme ID	C-CYB-003	IATI Unique ID	CSSF-14-000001
Start date	April 2022	End date	March 2025
HMG Partners / (Lead department in bold)	Foreign, Commonwealth and Development Office (FCDO), Ministry of Defence (MOD), Home Office (HO)
	Total overall Programme Allocation (e.g. 3 years) £m	Allocation FY2023/24 £m	Spend FY 2023/24 £m
ODA	10.6	4.2	6.2
Non-ODA	9.85	2.35	1.9
Total	20.45	6.55	8.1

## Outputs
Output statements	Individual Output Rating
Improved knowledge and skills around cyber diplomacy, threat intelligence, cybersecurity standards, cybercrime legislation, prevention and response	4
Tools, techniques and frameworks for cyber threat diagnosis, prevention and response	4 / 3
Improved capacity to deliver awareness-raising and educational initiatives to the public	4
Improved awareness and understanding of key cyber risks and issues of concern, including the strengths, weaknesses and gaps of countries’ cyber frameworks and capacity	4
Networks for peer learning, information-sharing and collaboration between private and government actors developed	4
Partnerships and coordination mechanisms between bilateral and regional government actors developed	4 / 3
Overall Rating of Output Delivery	4

## Outcomes
	Outcome statement(s)
Partner governments, law enforcement agencies and police effectively detect, report, respond to and mitigate risks and cyber threats
(Intermediate outcome) Partner governments and multilateral organisations strengthen and implement cybersecurity policies, frameworks and strategies
Private citizens and organisations are more cyber-literate, have better cyber hygiene, and better protect themselves from cyber risks
Increased coordination, cooperation, strategic planning and knowledge exchange on cybersecurity by partner governments and multilateral organisations, such as the Commonwealth
UK leadership in global cybersecurity demonstrated and UK influence in the cyber domain is increased (including on Gender Equality and Social Inclusion (GESI) considerations)
	Outcome Assessment	There is evidence the programme is delivering desired changes at outcome level in specific countries. Oman is a good example. There is evidence that with development of second order support (or similar) then delivering more desired changes at outcome level is possible. The provision of an evidence base (e.g. live data or Cyber Maturity Model (CMM) reports) supports this. Including being mindful of the previous annual review (and progress made since then), taking into account those parts of the programme that remain unmeasured, the overall outcome assessment is Amber.
	Overall Outcome Progress Rating:		Amber
	Overall Risk Rating:		Medium

## Summary of Programme Performance
Year	2021/22		2022/23		2023/24
	Output	Outcome	Output	Outcome	Output	Outcome
Programme Rating	N/A	N/A	3	Amber	4	Amber
Risk Rating	N/A		Medium		Medium

## What Support Did the UK Provide in FY 23/24?

In FY23/24, there was a continuation of existing multiyear agreements on the UK-Oman Digital Hub, on India Fellowships (albeit handed over to the India Programme during the course of the year, as a better fit), and with the OSCE. However, the programme took forward established activities with new phases of work on:

- Training cyber diplomats,
- Building Brazil’s national cyber security curriculum,
- Defence Cyber Exercising.
- The GCP continued work cybercrime with the UN Office in Drugs and Crime (UNODC) but tilted to a focus on online child sexual exploitation and abuse; and
- Cybercrime work with the Commonwealth Secretariat brought in a new focus on AI.
- Long running activity was refreshed with Oxford University, and in supporting the Global Forum on Cyber Expertise (GFCE).
- A new CMM assessment was conducted in Brazil.
- Work on cyber hygiene was scaled up over the year.
- Significant new activity on cyber threat intelligence and in joining the World Bank Cyber Trust Fund was brought online in quarter four of financial year (Q4).

## Key Results for FY 23/24:

The programme delivered in full across projects in FY23/24, as well as onboarding two significant projects in Q4. Strong improvements were made across programme governance and on Monitoring, Evaluation, Research and Learning (MERL).  The programme produced 11 change stories covering awareness building on cyber threats, catalysing global action, improving cyber strategy and values and increasing the resilience of partner countries to respond to cyber threats. Key achievements included:
- Increasing shared values on national cyber security in the Central Asia region (OSCE)
- Decreasing the threat window of vulnerabilities to application delivery controllers through showcasing UK funded threat reporting to strengthen the resilience of Cyber Security Incident Response Teams (CSIRTs) (Shadowserver)
- Catalysing global action through the Global Conference on Cyber Capacity Building in Ghana – GC3B. Including the adoption of a common set of Cyber Capacity Building (CCB) Principles, sharing of Africa best practice in relation to CCB and the signing of an MOU between GFCE and the United National Economic Community of Africa. (GFCE)
- Improving national governance mechanisms in Oman through the creation and implementation of a workforce cyber strategy (PLEXAL)
- Increasing diplomatic efforts using the Cyber Deterrence Toolkit (FCDO)
- Building awareness of cyber threats in the Caribbean and Rwanda (Get Safe Online)
- Improving awareness of cyber threats in Omani start-up companies (PLEXAL)
- Improving cyber education in Oman by embedding the workforce cyber strategy requirements into higher education courses. (PLEXAL)
- Catalysing global action through the Global Conference on Cyber Capacity Building through collecting and itemising the pledges made at the GC3B conference (GFCE)
- Improved ability to respond to cybercrime in Latin America (UNODC)
- Building awareness of cyber threats in Rwanda through its Ambassador Programme (Get Safe Online)

## Key Lessons:

Building on considerable informal learning in the programme, the programme understands the need to share and receive learning more widely. So, it has learned there is real benefit from sharing and receiving learning: from other similar programmes (e.g. by theme (cyber or risk); by activity (e.g. conferences and events, training); by programme outside cyber portfolio (e.g. Integrated Security Fund (ISF) Central Asia).

The programme has learnt that, in achieving global breadth with limited resources, there are trade-offs to be made. The programme is aware that utilising the risk register in line with ISF guidance will help inform the SRO and other stakeholders of the increased risk from main trade-offs.

Funding timing can have considerable impact on delivery in the financial year the activity is planned to take place. The programme recognises the impact of timing related to funding, and that it has consequences for implementers and delivery, with an associated increase in the administrative burden (e.g. no cost extensions).

## Key Recommendations for FY 23/24:

A technical review is needed covering the Shadowserver Q4 Sprint outputs and to understand better the link to impact. A qualified external hire, on a SMART contract, is best placed to quality-assure what was bought for £1.065m.

Timing: The qualified external hire should be in place as soon as possible.

The programme should review its commercial skills level. If necessary, FCDO Commercial can run a three-day training course, which can be inclusive of others in the Cyber Portfolio, that includes pre-market engagement and contract management / commercial awareness.

Timing: The commercial skills review should be completed by October 2024.

To prioritise projects that have a measurable tangible return beyond the short term and that lead to downstream change, utilising MERL resources in support, with clearly assessed capacity of beneficiaries at the beginning and end of a project.

Timing: By March 2025.

Deliver a GESI analysis at programme level, working with experts to deliver the analysis. In this context, the programme team should frame the analysis around a specific problem for prioritisation, being clear about the programme’s definition of GESI. The GESI analysis should then be used to inform project planning and implementation with the ambition to inform a future Category E project.
Timing: By March 2025.
Project-level measurement of progress against gender equality outcomes for all projects using the GESI marker process.

Timing: By March 2025.